## Sprint Metrics Template
Team Name
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates
Sprint Name
Total Effort In the Sprint
Commited
Emerged
Emerged Rate | 0%
Done Bug Effort
Commited Bug Effort
Emerged Bug Effort
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort
All Tasks Done Effort
Released Effort
Undone PBI Effort
Comitted Releasable Dev Tasks
Sprint Goal
Goal Achieved (0/1) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 0%
Bug/Development Ratio | 0%
Shipping Accuracy | 0%
Partner Focus
Bug Score
Sprint Goal Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Individual Committed Effort
Individual Done Effort
Note on A1: https://winsider.atlassian.net/browse/SD-105246 https://winsider.atlassian.net/browse/SD-105248 https://winsider.atlassian.net/browse/SD-104609 https://winsider.atlassian.net/browse/SD-105242 https://winsider.atlassian.net/browse/SD-105241 -Berna Ertenli
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A31: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
ATTENTION
Please right-click on this tab, duplicate, and rename it for your team.
Do not remove rows, use “hide rows” instead.
Do not add any rows above the 28th row, you can add them below the colored metrics.

## Sprint Metrics Details
Metric | Calculation | Status | Description
Dev Tasks Done Effort | Improvement + New Feature + Bug + Security + Tech Debt | Depends on the teams "done definition" (Waiting for Release, Pending for Release, Ready for Release, Done) after UAT status | Only the following type of tasks are included: Improvement + New Feature + Bug + Security + Tech Debt
All Tasks Done Effort | All tasks | Depends on the teams "done definition" (Waiting for Release, Pending for Release, Ready for Release, Done) after UAT status
Released Effort | Improvement + New Feature + Bug + Security + Tech Debt | Done + Released on Prod | Waiting for Release, Pending for Release, Ready for Release states are NOT included within this metric
Undone PBI Effort | All undone tasks | To Do, In Progress, In Testing etc.
Comitted Releasable Dev Tasks | Improvement + New Feature + Bug + Security + Tech Debt | - | Releaseble dev tasks effort that's been commited for that sprint
Shipping Accuracy | Released Effort / Dev Tasks Done Effort | - | Focuses on the percentage of work that has been released and is available on production for partners and end-users to utilize or available for test partners such as inshoppingcart
Plan Accuracy | All Done Tasks Effort / Commited | - | Measures the percentage of work that a team successfully completes out of the tasks they committed to during sprint planning, providing visibility into their ability to deliver on commitments.
Bug/Development Ratio | Bug / All Done Tasks Effort | - | Aims to calculate the percantege of the bug effort out of all the tasks and shows how much the team focuses on the bugs in the long term
Partner Focus Ratio | Comitted Releasable Dev Tasks / Commited All Tasks | - | Calculates the percentage of deployable tasks out of all planned tasks, helps emphasize the importance of delivering value to the customer Hint: This metric should be calculated as the final stage of sprint planning and filled in the sprint metrics sheet
Number of Team Member Participation | If designers are included in the sprint, half of the whole team (dev+designers)
If designers run separete sprint, half of the developers
Sprint Goal Effort | Calculated from the development sprint goal tasks. (QA & Design tasks are not included)
For Vikings and Kraken, include the Design Sprint goal as comment to the sheet. +Design System take design tasks as Sprint Goal

## Atrium
Atrium
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 | [6 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 28-12-2023 ¦ 10-01-2024 | 11-01-2024 ¦ 24-01-2024 | 25-01-2024 ¦ 07-02-2024 | 08-02-2024 ¦ 21-02-2024 | 22-02-2024 ¦ 06-03-2024 | 07-03-2024 ¦ 20-03-2024 | 21-03-2024 ¦ 09-04-2024 | 15-04-2024 ¦ 17-04-2024 | 18-04-2024 ¦ 01-05-2024 | 02-05-2024 ¦ 16-05-2024 | 17-05-2024 ¦ 29-05-2024 | 30-05-2024 ¦ 12-06-2024 | 13-06-2024 ¦ 26-06-2024 | 27-06-2024 ¦ 10-07-2024 | 11-07-2024 ¦ 24-07-2024 | 25-07-2024 ¦ 07-08-2024 | 08-08-2024 ¦ 21-08-2024 | 22-08-2024 ¦ 09-09-2024 | 09-09-2024 ¦ 19-09-2024 | 20-09-2024 ¦ 09-10-2024 | 10-10-2024 ¦ 23-10-2024
Sprint Name | AT Sprint 135 - 23Q4-7 | AT Sprint 136 - 24Q1-1 | AT Sprint 137 - 24Q1-2 | AT Sprint 138 - 24Q1-3 | AT Sprint 139 - 24Q1-4 | AT Sprint 140 - 24Q1-5 | AT Sprint 141 - 24Q1-6 | AT Sprint 142 - 24Q2-1 | AT Sprint 143 - 24Q2-2 | AT Sprint 144 - 24Q2-3 | AT Sprint 145 - 24Q2-4 | AT Sprint 146 - 24Q2-5 | AT Sprint 147 - 24Q2-6 | AT Sprint 148 - 24Q3-1 | AT Sprint 149 - 24Q3-2 | AT Sprint 150 - 24Q3-3 | AT Sprint 151 - 24Q3-4 | AT Sprint 152 - 24Q3-5 | AT Sprint 153 - 24Q3-6 | AT Sprint 154 - 24Q3-7 | AT Sprint 155 - 24Q1-7
Total Effort In the Sprint | 166 | 197 | 193 | 199 | 202 | 318 | 286 | 81 | 224 | 239 | 214 | 175 | 97 | 233 | 213 | 199 | 91 | 277 | 216 | 296
Commited | 152 | 174 | 177 | 185 | 178 | 182 | 169 | 63 | 193 | 143 | 166 | 163 | 81 | 202 | 203 | 161 | 77 | 269 | 179 | 230 | 266
Emerged | 14 | 23 | 16 | 14 | 27 | 136 | 117 | 18 | 31 | 96 | 48 | 12 | 16 | 31 | 10 | 38 | 14 | 8 | 37 | 66
Emerged Rate | 8.434% | 11.68% | 8.29% | 7.035% | 13.37% | 42.77% | 40.91% | 22.22% | 13.84% | 40.17% | 22.43% | 6.857% | 16.49% | 13.3% | 4.695% | 19.1% | 15.38% | 2.888% | 17.13% | 22.3%
Done Bug Effort | 7 | 22 | 14 | 18 | 29 | 60 | 22 | 5 | 56 | 29 | 44 | 16 | 21 | 27 | 22 | 41 | 16 | 15 | 17 | 52
Commited Bug Effort | 27 | 17 | 13 | 15 | 28 | 45 | 36 | 22 | 60 | 72 | 30 | 33 | 16 | 44 | 17 | 7 | 11 | 9 | 7 | 36 | 23
Emerged Bug Effort | 4 | 10 | 6 | 8 | 14 | 34 | 4 | 3 | 13 | 16 | 14 | 2 | 5 | 7 | 10 | 34 | 5 | 6 | 10 | 16
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 106 | 153 | 140 | 117 | 134 | 198 | 209 | 38 | 148 | 115 | 137 | 83 | 40 | 69 | 137 | 90 | 72 | 58 | 93 | 111
All Tasks Done Effort | 106 | 153 | 140 | 117 | 134 | 198 | 209 | 38 | 148 | 115 | 137 | 83 | 40 | 69 | 137 | 90 | 72 | 58 | 93 | 111
Released Effort | 56 | 67 | 67 | 91 | 96 | 164 | 134 | 21 | 109 | 101 | 124 | 29 | 14 | 50 | 56 | 68 | 45 | 50 | 50 | 47
Undone PBI Effort | 46 | 21 | 37 | 68 | 44 | -16 | -40 | 25 | 45 | 28 | 29 | 80 | 41 | 133 | 66 | 71 | 5 | 211 | 86 | 119
Comitted Releasable Dev Tasks
Sprint Goal | 1- Applying cache for product_id case: Not Done 2- Completing half the post-incident action tasks : Not Done | 1- Completion of all post-incident tasks in the sprint : Done | 1- Complete web push tasks Tasks: *AT-5903 Status: Done 2- GLU Migration Test Completion Tasks: *AT-6040 Status: Done | 1 - Group Level Tasks to be completed Tasks: *AT-6180 *AT-6165 *AT-6179 *AT-6178 2- Product_id tasks to be completed Tasks: *AT-5842 *AT-6165 *AT-5890 | 1 - Watsons task to be finished *AT-6319 *AT-6320 *AT-6027 *AT-6291 *AT-6308 *AT-6190 *AT-6310 | 1- Region Queues to be separated *AT-6568 *AT-6596 *AT-6486 *AT-6591 | 1- Web Suite Tech Design Task Support *AT-6573 Status: Done 2- Double Cloud with S3 *AT-6709 *AT-6476 Status: Done | 1- Hepsiburada shard migration to be finalized *AT-6808 | 1 - Finishing all S3 related tasks *AT-6809 *AT-6847 Status: Done 2 - Finishing Hepsiburada tasks *AT-6863 *AT-6864 Status: Done | NOTE Sprint goal has changed during the sprint aligning with our stakeholders due to partner urgency | 1- Finishing expressions tech design *AT-7140 | 1 - Completing Expressions Tasks *AT-7251 *AT-7249 *AT-7250 *AT-7255 *AT-7252 Status: Done 2 - Region S3 implementation *AT-6995 Status: Not Done | 1 - Multi Device *AT-7165 Status: Not Done 2- Suppression DB *AT-6612 Status: Not Done | 1- Expression Tasks Status: Not Done 2- New Data Structure Tasks Status: Not Done | 1 - Suppression DB: Done 2- New KR alignment: Done | 1 - Suppression DB Status: Not Done 2 - Treasure Hunt Status: Not Done | 1- Query templates and new scenarios coverage Status: Done | 1.We're going to finish our KR's items (Read task and Comparison task). Status: Not Done | 1.We're going to finish our KR's items Status: Not Done | 1.We're going to finish our KR's items | 1. Prod migration 10 partners. 2. Comparison of events & attributes 3. Complete fork work -Flagged TH tasks
Sprint Goal Efforts | 49 | 59 | 21 | 38 | 33 | 110 | 68 | 13 | 44 | 59 | 89 | 41 | 16 | 113 | 63 | 78 | 21 | 76 | 71 | 61 | 64
Sprint Goal KR Efforts
Goal Achieved (0/1) | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 69.74% | 87.93% | 79.1% | 63.24% | 75.28% | 108.8% | 123.7% | 60.32% | 76.68% | 80.42% | 82.53% | 50.92% | 49.38% | 34.16% | 67.49% | 55.9% | 93.51% | 21.56% | 51.96% | 48.26% | 0%
Bug/Development Ratio | 6.604% | 14.38% | 10% | 15.38% | 21.64% | 30.3% | 10.53% | 13.16% | 37.84% | 25.22% | 32.12% | 19.28% | 52.5% | 39.13% | 16.06% | 45.56% | 22.22% | 25.86% | 18.28% | 46.85% | 0%
Shipping Accuracy | 52.83% | 43.79% | 47.86% | 77.78% | 71.64% | 82.83% | 64.11% | 55.26% | 73.65% | 87.83% | 90.51% | 34.94% | 35% | 72.46% | 40.88% | 75.56% | 62.5% | 86.21% | 53.76% | 42.34% | 0%
Partner Focus
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 32.24% | 33.91% | 11.86% | 20.54% | 18.54% | 60.44% | 40.24% | 20.63% | 22.8% | 41.26% | 53.61% | 25.15% | 19.75% | 55.94% | 31.03% | 48.45% | 27.27% | 28.25% | 39.66% | 26.52% | 24.06% |  | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 30% | 100% | 70% | 85% | 85% | 100% | 100% | 85% | 85% | 100% | 100% | 85% | 0% | 30% | 100% | 30% | 85% | 15% | 30% | 15% | 15% |  | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [13 empty] | 30% | 100% | 30% | 100% | 30% | 30% | 15% | 15%
Individual Committed Effort
Cem Sancak | 27 | 35 | 31 | 33 | 21 | 34 |  | 18 | 58 |  |  | 56 | 19 | 98 |  | 39 | 23 | 36 | 24 | 26 | 39
Evren Baykan | [13 empty] | 11 |  | 21 | 9 | 42 | 36 | 35 | 26
Furkan Kahveci | 37 | 37 | 36 | 40 | 42 | 38 |  | 13 | 32 |  |  | 30 | 3 | 19 |  | 26 | 19 | 43 | 36 | 38 | 44
Orhan Yediyıldız | 29 | 31 | 34 | 37 | 36 | 42 |  | 11 | 33 |  |  | 22 | 24 | 21 |  | 38 | 15 | 65 | 15 | 37 | 36
Uğur Eski | 27 | 44 | 39 | 38 | 34 | 36 |  | 13 | 36 |  |  | 26 | 19 | 30 |  | 23 | 11 | 39 | 30 | 44 | 43
Yunus Ağtaş | 32 | 37 | 37 | 37 | 45 | 32 |  | 8 | 34 |  |  | 29 | 17 | 23 |  | 14 | - | 38 | 38 | 50 | 57
Ömer Özmen | [20 empty] | 21
Büşra Ayaksız | [20 empty] | 16
Mertcan Taşkın | [20 empty] | 14
Ali Çebi | [20 empty] | 10
Furkan Tök | [20 empty] | 9
Individual Done Effort
Cem Sancak | 20 | 36 | 12 | 10 | 12 | 40 |  | 20 | 25 |  |  | 5 | 1 | 4 | 50 | 0 | 23 | 1 | 5 | 3
Evren Baykan | [14 empty] | 4 | 13 | 14 | 0 | 20 | 27
Furkan Kahveci | 34 | 24 | 32 | 43 | 45 | 36 |  | 5 | 38 |  |  | 24 | 3 | 10 | 35 | 34 | 17 | 19 | 36 | 33
Orhan Yediyıldız | 24 | 33 | 37 | 16 | 36 | 16 |  | 1 | 32 |  |  | 13 | 16 | 13 | 18 | 5 | 7 | 12 | 10 | 14
Uğur Eski | 19 | 47 | 29 | 22 | 25 | 14 |  | 0 | 29 |  |  | 21 | 5 | 33 | 10 | 21 | 11 | 13 | 18 | 18
Yunus Ağtaş | 13 | 13 | 22 | 26 | 16 | 97 |  | 12 | 37 |  |  | 20 | 15 | 9 | 20 | 17 | - | 13 | 4 | 16
Büşra Ayaksız
Mertcan Taşkın
Ali Çebi
Furkan Tök
PO Happiness | -1 | 1 | 1 | 1 | 0 |  | 0 |  | 1 |  |  | - | 1 | 0 | 1 | 0 | 1 | 0 | 0 | -1
Team Happiness | 0 | 1 | 1 | 0 | 0 |  | 0 |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -1
Customer Happiness about PM
Team Happiness about PM | 0 | 1 | 1 | 1 | 1 |  | 0 |  | 1 |  |  | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0
Note on A7: Commited+Emerged
Note on A12: All done columns /bug based
Note on A13: Sprint report check without "*"
Note on A14: Sprint report check with "*"
Note on A19: All done column on board
Note on A20: Released And Done Tasks
Note on A26: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A34: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on B69: Yigit: - Burcin: -1
Note on B70: Busra: 0 Ugur: -1 Yunus: 0 Cem: 0 Mertcan: 0 Furkan: 0 Orhan: 0
Note on B72: Burçik ve Yiğit Busra: 0 Ugur: -1 Yunus: 0 Cem: 0 Mertcan: 0 Furkan: 0 Orhan: 0
Note on C69: Yigit: 1 Burcin: 1
Note on C70: Busra: 1 Ugur: 1 Yunus: 0 Cem: 0 Mertcan: 1 Furkan: 0 Orhan: 1
Note on C72: Burçik ve Yiğit Busra: 1 Ugur: 1 Yunus: 0 Cem: 1 Mertcan: 1 Furkan: 1 Orhan: 1
Note on D69: Yigit: 1 Burcin: 1
Note on D70: Busra: 1 Ugur: 1 Yunus: 1 Cem: - Mertcan: 0 Furkan: 1 Orhan: 1
Note on D72: Burçik ve Yiğit Busra: 1 Ugur: 1 Yunus: 1 Cem: - Mertcan: 1 Furkan: 1 Orhan: 1
Note on E69: Yigit: 1
Note on E70: Busra: 0 Ugur: 1 Yunus: 0 Cem: 0 Mertcan: 1 Furkan: 0 Orhan: 1
Note on E72: Busra: 1 Ugur: 1 Yunus: 1 Cem: 1 Mertcan: 1 Furkan: 1 Orhan: 1
Note on F69: Yigit: 0
Note on F70: Busra: 0 Ugur: 0 Yunus: 0 Cem: 0 Mertcan: 1 Furkan: 0 Orhan: 1 Alican: 1
Note on F72: Busra: 1 Ugur: 0 Yunus: 1 Cem: 1 Mertcan: 1 Furkan: 1 Orhan: 1 Alican: 1
Note on G69: Yigit:
Note on G70: Busra: Ugur: Yunus: Cem: Mertcan: Furkan: Orhan: Alican:
Note on G72: Busra: Ugur: Yunus: Cem: Mertcan: Furkan: Orhan: Alican:
Note on H69: Yigit: 0
Note on H70: Busra: -1 Ugur: -1 Yunus: 0 Cem: 0 Mertcan: -1 Furkan: 0 Orhan: 0 Alican: 0
Note on H72: Busra: 0 Ugur: 0 Yunus: 0 Cem: 0 Mertcan: 1 Furkan: 0 Orhan: 0 Alican: 1
Note on I69: Yigit: Selin:
Note on I70: Busra: Ugur: Yunus: Cem: Mertcan: Furkan: Orhan: Alican:
Note on I72: Busra: Ugur: Yunus: Cem: Mertcan: Furkan: Orhan: Alican:
Note on J69: Yigit: 1 Selin: 1
Note on J70: Busra: 1 Ugur: 0 Yunus: 1 Cem: 1 Mertcan: - Furkan: 1 Orhan: 1 Alican: 1
Note on J72: Busra: 1 Ugur: 0 Yunus: 1 Cem: 1 Mertcan: - Furkan: 1 Orhan: 1 Alican: 1
Note on K69: Yigit: Selin:
Note on K70: Busra: Ugur: Yunus: Cem: Mertcan: Furkan: Orhan: Alican:
Note on K72: Busra: Ugur: Yunus: Cem: Mertcan: Furkan: Orhan: Alican:
Note on L5: hepsiburada ve incident sprinti -Ugur Eski
Note on L69: Yigit: Selin:
Note on L70: Busra: Ugur: Yunus: Cem: Mertcan: Furkan: Orhan: Alican:
Note on L72: Busra: Ugur: Yunus: Cem: Mertcan: Furkan: Orhan: Alican:
Note on M69: Yigit: - Selin: -
Note on M70: Busra: - Ugur: 1 Yunus: 1 Cem: 1 Mertcan: 1 Furkan: - Orhan: 1 Alican: 1
Note on M72: Busra: - Ugur: 0 Yunus: 1 Cem: 0 Mertcan: 0 Furkan: - Orhan: 0 Alican: 1
Note on N69: Yigit: 1 Tugrul: -
Note on N70: Busra: 0 Ugur: 0 Yunus: 0 Cem: 0 Mertcan: 0 Furkan: - Orhan: 0 Alican: 0
Note on N72: Busra: 1 Ugur: 0 Yunus: 0 Cem: 1 Mertcan: 1 Furkan: - Orhan: 1 Alican: 1
Note on O69: Yigit: 0 Tugrul: 0
Note on O70: Busra: - Ugur: 0 Yunus: 0 Cem: - Mertcan: -1 Furkan: 0 Orhan: 1 Alican: -1
Note on O72: Busra: - Ugur: 0 Yunus: 0 Cem: - Mertcan: 1 Furkan: 1 Orhan: 1 Alican: 1
Note on P69: Yigit: 1 Tugrul: 1
Note on P70: Busra: 0 Ugur: 0 Yunus: 0 Cem: 1 Mertcan: 0 Furkan: 1 Orhan: 1 Alican: 0 Evren:
Note on P72: Busra: 0 Ugur: -1 Yunus: 0 Cem: 0 Mertcan: 1 Furkan: 0 Orhan: 1 Alican: 1
Note on Q69: Yigit: 0 Tugrul: 1
Note on Q70: Busra: 0 Ugur: 0 Yunus: - Cem: -1 Mertcan: 0 Furkan: 1 Orhan: 1 Evren: 0
Note on Q72: Busra: 0 Ugur: -1 Yunus: - Cem: 0 Mertcan: 1 Furkan: 1 Orhan: 1 Evren:
Note on R69: Yigit: 1 Tugrul: 1
Note on R70: Busra: 1 Ugur: 1 Yunus: - Cem: 1 Mertcan: 1 Furkan: 1 Orhan: 1
Note on R72: Busra: 1 Ugur: -1 Yunus: - Cem: 1 Mertcan: 1 Furkan: 1 Orhan: 1
Note on S69: Yigit: -1 Tugrul: 0
Note on S70: Busra: 0 Ugur: -1 Yunus: 0 Cem: 0 Mertcan: 0 Furkan: 1 Orhan: 1 Ali: 0 Furkan: 0
Note on S72: Busra: 0 Ugur: -1 Yunus: 1 Cem: 1 Mertcan: 1 Furkan: 1 Orhan: 1 Ali: 1 Furkan: 1
Note on T69: Yigit: 0 Tugrul: 0
Note on T70: Busra: -1 Ugur: 0 Yunus: 0 Cem: 0 Mertcan: - Furkan: - Orhan: - Furkan: 0 Ali: 0 Evren: 0
Note on T72: Busra: 0 Ugur: -1 Yunus: 0 Cem: 1 Mertcan: - Furkan: - Orhan: - Ali: 0 Furkan: 0 Evren: 0
Note on U69: Yigit: -1 Tugrul: -1
Note on U70: Busra: -1 Ugur: -1 Yunus: -1 Cem: - Mertcan: -1 Furkan: 0 Orhan: -1 Furkan T: 0 Ali: -1 Evren: -
Note on U72: Busra: 1 Ugur: -1 Yunus: 0 Cem: - Mertcan: 1 Furkan: 0 Orhan: 1 Ali: 0 Furkan T: 0 Evren: -

## Cerberus
Cerberus
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 28.12-11.01 | 11.01-25.01 | 25.01-07.02 | 08.02-22.02 | 22.02-07.03 | 07.03-20.30 | 21.03-03.04 | 04.04-24.04 | 25.04-09.05 | 09.05-22.05 | 23.05-05.06 | 06.06-26.06 | 27.06-10.07 | 11.07-24.07 | 25.07-07.08 | 08.08-22.08 | 22.08-04.09 | 05.09-18.09 | 19.09-02.10
Sprint Name | S29 - Sen de Yargılanacaksın | S30 - CerberPus | S31 - Zort | S32 Başlayalım Başlayalıııım | S33 - Kültür Zaferi | S34 - Karabina ve Ceket | S35 - Cerberus Kavurma | S36 - Yeniden Usero | S37 - Cairflow | S38 - <UNK> | S39 - Pairflow | S40 - Yugambeh People | S41 - No Country for Burak | S42 - Adío Useros Engagementi | S43 - Arctictis Binturong | S44 - Whiskey in the Jarir | S45 - ijaringvale | S46 - bilir faal german | S47 - Black Reco Friday
Total Effort In the Sprint | 147 | 145 | 173 | 165 | 154 | 159 | 170 | 136 | 155 | 150 | 151 | 150 | 162 | 129 | 143 | 100 | 140 | 113 | 167
Commited | 124 | 144 | 168 | 152 | 154 | 151 | 157 | 128 | 134 | 147 | 145 | 142 | 153 | 123 | 142 | 100 | 139 | 107 | 132
Emerged | 23 | 1 | 5 | 13 | 0 | 8 | 13 | 8 | 21 | 3 | 6 | 8 | 9 | 6 | 1 | 0 | 1 | 6 | 35
Emerged Rate | 18.55% | 0.6944% | 2.976% | 8.553% | 0% | 5.298% | 8.28% | 6.25% | 15.67% | 2.041% | 4.138% | 5.634% | 5.882% | 4.878% | 0.7042% | 0% | 0.7194% | 5.607% | 26.52%
Done Bug Effort | 0 | 0 | 18 | 18 | 21 | 20 | 13 | 17 | 14 | 20 | 17 | 20 | 13 | 7 | 9 | 21 | 0 | 13 | 49
Commited Bug Effort | 0 | 21 | 13 | 18 | 26 | 15 | 13 | 21 | 14 | 18 | 11 | 12 | 5 | 1 | 9 | 21 | 0 | 13 | 28
Emerged Bug Effort | 0 | 0 | 5 | 13 | 0 | 5 | 8 | 8 |  | 2 | 6 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 21
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 82 | 65 | 170 | 44 | 58 | 31 | 45 | 37 | 55 | 39 | 75 | 35 | 43 | 60 | 121 | 50 | 39 | 40 | 50
All Tasks Done Effort | 112 | 68 | 173 | 149 | 144 | 125 | 147 | 105 | 124 | 77 | 104 | 123 | 142 | 113 | 130 | 84 | 123 | 108 | 86
Released Effort | 82 | 60 | 165 | 44 | 58 | 31 | 45 | 37 | 47 | 39 | 41 | 14 | 43 | 26 | 121 | 50 | 39 | 40 | 50
Undone PBI Effort | 35 | 77 | 0 | 16 | 10 | 34 | 23 | 31 | 31 | 73 | 47 | 27 | 20 | 16 | 13 | 16 | 17 | 5 | 81
Comitted Releasable Dev Tasks | 90 | 84 | 165 | 45 | 68 | 57 | 55 | 60 | 89 | 78 | 116 | 56 | 43 | 76 | 129 | 64 | 52 | 40 | 59
Sprint Goal | Getting User Engagement algorithm ready to release and testing performance of algorithm | Ensuring AB test process health and final checks on User Engagement
Goal Achieved (0/1) | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 90.32% | 47.22% | 103% | 98.03% | 93.51% | 82.78% | 93.63% | 82.03% | 92.54% | 52.38% | 71.72% | 86.62% | 92.81% | 91.87% | 91.55% | 84% | 88.49% | 100.9% | 65.15%
Bug/Development Ratio | 0% | 0% | 10.59% | 40.91% | 36.21% | 64.52% | 28.89% | 45.95% | 25.45% | 51.28% | 22.67% | 57.14% | 30.23% | 11.67% | 7.438% | 42% | 0% | 32.5% | 98%
Shipping Accuracy | 100% | 92.31% | 97.06% | 100% | 100% | 100% | 100% | 100% | 85.45% | 100% | 54.67% | 40% | 100% | 43.33% | 100% | 100% | 100% | 100% | 100%
Partner Focus | 72.58% | 58.33% | 98.21% | 29.61% | 44.16% | 37.75% | 35.03% | 46.88% | 66.42% | 53.06% | 80% | 39.44% | 28.1% | 61.79% | 90.85% | 64% | 37.41% | 37.38% | 44.7%
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 54.84% | 38.89% | 85.71% | 58.55% | 52.6% | 38.41% | 78.34% | 69.53% | 52.99% | 52.38% | 52.41% | 48.59% | 66.01% | 55.28% | 33.1% | 34% | 54.68% | 71.03% | 67.42% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 100% | 100% | 100% | 100% | 100% | 30% | 100% | 100% | 100% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [13 empty] | 100% | 100% | 100% | 100% | 100% | 30%
Sprint Goal | Getting User Engagement algorithm ready to release and testing performance of algorithm | Ensuring AB test process health and final checks on User Engagement | Deciding which scaling option will be proceeded with for User Engagement | Discovering various fallback sources | Finding action items to increase recommendation generation step's quality | Finalizing the fallback monitoring dashboards and fallback research phase | Finalizing fallback dashboard & fallback research Tech Design. | Defining user engagement algorithm's performance metrics and resolving illegal memory access | Analyzing problems, improvements, implementing solutions for User Engagement. | Defining possible new attributes for model and implementing custom metrics. | Implementing new features and adjusting data sets for User Engagement | Analyzing new implementation outcomes and implementing brand and color features | Releasing User Engagement with tolerable performance with completing targeted improvements | Implementing the first phase of caching mechanism and defining next requirements | Finalize and implement Smart Caching and monitor outcomes | Releasing caching and increasing throughput plan | Resolving development plans, determining smart event management rules | Cache implementation and roadmap clarification, enabling POC partners | Resolving blocks on SR API caching mechanism for Black Friday readiness
Individual Committed Effort | 124 | 144 | 168 | 152 | 154 | 151 | 157 | 128 | 134 | 147 | 145 | 142 | 153 | 123 | 142 | 100 | 138 | 107 | 127
Mert Gürkan | 42 | 56 | 58 | 52 | 52 | 50 | 55 | 21 | 48 | 48 | 48 | 50 | 37 | 40 | 45 | 34 | 44 | 34
Can Yunus Erözden | 39 | 53 | 55 | 50 | 52 | 54 | 52 | 55 | 44 | 47 | 50 | 46 | 34 | 36 | 45 | 32 | 47 | 18 | 52
Burak Tağtekin | 43 | 35 | 55 | 50 | 50 | 47 | 50 | 52 | 42 | 52 | 47 | 46 | 40
Turan Seza Akgün | [12 empty] | 42 | 47 | 52 | 34 | 47 | 55 | 57
Emir Faruk Erman | [18 empty] | 18
Individual Done Effort | 112 | 68 | 173 | 149 | 144 | 125 | 147 | 105 | 124 | 77 | 104 | 115 | 142 | 113 | 122 | 84 | 123 | 108 | 76
Mert Gürkan | 42 | 14 | 63 | 52 | 52 | 34 | 55 | 21 | 40 | 36 | 40 | 47 | 34 | 43 | 42 | 31 | 42 | 55
Can Yunus Erözden | 28 | 19 | 55 | 50 | 47 | 52 | 47 | 50 | 47 | 10 | 30 | 40 | 42 | 23 | 40 | 32 | 34 | 18 | 40
Burak Tağtekin | 42 | 35 | 55 | 47 | 45 | 39 | 45 | 34 | 37 | 31 | 34 | 28 | 35
Turan Seza Akgün | [12 empty] | 31 | 47 | 40 | 21 | 47 | 35 | 36
Emir Faruk Erman
Sprint Goal Contribution (Comitted) | 68 | 56 | 144 | 89 | 81 | 58 | 123 | 89 | 71 | 77 | 76 | 69 | 101 | 68 | 47 | 34 | 76 | 76 | 89
Mert Gürkan | 8 | 14 | 34 | 34 | 26 | 29 | 55 | 21 | 29 | 22 | 21 | 13 | 29 | 34 | 34 | 21 | 21 | 55
Can Yunus Erözden | 26 | 8 | 55 | 34 | 34 | 13 | 34 | 34 | 21 | 34 | 21 | 35 | 29 |  | 13 | 13 | 21 |  | 34
Burak Tağtekin | 34 | 34 | 55 | 21 | 21 | 16 | 34 | 34 | 21 | 21 | 34 | 21 | 22
Turan Seza Akgün | [12 empty] | 21 | 34 | 0 | 0 | 34 | 21 | 55
Emir Faruk Erman
Sprint Goal Contribution (Delivered) | 68 | 56 | 144 | 89 | 81 | 37 | 123 | 89 | 81 | 43 | 76 | 76 | 101 | 68 | 47 | 34 | 76 | 76 | 21
Mert Gürkan | 8 | 14 | 34 | 34 | 26 | 8 | 55 | 21 | 39 | 22 | 21 | 13 | 29 | 34 | 34 | 21 | 21 | 55
Can Yunus Erözden | 26 | 8 | 55 | 34 | 34 | 13 | 34 | 34 | 21 | 0 | 21 | 35 | 29 |  | 13 | 13 | 21 | 0 | 0
Burak Tağtekin | 34 | 34 | 55 | 21 | 21 | 16 | 34 | 34 | 21 | 21 | 34 | 28 | 22 | 34
Turan Seza Akgün | [12 empty] | 21 |  | 0 | 0 | 34 | 21 | 21
Emir Faruk Erman
Sprint Goal KR Focused Effort
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on J35: Goal Tasks: - https://winsider.atlassian.net/browse/PA-26290 - https://winsider.atlassian.net/browse/PA-26523 - https://winsider.atlassian.net/browse/PA-26524 - https://winsider.atlassian.net/browse/PA-26547 - https://winsider.atlassian.net/browse/PA-26567 - https://winsider.atlassian.net/browse/PA-26717 -Can Yunus Erozden
Note on J55: During the sprint, it was realized that one of the goal task needed a broader scope, so a subtask was created. Goal task -> https://winsider.atlassian.net/browse/PA-26567 Sub task -> https://winsider.atlassian.net/browse/PA-26717 -Can Yunus Erozden
Note on K35: Goal Tasks: - https://winsider.atlassian.net/browse/PA-26295 - https://winsider.atlassian.net/browse/PA-26759 - https://winsider.atlassian.net/browse/PA-26766 - https://winsider.atlassian.net/browse/PA-26783 - https://winsider.atlassian.net/browse/PA-26796 - https://winsider.atlassian.net/browse/PA-26292 -Can Yunus Erozden
Note on L35: Goal Tasks: - https://winsider.atlassian.net/browse/PA-26958 - https://winsider.atlassian.net/browse/PA-26757 - https://winsider.atlassian.net/browse/PA-26292 -Can Yunus Erozden
Note on M35: Goal Tasks: - https://winsider.atlassian.net/browse/PA-27141 - https://winsider.atlassian.net/browse/PA-27011 - https://winsider.atlassian.net/browse/PA-26782 - https://winsider.atlassian.net/browse/PA-26841 - https://winsider.atlassian.net/browse/PA-27139 - https://winsider.atlassian.net/browse/PA-27140 -Can Yunus Erozden
Note on N35: Goal Tasks: - https://winsider.atlassian.net/browse/PA-27318 - https://winsider.atlassian.net/browse/PA-27328 -https://winsider.atlassian.net/browse/PA-27326 -https://winsider.atlassian.net/browse/PA-27321 -https://winsider.atlassian.net/browse/PA-27088 -https://winsider.atlassian.net/browse/PA-27320 -https://winsider.atlassian.net/browse/PA-27330 -Can Yunus Erozden
Note on O35: Goal Tasks: -https://winsider.atlassian.net/browse/PA-27593 - https://winsider.atlassian.net/browse/PA-27594 -Can Yunus Erozden
Note on P35: Goal Tasks: - https://winsider.atlassian.net/browse/PA-27603 - https://winsider.atlassian.net/browse/PA-27753 - https://winsider.atlassian.net/browse/PA-27601 -Can Yunus Erozden
Note on Q35: Releasing caching and increasing throughput plan - https://winsider.atlassian.net/browse/PA-27879 - https://winsider.atlassian.net/browse/PA-27928 -Can Yunus Erozden

## Coruscant
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 30.12-23-10.01 | 11.01/24.01 | 25.01/07.02 | 8.2/21.2 | 22.3/6.3 | 7.3/20.3 | 21.03/03.04 | 04.04/24.04 | 04.04/24.05 | 9.5/22.5 | 23.5/6.6 | 6.6/27.6 | 27.06/11.07 | 11.07/24.07 | 25.07/07.08 | 08.08/21.08 | 22.08/5.9 | 06.09/19.09 | 20.09/2.10 | 3.10/16.10 | 17.10/30.10
Sprint Name | #25 - 🧿 İYİYİZ 🧿 | #26 - ByeBye Ahtapot | #3 - PositiveVibes | #4 - KelimelerKiyafetsiz | #5 - 21Forever | #6 - Kiralık QA | #7 - S.A. Muzat | #8 - Eid Mubarak | #9 - SerkanaMolaYok | #10 - AutomationWars | #11 - OffNeGünlerdi! | #12 - ForArda | #13 - HacıYatmazSerkan | #14 - ForÜmmühan | #15 - HangInThere | #16 - Retreat | #17 - All in! | #18 - NoBugNoCry | #19 | #20 | #21
Total Effort In the Sprint | 201 | 230 | 154 | 208 | 215 | 203 | 218 | 139 | 160 | 155 | 183 | 137 | 154 | 142 | 142 | 113 | 159 | 157 | 196 | 160
Commited | 191 | 186 | 117 | 181 | 192 | 200 | 218 | 134 | 160 | 155 | 180 | 133 | 151 | 139 | 137 | 113 | 156 | 156 | 176 | 150
Emerged | 25 | 60 | 5 | 11 | 17 | 16 | 16 | 10 | 8 | 18 | 9 | 19 | 0 | 16 | 13 | 8 | 28 | 20 | 10 | 42
Emerged Rate | 12.44% | 26.09% | 3.247% | 5.288% | 7.907% | 7.882% | 7.339% | 7.194% | 5% | 11.61% | 4.918% | 13.87% | 0% | 11.27% | 9.155% | 7.08% | 17.61% | 12.74% | 5.102% | 26.25%
Done Bug Effort | 19 | 44 | 28 | 53 | 36 | 8 | 48 | 18 | 25 | 27 | 17 | 21 | 7 | 11 | 8 | 11 | 23 | 69 | 22 | 22
Commited Bug Effort | 21 | 47 | 40 | 53 | 36 | 5 | 49 | 26 | 22 | 24 | 20 | 9 | 7 | 21 | 3 | 11 | 5 | 77 | 50 | 30
Emerged Bug Effort | 0 | 11 | 0 | 0 | 0 | 3 | 9 | 13 | 3 | 5 | 0 | 12 | 0 | 3 | 5 | 8 | 25 | 7 | 0 | 47
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 109 | 114 | 103 | 154 | 143 | 88 | 115 | 47 | 131 | 137 | 108 | 110 | 100 | 86 | 119 | 55 | 123 | 109 | 52 | 45
All Tasks Done Effort | 121 | 150 | 110 | 176 | 143 | 175 | 171 | 86 | 142 | 151 | 147 | 115 | 107 | 99 | 132 | 75 | 140 | 111 | 61 | 45
Released Effort | 100 | 106 | 88 | 127 | 69 | 80 | 114 | 40 | 118 | 137 | 90 | 98 | 87 | 73 | 117 | 37 | 119 | 83 | 37 | 32
Undone PBI Effort | 82 | 72 | 19 | 22 | 60 | 68 | 37 | 42 | 18 | 4 | 33 | 21 | 41 | 42 | 5 | 38 | 5 | 46 | 134 | 97
Comitted Releasable Dev Tasks | 157 | 186 | 104 | 176 | 143 | 103 | 147 | 97 | 136 | 128 | 124 | 131 | 128 | 134 | 116 | 67 | 112 | 156 | 176 | 69
Sprint Goal | - Releasing mobile on-page template to the beta partners. - Finalizing analytics inconsistency and DS transition target. | - Having 0 bugs on the Mobile OnPage Template - Decreasing the load on PCD change detection and improve performance - Ensure all partners don't have access to the sunsetted CloneDiv feature from InOne. | Finalizing the Locale KR with all the UAT and QA camp outcomes implemented. Being ready for the 90-day lookback period GTM. Starting micro frontend implementation. | Finalizing the viewable impression calculation logic, and aligning with Valorem to make sure development starts next sprint. Also, finalize the interface development of Locale KR. | Providing the final version of impression logs, also enables tech design and create the following tasks for Stategy KR. | 1. Finalizing the strategy KR tech design and creating the development tasks for the upcoming sprints. 2. Finalising all log collection cases on the Analytics KR and leaving only FE developments on the page. | Analytics: No tasks remain for its final GTM. RRS: Finishing GSS API Pt.1 development and all API test cases. GLA: Making it ready for development. | Have a clear roadmap for the Enigma transition, all questions answered, and all tasks created. Complete the test for GSS API filtering capabilities. | Deliver the live listing table with details (list, delete, de-activate). | RSS - Creation flow is moved to production | 1. SR API works for all the algorithms. 2. Strategies can be deleted and edited. | 1. New (channel and page9 creation flow will be delivered. 2. Strategies will be called from the variant section. 3. Chef cases will be finalized in backend. | 1. Complete the strategy recommendation - api connection 2. Document the results from and solutions for "transition" research. | 1. Finalize and complete the SR API Strategy Endpoint 2. Complete the (new) creation flow. 3. Complete the 'connection' between Gachapon and strategy creation (algorithms) | 1. Transition (migration) flow will be completed. 2. Upsert & insert validations will be completed. | 1. Chef is added to the strategy system as a functional algorithm 2. Recommendation Settings are handled for old and new campaigns. 3. Requirements are clarified and documented for Email channel enablement | 1. Completing the RRS development to have it ready for e2e test in the next sprint. 2. Improving how the viewable impressions are collected. 3. Completing the "tech design" for channel enablement. | 1- RSS Features & bugs completion and make it ready for QA camp 2-Analytics Issues Resolution | Releasing the RSS KR | Completing at least 100 analytics campaign cases troubleshooting and finding root causes. Releasing the RRS KR
Goal Achieved (0/1) | 0% | 0% | 100% | 0% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 63.35% | 80.65% | 94.02% | 97.24% | 74.48% | 87.5% | 78.44% | 64.18% | 88.75% | 97.42% | 81.67% | 86.47% | 70.86% | 71.22% | 96.35% | 66.37% | 89.74% | 71.15% | 34.66% | 30%
Bug/Development Ratio | 17.43% | 38.6% | 27.18% | 34.42% | 25.17% | 9.091% | 41.74% | 38.3% | 19.08% | 19.71% | 15.74% | 19.09% | 7% | 12.79% | 6.723% | 20% | 18.7% | 63.3% | 42.31% | 48.89%
Shipping Accuracy | 91.74% | 92.98% | 85.44% | 82.47% | 48.25% | 90.91% | 99.13% | 85.11% | 90.08% | 100% | 83.33% | 89.09% | 87% | 84.88% | 98.32% | 67.27% | 96.75% | 76.15% | 71.15% | 71.11%
Partner Focus | 82.2% | 100% | 88.89% | 97.24% | 74.48% | 51.5% | 67.43% | 72.39% | 85% | 82.58% | 68.89% | 98.5% | 84.77% | 96.4% | 84.67% | 59.29% | 71.79% | 100% | 100% | 46%
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 15.18% | 17.2% | 26.13% | 26.79% | 17.71% | 51% | 31.19% | 47.01% | 34.38% | 49.03% | 31.11% | 35.34% | 31.13% | 30.22% | 40.15% | 30.09% | 33.33% | 35.26% | 30.68% | 54% | 0% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 0% | 0% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 0% | 0% | 85% | 15% | 70% | 100% | 100% | 30% | 30% | 100% | 100% | 30% | 100% | 100% | 100% | 100% | 30% | 30% | 30% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [13 empty] | 100% | 100% | 100% | 30% | 30% | 30%
Individual Committed Effort | 191 | 186 | 111 | 168 | 192 | 200 | 218 | 134 | 160 | 155 | 180 | 133 | 151 | 139 | 137 | 113 | 159 | 157 | 196 | 150
Abdullah Alrifai |  |  | 18 | 21 | 37 | 45 | 43
Ahmet Önol | 53 | 50 | 44 | 30 | 52 | 53 | 46 | 47 | 52 | 54 | 48 | 36 | 24 | 50 | 44 | 29 | 47 | 36 | 50 | 50
Berk Yaşar | 46 | 40
Murat Çakmak |  |  | 41 | 31 | 32 | 34 | 40
Rafet Topçu | 45 | 44
Serkan Şahin |  |  | 8 | 28 | 21 | 21 | 37 | 35 | 45 | 38 | 47 | 42 | 45 | 39 | 41 | 26 | 38 | 50 | 41 | 52
Turan Seza Akgün | 47 | 52
Yasin Güzel |  |  |  | 45 | 50 | 47 | 52 | 52 | 37 | 44 | 50 | 44 | 48 | 42 | 39 | 26 | 37 | 37 | 47
Buğra Sercan Şeker | [13 empty] | 8 | 13 | 20 | 34 | 34 | 34 | 29
Ümmühan Dönmezer |  |  |  | 10 |  |  |  |  | 10 | 8 | 10 | 5 | 8 | 0
Murat Feyzioğlu |  |  |  | 3 |  |  |  |  | 8 | 6 | 18 | 0 | 8 | 0 | 0 | 4 | 0 |  | 11 | 0
Mısra Öztoprak | [8 empty] | 8 | 5 | 7 | 6 | 18 | 0 | 0 | 3 | 0 |  | 5 | 0
Ege Bozdemir | [15 empty] | 5 |  |  | 3 | 8
Sinem Sungur | [18 empty] | 5 | 11
Individual Done Effort | 109 | 114 | 92 | 146 | 132 | 132 | 181 | 92 | 142 | 151 | 147 | 112 | 110 | 97 | 132 | 75 | 154 | 111 | 62 | 53
Abdullah Alrifai |  |  | 19 | 21 | 32 | 32 | 43
Ahmet Önol | 23 | 41 | 38 | 20 | 18 | 47 | 24 | 49 | 52 | 44 | 40 | 32 | 1 | 29 | 36 | 3 | 43 | 25 | 14 | 0
Berk Yaşar | 11 | 19
Murat Çakmak |  |  | 25 | 27 | 19 | 24 | 35
Rafet Topçu | 70 | 45
Serkan Şahin |  |  | 10 | 34 | 21 | 32 | 40 | 35 | 48 | 51 | 31 | 25 | 40 | 25 | 36 | 24 | 51 | 42 | 5 | 10
Buğra Sercan Şeker | [13 empty] | 13 | 18 | 13 | 28 | 26 | 34 | 37
Turan Seza Akgün | 5 | 9
Yasin Güzel |  |  |  | 44 | 42 | 37 | 39 | 8 | 16 | 42 | 50 | 44 | 48 | 29 | 39 | 26 | 19 | 16 | 0
Ümmühan Dönmezer | [8 empty] | 10 | 8 | 8 | 5 | 5 | 0
Murat Feyzioğlu | [8 empty] | 8 | 6 | 18 | 0 | 8 | 0 | 0 | 4 | 32 |  | 3 | 0
Mısra Öztoprak | [8 empty] | 8 | 0 |  | 6 | 11 | 1 | 0 | 3 | 0 | 2 | 3 | 0
Ege Bozdemir | [14 empty] | 3 | 2 |  |  | 3 | 0
Sinem Sungur | [18 empty] | 0 | 6
Sprint Goal Contribution (Comitted) | 29 | 32 | 29 | 45 | 34 | 102 | 68 | 63 | 55 | 76 | 56 | 47 | 47 | 42 | 55 | 34 | 52 | 55 | 54 | 81
Abdullah Alrifai |  |  | 5 | 0 | 13 | 21 | 0
Ahmet Önol | 21 | 16 | 11 | 9 | 0 | 34 | 8 | 21 | 39 | 34 | 13 | 21 | 0 | 21 | 21 | 0 | 13 | 8 | 8 | 34
Berk Yaşar | 8
Murat Çakmak |  |  | 13 | 5 | 0 | 0 | 13
Rafet Topçu | 0 | 16
Serkan Şahin |  |  |  | 20 | 0 | 13 | 8 | 8 | 0 | 21 | 8 | 13 | 26 | 13 | 21 | 21 | 13 | 31 | 3 | 34
Turan Seza Akgün | 0
Yasin Güzel |  |  |  | 11 | 21 | 34 | 39 | 34 | 16 | 21 | 27 | 13 | 21 | 8 | 13 | 13 | 13 | 0
Murat Feyzioğlu | [10 empty] | 8 |  | 0 | 0 | 0
Buğra Sercan Şeker | [13 empty] | 0 | 0 | 8 | 13 | 16 | 34 | 13
Sinem Sungur | [19 empty] | 0
Mısra Öztoprak | [18 empty] | 3 | 0
Ege Bozdemir | [18 empty] | 3 | 0
Murat Feyzioğlu | [18 empty] | 3 | 0
Sprint Goal Contribution (Delivered) | 0 | 19 | 29 |  | 34 | 102 | 68 | 34 | 34 | 76 | 56 | 34 | 47 | 42 | 55 | 42 | 26 | 8 | 27 | 0
Abdullah Alrifai |  |  | 5 | 0 | 13 | 21 | 0
Ahmet Önol |  | 16 | 11 | 9 | 0 | 34 | 8 | 21 | 0 | 34 | 13 | 21 | 0 | 21 | 21 | 0 | 13 | 8 | 8 | 0
Berk Yaşar | [19 empty] | 0
Murat Çakmak |  |  | 13 | 5 | 0 | 0 | 13 | [12 empty] | 0
Rafet Topçu |  | 3 | [17 empty] | 0
Serkan Şahin |  |  |  | 20 | 0 | 13 | 8 | 8 | 0 | 21 | 8 | 0 | 26 | 13 | 21 | 21 | 0 | 0 |  | 0
Turan Seza Akgün | [19 empty] | 0
Yasin Güzel |  |  |  | 11 | 21 | 34 | 39 | 5 | 16 | 21 | 27 | 13 | 21 | 0 | 13 | 13 | 0 | 0 | 0 | 0
Murat Feyzioğlu | [10 empty] | 8 |  | 0 | 0 | 0 |  |  |  |  | 0
Buğra Sercan Şeker | [13 empty] | 0 | 0 | 8 | 13 | 0 | 13 | 0
Sinem Sungur | [19 empty] | 0
Mısra Öztoprak | [18 empty] | 3 | 0
Ege Bozdemir | [18 empty] | 3 | 0
Murat Feyzioğlu | [19 empty] | 0
Sprint Goal KR Focused Effort
Note on A23: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A31: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on D42: on leave
Note on O31: 3/5 -Didem Akgun
Note on Q58: retreat sprinti ama hasta
Note on R58: 30 ağustos ve 1 gün izin
Note on S36: Eforu belirsiz 2 task ile -Ahmet Onol

## Design System
Team Name
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 03.01.24-17.01.24 | 17.01.24-31.01.24 | 31.01.24-14.02.24 | 14.02.24-28.02.24 | 28.02.24-13.03.24 | 13.03.24-27.03.24 | 27.03.24-09.04.24 | 09.04.24-24.04.24 | 24.04.24-08.05.24 | 08.05.24-22.05.24 | 22.05.24-05.06.24 | 05.06.24-26.06.24 | 26.06.24-10.07.24 | 10.07.24-24.07.24 | 24.07.24-07.08.24 | 07.08.24-22.08.24 | 22.08.24-04.09.24 | 04.09.24-18.09.24 | 18.09.24-02.10.24 | 02.10.24-16.10.24
Sprint Name | DS 23-3, Sprint 5 | DS 23-3, Sprint 6 | DS 24-1, Sprint 7 | DS 24-1, Sprint 8 | DS 24-1, Sprint 9 | DS 24-1, Sprint 10 | DS-24-Q2 Sprint 1 | DS-24-Q2 Sprint 2 | DS-24-Q2 Sprint 3 | DS-24-Q2 Sprint 4 | DS-24-Q2 Sprint 5 | DS-24-Q2 Sprint 6 | DS-24-Q3 Sprint 1 | DS-24-Q3 Sprint 2 | DS-24-Q3 Sprint 3 | DS-24-Q3 Sprint 4 | DS-24-Q3 Sprint 5 | DS-24-Q3 Sprint 6 | DS-24-Q3 Sprint 7 | DS-24-Q4 Sprint 1
Total Effort In the Sprint | 390 | 359 | 284 | 382 | 281 | 310 | 370 | 283 | 277 | 282 | 336 | 363 | 375 | 225 | 241 | 224 | 222 | 254 | 228 | 277
Commited | 348 | 335 | 274 | 376 | 234 | 256 | 369 | 283 | 249 | 264 | 315 | 260 | 353 | 216 | 217 | 218 | 167 | 231 | 190 | 232
Emerged | 42 | 24 | 10 | 6 | 47 | 54 | 1 | 0 | 28 | 18 | 21 | 103 | 22 | 9 | 24 | 6 | 55 | 23 | 38 | 45
Emerged Rate | 10.77% | 6.685% | 3.521% | 1.571% | 16.73% | 17.42% | 0.2703% | 0% | 10.11% | 6.383% | 6.25% | 28.37% | 5.867% | 4% | 9.959% | 2.679% | 24.77% | 9.055% | 16.67% | 16.25%
Done Bug Effort | 5 | 5 | 5 | 0 | 8 | 11 | 32 | 0 | 35 | 21 | 42 | 37 | 13 | 26 | 0 | 24 | 0 | 21 | 13 | 7
Commited Bug Effort | 5 | 5 | 5 | 0 | 8 | 10 | 40 | 8 | 32 | 29 | 21 | 47 | 26 | 26 | 0 | 24 | 0 | 24 | 14 | 18
Emerged Bug Effort | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 21 | 16 | 0 | 0 | 8 | 0 | 3 | 0 | 19 | 2
Done Pool Effort | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Done Pool Bug Effort | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dev Tasks Done Effort | 133 | 149 | 135 | 144 | 156 | 120 | 114 | 140 | 80 | 115 | 106 | 94 | 67 | 81 | 48 | 113 | 86 | 107 | 85 | 81
All Tasks Done Effort | 365 | 336 | 266 | 346 | 266 | 277 | 313 | 237 | 223 | 256 | 271 | 304 | 308 | 197 | 148 | 187 | 178 | 221 | 179 | 213
Released Effort | 0 | 0 | 0 | 21 | 0 | 46 | 0 | 0 | 0 | 48 | 1 | 24 | 13 | 34 | 0 | 8 | 8 | 49 | 4 | 1
Undone PBI Effort | 25 | 23 | 18 | 36 | 15 | 33 | 57 | 46 | 54 | 26 | 65 | 59 | 67 | 28 | 93 | 37 | 44 | 33 | 49 | 64
Comitted Releasable Dev Tasks | 158 | 150 | 129 | 181 | 165 | 114 | 169 | 167 | 125 | 129 | 135 | 106 | 104 | 109 | 133 | 144 | 109 | 127 | 97 | 135
Sprint Goal | DT-15652 DT-15651 DS-2400 DS-2618 | DS-2400 DS-2445 DT-15808 DT-15809 | Relasing the Date PickerV2: DS-2696, DS-2655 Completing the InOne Implementation of Modal v2 and Drawer: DS-2448, DS-2698 Make the spacings consistent in Form Components DT-14773, DT-16281 | Creating the main structure of Sidebarv2 DS-2752, DS-2756 Release Drawer Component DS-2698 Prepare the Final Design for Sidebarv2 DT-16204, DT-16575 | Finishing Sidebar v2 Development and Design: DS-2760, DT-16860 Enabling NNG Output Functionality regarding Split Button: DS-2728 Finish Benchmark and Ideation for Ghost Input: DT-16847 | Implementing Sidebar v2 to the InOne: DS-2764 DS-2815, DT-16649 Enabling Dropdown Usage in Chips: DS-2308 Having Smaller Size in Form Components: DT-17142 | Enable Usage of Organisms with v2 Stylings in Figma Level: DT-17348, DT-17346 Finalize the Sidebar v2 Development: DS-2768 Provide US Date Formatting in Data Table and Charts: DS-2886, DS-2877 | Start v2 Transitioning Process: DS-2921 Enable the Teams to use Bulk Action: DS-2853 Resolve the Multi Level Dropdown Issue in Modal and Drawer: DT-17586 Provide Solution to the Pinned Column Issue in Data Table: DT-17757 | Completing Migration of Create Button DS-2939, DS-2919 Create PLG Library DT-17728 Enable Advanced Kube Usage within DS Team DS-2955 | Start Working on new Button v2 Migration KR: DS-3010 Complete Sidebar KR Related Points: DS-2981, DS-2982 Start Documentation KR on Design Side: DT-18462, DT-18458 | Complete Button Migration DS-3051 Completing Vitest Implementation DS-3052 Start Creating Documentations in Supernova DT-17739, DT-17856 | Complete Sidebar v2 findings and make it ready for QA Camp. DS-3062 Migrating to Vitest to create route for CI/CD process for DS. DS-3078 Complete Documentation for RTI and Start Documenting Select Dropdown Menu. DT-17736, DT-19099 | Completing Sidebar QA Camp Fixings: DS-3116 Completing Single Button Findings: DS-3128 Complete Documentation for Multi Select Dropdown Menu and Modal v2: DT-17857, DT-19101 | Increase the usage of Button v2 component in DS Repository DS-3018 Increase test coverage for Design System Components DS-3166 Complete documentation for v2 component in SuperNova DT-17849 DT-17851 | Completing Vitest Migration for DP and RTI - DS-3206 , DS-3203 Preparing Sidebar for AUT Camp. DS-3208 Start Releasing Create Button in All Repositories Except HB. - DS-3212 Upgrading the AG Grid and check the DTs in Panel - DS-3202 Fixing inconsistencies of listed components (written in ACs) - DT-20111, DT-19931 | Fixing all the Sidebar UAT Camp Findings. DS-3230 Fixing the Single Button Related findings in DS repository. DS-3220 Updating the missign items Guideline tab in Documentation DT-20497 Provide beahviors and Examples for Multi Select Component DT-19178 | Fixing QA and UAT Camp Findings for Sidebar v2 - DS-3254 Releasing Create Button in Aristo Repository - DS-3255 Completing Documentations for Form Status, Onpage Message and Toaster - DT-20060 DT-20062 DT-20058 | Checking updated writings and behaviors in Sidebar v2: DS-3350 Preparing the Create Button for Release: DS-3356, DS-3358 Finishing the documentations for listed component: DT-20936, DT-21068, DT-20075, DT-20932, DT-20934 | Apply Sidebar related changes in Aristo: DS-3397 Release Button v2 in Web Push Repository: DS-3403 Complete Documentations for the listed components: DT-21064. DT-21074. DT-21070 | Complete Migration in WhatsApp DS-3401 Providing preselected functionality in Data Table DS-3057 Completing the listed documentations DT-21361 DT-21349 DT-21351
Goal Achieved (0/1) | 0% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 0% | 100% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 104.9% | 100.3% | 97.08% | 92.02% | 113.7% | 108.2% | 84.82% | 83.75% | 89.56% | 96.97% | 86.03% | 116.9% | 87.25% | 91.2% | 68.2% | 85.78% | 106.6% | 95.67% | 94.21% | 91.81%
Bug/Development Ratio | 3.759% | 3.356% | 3.704% | 0% | 5.128% | 9.167% | 28.07% | 0% | 43.75% | 18.26% | 39.62% | 39.36% | 19.4% | 32.1% | 0% | 21.24% | 0% | 19.63% | 15.29% | 8.642%
Shipping Accuracy | 0% | 0% | 0% | 14.58% | 0% | 38.33% | 0% | 0% | 0% | 41.74% | 0.9434% | 25.53% | 19.4% | 41.98% | 0% | 7.08% | 9.302% | 45.79% | 4.706% | 1.235%
Partner Focus | 45.4% | 44.78% | 47.08% | 48.14% | 70.51% | 44.53% | 45.8% | 59.01% | 50.2% | 48.86% | 42.86% | 40.77% | 29.46% | 50.46% | 61.29% | 66.06% | 65.27% | 54.98% | 51.05% | 58.19%
Bug Score | 1.282% | 1.393% | 1.761% | 0% | 2.847% | 3.548% | 10.81% | 2.827% | 12.64% | 10.28% | 12.5% | 17.36% | 6.933% | 11.56% | 3.32% | 10.71% | 1.351% | 9.449% | 14.47% | 7.22%
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.55% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 29.31% | 42.99% | 34.31% | 38.3% | 30.34% | 31.64% | 35.5% | 48.06% | 33.73% | 36.74% | 45.71% | 45.38% | 37.11% | 41.2% | 39.63% | 31.19% | 30.54% | 30.74% | 30.53% | 30.6% | 0% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 15% | 100% | 30% | 100% | 100% | 100% | 100% | 100% | 30% | 100% | 100% | 100% | 30% | 100% | 30% | 100% | 100% | 100% | 100% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [13 empty] | 100% | 30% | 100% | 100% | 100% | 100%
Sprint goals efforts | 102 | 144 | 94 | 144 | 71 | 81 | 131 | 136 | 84 | 97 | 144 | 118 | 131 | 89 | 86 | 68 | 51 | 71 | 58 | 71
Sprint goals KR efforts | [19 empty] | 50
Devs
Individual Committed Effort | 167 | 151 | 130 | 182 | 166 | 133 | 175 | 173 | 131 | 144 | 150 | 129 | 112 | 109 | 133 | 144 | 109 | 127 | 104 | 142
Alp Senel | 47 | 55 | 31 | 58 | 52 | 44 | 49 | 41 | 41 | 48 | 51 | 31 | 22 | 14 | 37 | 29 | 24 | 27 | 32 | 47
Sprint Goal Contribution |  | DS-2445 | DS-2698 | [5 empty] | DS-2955 |  | DS-3052 | DS-3078 |  |  | DS-3203 |  | DS-3255 | DS-3358
Emrah Polatcan | 12 | 5 | 8 | 10 | 15 | 15 | 20 | 21 | 8 | 6 | 30 | 30 | 27 | 24 | 21 | 21 | 1 | 24 | 6 | 6
Sprint Goal Contribution
Julia Lopatka | 53 | 44 | 44 | 54 | 52 | 31 | 54 | 56 | 40 | 43 | 27 | 23 | 34 | 37 | 34 | 42 | 42 | 39 | 27 | 39
Sprint Goal Contribution | DS-2618 |  | DS-2448 | DS-2698 | DS-2728 | DS-2308 | DS-2886, DS-2877 | DS-2853 | DS-2919 | DS-2982 |  |  | DS-3128 | DS-3166 | DS-3206, DS-3202 | DS-3220 |  | DS-3356 | DS-3403 | DS-3057
Andrey Sukhin | 55 | 47 | 47 | 60 | 47 | 43 | 52 | 55 | 42 | 47 | 42 | 45 | 29 | 34 | 41 | 52 | 42 | 37 | 39 | 50
Sprint Goal Contribution | DS-2400 | DS-2400 | DS-2696, DS-2655 | DS-2752, DS-2756 | DS-2760 | DS-2764, DS-2815 | DS-2768 | DS-2921 | DS-2939 | DS-3010, DS-2981 | DS-3051 | DS-3062 | DS-3116 | DS-3018 | DS-3208 DS-3212 | DS-3230 | DS-3254 | DS-3350 | DS-3397 | DS-3401
Individual Done Effort | 142 | 149 | 135 | 144 | 156 | 120 | 114 | 140 | 80 | 115 | 106 | 94 | 67 | 81 | 48 | 113 | 86 | 107 | 85 | 81
Alp Senel | 47 | 55 | 25 | 16 | 52 | 32 | 0 | 31 | 29 | 18 | 29 | 21 | 29 | 0 | 1 | 26 | 13 | 21 | 8 | 15
Emrah Polatcan | 0 | 0 | 11 | 6 | 5 | 0 | 0 | 6 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 1 | 23 | 8 | 0
Julia Lopatka | 53 | 39 | 44 | 62 | 52 | 32 | 75 | 48 | 43 | 29 | 43 | 28 | 13 | 34 | 24 | 48 | 42 | 39 | 31 | 32
Andrey Sukhin | 42 | 55 | 55 | 60 | 47 | 56 | 39 | 55 | 8 | 68 | 34 | 37 | 21 | 47 | 23 | 39 | 30 | 24 | 38 | 34
Designers
Individual Committed Effort | 181 | 184 | 144 | 194 | 68 | 123 | 194 | 110 | 118 | 120 | 165 | 131 | 241 | 107 | 84 | 74 | 58 | 104 | 86 | 90
Julide Erdogan | 76 | 66 | 42 | 71 | 34 | 37 | 63 | 42 | 55 | 18 | 55 | 21 | 76 | 31 | 42 | 21 | 21 | 26 | 21 | 21
Sprint Goal Contribution | DT-15651 | DT-15808 | DT-14773 | DT-16204 | DT-16860 | DT-16649 |  | DT-17586 |  |  | DT-1785 | DT-19099 |  |  | DT-20111 | DT-20497 | DT-20060 | DT-20936, DT-20934 | DT-21070 | DT-21351
Tarikul islam | 55 | 55 | 55 | 58 | 13 | 39 | 68 | 34 | 13 | 47 | 55 | 55 | 68 | 42 | 0 | 16 | 13 | 42 | 34 | 37
Sprint Goal Contribution | DT-15652 | DT-15809 |  |  | DT-16847 | DT-17142 | DT-17348 | DT-17757 |  | DT-18458 |  |  | DT-17857 | DT-17851 |  |  | DT-20062 | DT-20932 | DT-21074 | DT-21361
Cagdas Yildirim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal Contribution | [9 empty] | DT-18462
Cagla Col | 50 | 63 | 47 | 65 | 21 | 47 | 63 | 34 | 50 | 55 | 55 | 55 | 97 | 34 | 42 | 37 | 24 | 36 | 31 | 32
Sprint Goal Contribution |  |  | DT-16281 | DT-16575 |  |  | DT-17346 |  | DT-17728 |  | DT-17739 | DT-17736 | DT-19101 | DT-17849 | DT-19931 | DT-19178 | DT-20058 | DT-21068 DT-20075 | DT-21064 | DT-21349
Ummu Kaya
Sprint Goal Contribution
Individual Done Effort | 223 | 187 | 131 | 202 | 110 | 157 | 199 | 97 | 143 | 141 | 165 | 210 | 241 | 116 | 100 | 74 | 92 | 114 | 94 | 132
Julide Erdogan | 89 | 66 | 42 | 71 | 34 | 50 | 63 | 42 | 58 | 31 | 55 | 34 | 76 | 60 | 42 | 21 | 21 | 26 | 29 | 21
Tarikul islam | 71 | 55 | 21 | 58 | 34 | 39 | 73 | 21 | 34 | 55 | 55 | 66 | 68 | 0 | 0 | 16 | 13 | 42 | 34 | 37
Cagdas Yildirim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cagla Col | 63 | 66 | 68 | 73 | 42 | 68 | 63 | 34 | 51 | 55 | 55 | 110 | 97 | 56 | 58 | 37 | 58 | 46 | 31 | 40
Ummu Kaya | [19 empty] | 34
QAs
Individual Committed Effort | 50 | 44 | 33 | 49 | 49 | 68 | 50 | 34 | 59 | 61 | 69 | 70 | 40 | 47 | 56 | 43 | 23 | 39 | 36
Ahmet Toktas | 26 | 29 | 15 | 19 | 33 | 34 | 36 | 18 | 31 | 31 | 28 | 36 | 40 | 18 | 23 | 15 | 10 | 15 | 7
Gulcin Kulunk | 24 | 15 | 18 | 30 | 16 | 34 | 14 | 16 | 28 | 30 | 41 | 34 | 0 | 29 | 33 | 28 | 13 | 24 | 29
Individual Done Effort | 50 | 44 | 33 | 31 | 31 | 45 | 27 | 11 | 41 | 48 | 43 | 48 | 14 | 31 | 38 | 38 | 13 | 24 | 10
Ahmet Toktas | 26 | 29 | 15 | 6 | 15 | 16 | 18 | 0 | 13 | 18 | 15 | 14 | 14 | 5 | 13 | 10 | 5 | 10 | 0
Gulcin Kulunk | 24 | 15 | 18 | 25 | 16 | 29 | 9 | 11 | 28 | 30 | 28 | 34 | 0 | 26 | 25 | 28 | 8 | 14 | 10
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
ATTENTION
Please right-click on this tab, duplicate, and rename it for your team.
Do not remove rows, use “hide rows” instead.
Do not add any rows above the 28th row, you can add them below the colored metrics.

## Mobile Cartel
Team Name
Quarter | Q1 | [6 empty] | Q2 | [5 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 25.12-08.01 | 08.01-22.01 | 22.01-05.02 | 05.02-20.02 | 20.02-04.03 | 04.03-18.03 | 18.03-01.04 | 01.04-15.04 | 15.04-29.04 | 29.04-13.05 | 13.05-27.05 | 27.05-10.06 | 10.06-24.06 | 24.06-08.07 | 08.07-22.07 | 22.07-05.08 | 06.08-16.08 | 16.08-02.09 | 02.08-14.09 | 16.09-30.09
Sprint Name | #7 | #1 | #2 | #3 | #4 | #5 | #6 | #7 | #1 | #2 | #3 | #4 | #5 | #1 | #2 | #3 | #4 | Cartel#17¦After Party🪅 | Cartel#18¦Expo=Dollar(0)💸 | Cartel#19¦Dümdüz bir sprint😰 | Cartel#20¦Pixel Pixel Gozler🤪 | Cartel#21¦allstar-25💦
Total Effort In the Sprint | 63 | 105 | 47 | 39 | 37 | 37 | 43 | 29 | 37 | 55 | 41 | 65 | 69 | 88 | 96 | 114 | 39 | 112 | 92 | 105 | 117
Commited | 63 | 71 | 34 | 30 | 33 | 35 | 33 | 16 | 29 | 43 | 40 | 59 | 62 | 72 | 85 | 106 | 39 | 102 | 84 | 102 | 105 | 86
Emerged | 4 | 34 | 13 | 9 | 4 | 2 | 10 | 13 | 8 | 12 | 3 | 7 | 7 | 16 | 11 | 8 | 0 | 10 | 8 | 3 | 12
Emerged Rate | 6.349% | 32.38% | 27.66% | 23.08% | 10.81% | 5.405% | 23.26% | 44.83% | 21.62% | 21.82% | 7.317% | 10.77% | 10.14% | 18.18% | 11.46% | 7.018% | 0% | 8.929% | 8.696% | 2.857% | 10.26%
Done Bug Effort | 31 | 5 | 18 | 3 | 8 | 0 | 2 | 11 | 24 | 6 | 1 | 5 | 5 | 9 | 20 | 22 | 18 | 11 | 15 | 5 | 10
Commited Bug Effort | 27 | 5 | 23 | 0 | 8 | 0 | 8 | 19 | 16 | 14 | 1 | 10 | 7 | 33 | 27 | 25 | 23 | 5 | 15 | 10 | 5 | 20
Emerged Bug Effort | 4 | 5 | 3 | 3 | 0 | 0 | 2 | 11 | 8 | 3 | 0 | 0 | 1 | 4 | 3 | 2 | 0 | 8 | 0 |  | 0
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 36 | 37 | 32 | 29 | 37 | 37 | 16 | 13 | 24 | 10 | 15 | 47 | 24 | 38 | 28 | 34 | 23 | 94 | 50 | 27 | 56
All Tasks Done Effort | 42 | 37 | 32 | 29 | 37 | 37 | 16 | 13 | 24 | 10 | 15 | 47 | 24 | 38 | 28 | 34 | 23 | 76 | 50 | 35 | 62
Released Effort | 36 | 37 | 32 | 29 | 37 | 37 | 16 | 13 | 24 | 10 | 15 | 47 | 24 | 38 | 28 | 34 | 23 | 76 | 50 | 27 | 6
Undone PBI Effort | 19 | 68 | 13 | 10 | 0 | 0 | 27 | 16 | 13 | 45 | 26 | 18 | 45 | 50 | 62 | 83 | 16 | 18 | 42 | 70 | 55
Comitted Releasable Dev Tasks | 63 |  | 34 | 30 | 33 | 35 | 33 | 27 | 29 | 43 | 35 | 59 | 45 | 70 | 85 | 106 | 37 |  |  |  | 100 | 66
Sprint Goal | Turkcell smart recomender issue must be solve | Events & Attributes Done Forever | Android Event Attributes Sync | iOS + Andorid Release With Healthy Flows | Sdk lifecycles done | Config Done-Middle SDK | [iOS] Events Middle SDK | SDK Disabled key is not working issue must be solved | [iOS] Events Middle SDK | [iOS] Events Middle SDK | [iOS] Events Sync Middle SDK and flushing & android all released | Removing Bridging Header | Optimizing SDK to Lower App Startup Durations | iOS events and android api parts | iOS user attr and events and config and err handler and android err handler events part | iOS user attr and events and config and err handler and android err handler events part | rich push and session start issues resolve, lets go | New Flushing Improvements | Flush Ends Totally from SDK side, ready for QA camp from SDK side and Expo POC done to decide to have this product or not | Inapp logic data commection over flush system KR | Pixeli verelim, Enhanced Tempaltes ucsun, acık olan onlarca bug kapatılsın
Goal Achieved (0/1) | 100% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 66.67% | 52.11% | 94.12% | 96.67% | 112.1% | 105.7% | 48.48% | 81.25% | 82.76% | 23.26% | 37.5% | 79.66% | 38.71% | 52.78% | 32.94% | 32.08% | 58.97% | 74.51% | 59.52% | 34.31% | 59.05%
Bug/Development Ratio | 86.11% | 13.51% | 56.25% | 10.34% | 21.62% | 0% | 12.5% | 84.62% | 100% | 60% | 6.667% | 10.64% | 20.83% | 23.68% | 71.43% | 64.71% | 78.26% | 11.7% | 30% | 18.52% | 17.86%
Shipping Accuracy | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80.85% | 100% | 100% | 10.71%
Partner Focus | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 168.8% | 100% | 100% | 87.5% | 100% | 72.58% | 97.22% | 100% | 100% | 94.87% | 0% | 0% | 0% | 95.24%
Bug Score
Sprint Goal KR Effort (%) | [17 empty] | 0% | 0% | 0% | 0% | 32.56% | #DIV/0! | #DIV/0! | #DIV/0! | bar: #7 to #4
Sprint Goal Effort (%) | 25% | 61% | 17% | 51% | 39% | 45% | 39% | 50% | 48% | 52% | 57% | 35% | 31% | 34% | 34% | 32% | 30% | 69% | 17% | 34% | 51.43% | 32.56% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 85% | 30% | 85% | 100% | 100% | 100% | 30% | 30% | 30% | 30% | 30% | 100% | 30% | 30% | 30% | 30% | 100% | 30% | 15% | 30% | 30% | 15% | 0% | 0% | 0%
Updated A. Sprint Goal Success | #1: 30%; #2: 30%; #3: 30%; #4: 100% | 30% | 30%
Individual Committed Effort
Abdurrahman Sanli | #7: 22; #1: 36; #2: -
Melih Karadaş | 29 | 33 | 34 | 30 | 33 | 35 | 33 | 16 | 29 | 25 | 25 | 22 | 19 | 11 | 20 | 39 | 9 | 26 | 26 | 29 |  | 32
Alper Önal | bar: #7 to #1
Ercüment Ölçer | #2: 18; #3: 15; #4: 27; #5: 19; #1: 24; #2: 26; #3: 36; #4: 5 | 21 | 19 | 24 |  | 8
Bedir Aktaş | #4: 10; #5: 16; #1: 22; #2: 20; #3: 15; #4: 12 | 21 | 19 | 19 |  | 23
Şafak Can Baş | #5: 8; #1: 15; #2: 19; #3: 19; #4: 13 | 21 | 16 | 16 |  | 23
Betül Arı | [17 empty] | 13 | 4 | 14
Ayberk Ersoy | #7: 8; #1: 3; #2: 13; #3: -; #4: -; #5: 8
Individual Done Effort
Abdurrahman Sanli | #7: 18; #1: 11; #2: -
Sprint Goal Contribution | #7: MOB-17212
Melih Karadaş | 13 | 24 | 32 | 29 | 37 | 37 | 16 | 13 | 24 | 9 | 8 | 15 | 7 | 16 | 17 | 16 | 7 | 34 | 22 | 13
Sprint Goal Contribution | #7: MOB-17213
Alper Önal | bar: #7 to #1
Ercüment Ölçer | #2: 1; #3: 7; #4: 27; #5: 8; #1: 13; #2: 5; #3: 3; #4: 0 | 21 | 9 | 0
Bedir Aktaş | #4: 5; #5: 0; #1: 9; #2: 3; #3: 9; #4: 8 | 13 | 11 | 11
Şafak Can Baş | #5: 8; #1: 0; #2: 3; #3: 6; #4: 8 | 18 | 8 | 0
Betül Arı | [17 empty] | 8 | 0 | 11
Ayberk Ersoy | #7: 8; #1: 0; #2: 13; #4: -; #5: 8
Individual Done Rate
Abdurrahman Sanli | #7: 81.82%; #1: 30.56%
Melih Karadaş | 36.11% | 66.67% | 88.89% | 80.56% | 102.8% | 102.8% | 44.44% | 36.11% | 66.67% | 25% | 22.22% | 41.67% | 19.44% | 44.44% | 47.22% | 44.44% | 19.44% | 94.44% | 61.11% | 36.11%
Alper Önal | bar: #7 to #6
Ercüment Ölçer | #2: 5.556%; #3: 46.67%; #4: 100%; #5: 42.11%; #1: 54.17%; #2: 19.23%; #3: 8.333%; #4: 0% | 100% | 47.37% | 0%
Bedir Aktaş | #4: 50%; #5: 0%; #1: 40.91%; #2: 15%; #3: 60%; #4: 66.67% | 61.9% | 57.89% | 57.89%
Şafak Can Baş | #4: #DIV/0!; #5: 100%; #1: 0%; #2: 15.79%; #3: 31.58%; #4: 61.54% | 85.71% | 50% | 0%
Betül Arı | [17 empty] | 61.54% | 0% | 78.57%
Ayberk Ersoy | #7: 100%; #1: 0%; #2: 100%; #3: #VALUE!; #4: #VALUE!; #5: 100%; #6: #DIV/0!
Sprint Goal KR Focused Effort | [21 empty] | 28 | bar: #7
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%

## Mobile West
Mobile West
Quarter | Q1 | [5 empty] | Q2 | [7 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 22.12-04.01 | 05.01-18.01 | 18.01-01.02 | 02.02-15.02 | 16.02-29.02 | 01.03-14.03 | 15.03-28.03 | 29.03-14.04 | 15.04-25.04 | 26.04-09.05 | 10.05 - 23.05 | 24.05-06.06 | 07.06-24.06 | 24.06-04.07 | 05.07-18.07 | 19.07-01.08 | 02.08-15.08 | 16.08-29.08 | 30.08-12.09 | 13.09-26.09 | 27.09-10.10 | 11.10-24.10
Sprint Name | #7 | #1 | #2 | #3 | #4 | #5 | #6 | #7 | #8 | #9 | #10 | #11 | #12 | #13 | #14 | West ¦ Segment Kurdele 🎀 #15 | West#16¦Happy Retreats🤡 | West#17¦Karma is real🔮 | West#18¦Kovboy Ahmet🗺️🔫 | West#19¦Terapi🤲🏽/Travma🤕 | West#20¦GüneşliGünler🌞 | West#21¦Ahmetsiz Dailys📅🌜🦅
Total Effort In the Sprint | 103 | 81 | 104 | 94 | 105 | 86 | 83 | 46 | 63 | 113 | 125 | 139 | 88 | 110 | 116 | 129 | 90 | 100 | 143 | 198 | 194
Commited | 82 | 71 | 70 | 74 | 89 | 76 | 79 | 39 | 55 | 111 | 109 | 120 | 81 | 108 | 116 | 117 | 83 | 88 | 125 | 159 | 176 | 164
Emerged | 21 | 10 | 34 | 20 | 16 | 10 | 4 | 7 | 8 | 2 | 16 | 19 | 7 | 2 | 0 | 12 | 7 | 12 | 18 | 39 | 18
Emerged Rate | 20.39% | 12.35% | 32.69% | 21.28% | 15.24% | 11.63% | 4.819% | 15.22% | 12.7% | 1.77% | 12.8% | 13.67% | 7.955% | 1.818% | 0% | 9.302% | 7.778% | 12% | 12.59% | 19.7% | 9.278%
Done Bug Effort | 27 | 11 | 3 | 11 | 15 | 12 | 9 | 7 | 3 | 2 | 20 | 20 | 15 | 17 | 13 | 17 | 6 | 25 | 28 | 29 | 22
Commited Bug Effort | 6 | 8 | 13 | 11 | 13 | 7 | 5 | 5 | 0 | 0 | 15 | 16 | 13 | 17 | 13 | 17 | 5 | 21 | 10 | 28 | 11
Emerged Bug Effort | 21 | 8 | 0 | 0 | 2 | 5 | 4 | 7 | 3 | 2 | 5 | 9 | 15 | 0 | 0 | 0 | 1 | 4 | 18 | 1 | 16
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 65 | 68 | 59 | 58 | 28 | 26 | 50 | 19 | 23 | 71 | 110 | 54 | 47 | 25 | 71 | 79 | 41 | 63 | 46 | 84 | 88
All Tasks Done Effort | 65 | 71 | 92 | 76 | 34 | 36 | 53 | 19 | 28 | 71 | 115 | 87 | 63 | 40 | 76 | 116 | 70 | 89 | 75 | 97 | 132
Released Effort | 56 | 55 | 5 | 19 | 28 | 11 | 47 | 19 | 21 | 71 | 107 | 45 | 31 | 25 | 35 | 58 | 6 | 33 | 46 | 64 | 52
Undone PBI Effort | 38 | 10 | 12 | 18 | 71 | 50 | 30 | 27 | 35 | 42 | 10 | 52 | 25 | 70 | 40 | 13 | 20 | 11 | 68 | 101 | 62
Comitted Releasable Dev Tasks | 79 | 68 | 70 | 66 | 86 | 67 | 76 | 39 | 50 | 111 | 104 | 92 | 64 | 77 | 63 | 88 | 46 | 62 | 96 | 125 | 132
Sprint Goal | Test Device live | AI to Text live | Event Param live | Settings'in seçilen tableri (push channels dışındaki tüm tabler) test partnerinde live | - Settings tamamı, FCM dahil flagli Orkunbites'ta live | FCM/Settings beta partner için canlıda | Test Device Grouping Beta'da (Test partners + hepsiburada?) | FCM Unit Testleri, Push Logic Improvementı vs. Majör Fixi Kalmaması (Bayram Dönüşü Pzt, Salı canlıya çıkacak halde) | FCM & Settings Canlıda | FCM Live -Segment Migration Rules ok -Segment FE on App Push at least be ready | Segment on HB Live | FCM v2, no leftovers from KRs! | UX show! UX ler bitecektir. | Segment be ready for everyone | segment be ready, no more code left, ready for deploy | SEGMENT CANLI + ufak bir sertifika yok etmece | Segment Last Changes, Currency Needs | Enhanced Live Preview to be ready, Certificate via API for partner Ibood, App Push Improvement Points | KR focus for App Push DB start to KR with first task and Dynamic Expression for HepsiBurada (development done) | Expression on push live + App Push KR backend First Sprint tasks fully be developed | Segment Issue Jobs to be live + KR App Push Progress as planned over KR Groom
Goal Achieved (0/1) | 100% | 100% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 79.27% | 100% | 131.4% | 102.7% | 38.2% | 47.37% | 67.09% | 48.72% | 50.91% | 63.96% | 105.5% | 72.5% | 77.78% | 37.04% | 65.52% | 99.15% | 84.34% | 101.1% | 60% | 61.01% | 75%
Bug/Development Ratio | 41.54% | 16.18% | 5.085% | 18.97% | 53.57% | 46.15% | 18% | 36.84% | 13.04% | 2.817% | 18.18% | 37.04% | 31.91% | 68% | 18.31% | 21.52% | 14.63% | 39.68% | 60.87% | 34.52% | 25%
Shipping Accuracy | 86.15% | 80.88% | 8.475% | 32.76% | 100% | 42.31% | 94% | 100% | 91.3% | 100% | 97.27% | 83.33% | 65.96% | 100% | 49.3% | 73.42% | 14.63% | 52.38% | 100% | 76.19% | 59.09%
Partner Focus | 96.34% | 95.77% | 100% | 89.19% | 96.63% | 88.16% | 96.2% | 100% | 90.91% | 100% | 95.41% | 76.67% | 79.01% | 71.3% | 54.31% | 75.21% | 55.42% | 70.45% | 76.8% | 78.62% | 75%
Bug Score
Sprint Goal KR Effort (%) | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 30.49% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | bar: #7 to #14
Sprint Goal Effort (%) | 35% | 25% | 74% | 45% | 52% | 35% | 45% | 37% | 35% | 78% | 43% | 30% | 30% | 45% | 30% | 29% | 31% | 30% | 49% | 43% | 46% | 30.49% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 100% | 85% | 30% | 100% | 30% | 30% | 100% | 30% | 30% | 30% | 100% | 30% | 30% | 30% | 100% | 85% | 30% | 100% | 30% | 30% | 30% | 30% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | #14: 100% | 100% | 30% | 100% | 30% | 30%
Individual Committed Effort
Yavuz Dalkılıç | 13 | 14 | 23 | 21 | 22 | 33 | 23 | 18 | 13
Uğur Cibaroğlu | #9: 24; #10: 26; #11: 29; #12: 19; #13: 23; #14: 29 | 31 | 24 | 22 | 26 | 33 | 27 | 25
Ahmet Furtun | 38 | 28 | 16 | 24 | 26 | 16 | 26 | 11 | 21 | 24 | 24 | 32 | 24 | 31 | 30 | 27 | 14 | 11 | 23 | 29 | 28 | 26
Gökhan Atas | 33 | 30 | 31 | 29 | 31 | 27 | 33 | 10 | 21 | 29 | 31 | 31 | 21 | 26 | 31 | 33 | 31 | 9 | 25 | 30 | 26 | 25
Mansur Ekici | [20 empty] | 33 | 32
Ahmet Can Ergiyen | [17 empty] | 20 | 22 | 35 | 28 | 27
Evren Baykan | #7: -; #1: -; #2: -; #3: -; #4: 13; #5: 1; #6: 9; #8: 0
Hümeyra Doğuş | #7: -; #1: 13; #2: 13; #3: -; #5: -
Aziz Karayel | #7: 18; #1: 8; #2: -; #3: 18; #5: 7
Individual Done Effort
Yavuz Dalkılıç | 15 | 14 | 26 | 21 | 16 | 27 | 18 | 5 | 13
Uğur Cibaroğlu | #9: 11; #10: 34; #11: 19; #12: 16; #13: 5; #14: 21 | 35 | 13 | 25 | 5 | 12 | 25
Ahmet Furtun | 21 | 30 | 18 | 24 | 5 | 0 | 21 | 5 | 15 | 5 | 27 | 21 | 16 | 11 | 30 | 27 | 12 | 3 | 10 | 20 | 15
Gökhan Atas | 31 | 30 | 32 | 22 | 15 | 19 | 32 | 9 | 0 | 29 | 28 | 14 | 15 | 9 | 20 | 28 | 31 | 9 | 9 | 31 | 16
Mansur Ekici | [20 empty] | 9
Ahmet Can Ergiyen | [17 empty] | 26 | 22 | 23 | 33
Evren Baykan | #7: 13; #1: -; #2: -; #3: -; #4: 3; #5: 0; #6: 0; #8: 0
Hümeyra Doğuş | #7: -; #1: 13; #2: 13; #3: -; #5: -
Aziz Karayel | #7: 18; #2: -; #3: 18; #5: 2
Individual Commit Rate
Yavuz Dalkılıç | 115.4% | 100% | 113% | 100% | 72.73% | 81.82% | 78.26% | 27.78% | 100% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Uğur Cibaroğlu | #8: #DIV/0!; #9: 45.83%; #10: 130.8%; #11: 65.52%; #12: 84.21%; #13: 21.74%; #14: 72.41% | 112.9% | 54.17% | 113.6% | 19.23% | 36.36% | 92.59%
Ahmet Furtun | 55.26% | 107.1% | 112.5% | 100% | 19.23% | 0% | 80.77% | 45.45% | 71.43% | 20.83% | 112.5% | 65.62% | 66.67% | 35.48% | 100% | 100% | 85.71% | 27.27% | 43.48% | 68.97% | 53.57%
Gökhan Atas | 93.94% | 100% | 103.2% | 75.86% | 48.39% | 70.37% | 96.97% | 90% | 0% | 100% | 90.32% | 45.16% | 71.43% | 34.62% | 64.52% | 84.85% | 100% | 100% | 36% | 103.3% | 61.54%
Mansur Ekici | [19 empty] | #DIV/0! | 27.27%
Ahmet Can Ergiyen | #8: #DIV/0!; #9: #DIV/0!; #10: #DIV/0!; #11: #DIV/0!; #12: #DIV/0!; #13: #DIV/0!; #14: #DIV/0! | #DIV/0! | #DIV/0! | 130% | 100% | 65.71% | 117.9%
Evren Baykan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 23.08% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Hümeyra Doğuş | #VALUE! | 100% | 100% | #VALUE! | #DIV/0! | #VALUE! |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Aziz Karayel | 100% | 0% | #VALUE! | 100% | #DIV/0! | 28.57% |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Design Metrics
Commited | #7: 57; #1: 76; #2: 50; #3: 53; #4: 39; #5: 51; #6: 57 |  |  | 26 |  |  | 34 | 29
Emerged | #7: 8; #1: 3; #2: 2; #3: 2; #4: 0; #5: 13; #6: 3 |  |  | 3 |  |  | 0
Total | #7: 65; #1: 79; #2: 52; #3: 55; #4: 39; #5: 64; #6: 60 |  |  | 29 |  |  | 34
Done | #7: 49; #1: 45; #2: 52; #3: 55; #4: 39; #5: 54; #6: 60 |  |  | 26 |  |  | 34
Plan Accuracy | #7: 85.96%; #1: 59.21%; #2: 104%; #3: 103.8%; #4: 100%; #5: 105.9%; #6: 105.3%
Sprint Goal KR Focused Effort | [21 empty] | 50
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on E20: Valentine's Day -Orhun Turan

## Mobile East
Mobile East
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 22.12-04.01 | 05.01-18.01 | 18.01-01.02 | 02.02-15.02 | 16.02-29.02 | 01.03-14.03 | 14.03-28.03 | 29.03-14.04 | 15.04-25.04 | 26.04-09.05 | 10.05-23.05 | 24.05-06.06 | 07.06-24.06 | 24.06-04.07 | 05.07-19.07 | 19.07-02.08 | 02.08-16.08 | 16.08-30.08 | 30.08-13.09 | 13.09-27.09 | 30.09-11.10
Sprint Name | #7 | #1 | #2 | #3 | #4 | #5 | #6 | #7 | #8 | #9 | #10 | #11 | #12 | #13 | #14 | #15 | #16 | #17 | #18 | #19 | #20 | #21
Total Effort In the Sprint | 93 | 71 | 107 | 149 | 127 | 149 | 123 | 97 | 137 | 90 | 91 | 153 | 91 | 120 | 139 | 124 | 94 | 109 | 157 | 119 | 129
Commited | 93 | 65 | 82 | 108 | 115 | 134 | 101 | 82 | 109 | 81 | 84 | 123 | 89 | 86 | 114 | 103 | 75 | 101 | 144 | 94 | 112 | 145
Emerged | 0 | 6 | 25 | 41 | 12 | 15 | 22 | 15 | 25 | 9 | 7 | 30 | 2 | 34 | 26 | 21 | 19 | 8 | 13 | 52 | 17
Emerged Rate | 0% | 8.451% | 23.36% | 27.52% | 9.449% | 10.07% | 17.89% | 15.46% | 18.25% | 10% | 7.692% | 19.61% | 2.198% | 28.33% | 18.71% | 16.94% | 20.21% | 7.339% | 8.28% | 43.7% | 13.18%
Done Bug Effort | 10 | 9 | 15 | 35 | 26 | 17 | 25 | 23 | 15 | 32 | 9 | 25 | 15 | 23 | 25 | 50 | 35 | 16 | 4 | 28 | 12
Commited Bug Effort | 18 | 12 | 26 | 21 | 29 | 20 | 20 | 26 | 28 | 26 | 14 | 28 | 13 | 18 | 19 | 43 | 35 | 16 | 21 | 23 | 14 | 11
Emerged Bug Effort | 0 | 6 | 5 | 14 | 0 |  | 12 | 5 | 0 | 9 | 3 | 5 | 2 | 10 | 9 | 10 | 0 | 0 | 6 | 5 | 9
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 37 | 31 | 54 | 86 | 95 | 110 | 98 | 76 | 62 | 62 | 40 | 123 | 73 | 42 | 112 | 115 | 80 | 60 | 58 | 81 | 48
All Tasks Done Effort | 37 | 31 | 67 | 104 | 116 | 128 | 110 | 76 | 67 | 62 | 48 | 123 | 73 | 57 | 116 | 121 | 83 | 88 | 71 | 101 | 71
Released Effort | 15 | 23 | 42 | 33 | 63 | 99 | 78 | 57 | 19 | 28 | 30 | 101 | 24 | 14 | 92 | 71 | 66 | 45 | 56 | 68 | 11
Undone PBI Effort | 56 | 40 | 40 | 45 | 11 | 21 | 13 | 21 | 70 | 28 | 43 | 30 | 18 | 63 | 23 | 3 | 11 | 21 | 86 | 18 | 58
Comitted Releasable Dev Tasks | 93 | 65 | 69 | 108 | 102 | 129 | 89 | 82 | 112 | 81 | 71 | 123 | 89 | 81 | 104 | 97 | 72 | 79 | 105 | 62 | 87 | 120
Sprint Goal | 3 enhenced template must be live! | 3 enhenced template must be releasable! | Responsive 3 Templates on Live | - DataTable v2 > Waiting for Release - Lead export canlıda | Enhanced Live Preview and Social Proof Researches to be Completed - MultiSelect task & Datatable Expandable | - V2 Transition Completed | Completing all remaining security tasks and reproduceable bugs marked. | BUGLARI DELIVER ET LUTFEN | Social Proof & Live Preview Yeşillendir | Social Proof Yeşillendir | Get rid of dependencies and blockers!!! | Ending the survey drama & Relaxing DB & Completing FE Security | Survey Ready to Release Group Level Access Parts Ready to Release. | GLA Flagged Tasks | GLA Tasks - Green | GLA flagliler yeşil | GLA ıvır zıvırı yeşilli | Geriden kalan KR parcacıkları olmasın; GLA & Enhanced & UninstallFCM | Play for future: Next 2 KRs Research to be done and ready for KR Groom + Fixing Kube Issues for Tests | Finish Security, Finish Bugs that are marked totally | 2 partner request done, Click Data KR progress in the set of KR Groom
Goal Achieved (0/1) | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 0% | 0% | 100% | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 39.78% | 47.69% | 81.71% | 96.3% | 100.9% | 95.52% | 108.9% | 92.68% | 61.47% | 76.54% | 57.14% | 100% | 82.02% | 66.28% | 101.8% | 117.5% | 110.7% | 87.13% | 49.31% | 107.4% | 63.39%
Bug/Development Ratio | 27.03% | 29.03% | 27.78% | 40.7% | 27.37% | 15.45% | 25.51% | 30.26% | 24.19% | 51.61% | 22.5% | 20.33% | 20.55% | 54.76% | 22.32% | 43.48% | 43.75% | 26.67% | 6.897% | 34.57% | 25%
Shipping Accuracy | 40.54% | 74.19% | 77.78% | 38.37% | 66.32% | 90% | 79.59% | 75% | 30.65% | 45.16% | 75% | 82.11% | 32.88% | 33.33% | 82.14% | 61.74% | 82.5% | 75% | 96.55% | 83.95% | 22.92%
Partner Focus | 100% | 100% | 84.15% | 100% | 88.7% | 96.27% | 88.12% | 100% | 102.8% | 100% | 84.52% | 100% | 100% | 94.19% | 91.23% | 94.17% | 96% | 78.22% | 72.92% | 65.96% | 77.68%
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.38% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 58% | 35% | 24% | 24% | 31% | 44% | 24% | 28% | 35% | 32% | 31% | 30% | 30% | 41% | 36% | 38% | 31% | 30% | 33% | 46% | 32% | 37.24% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 30% | 30% | 85% | 85% | 100% | 100% | 85% | 85% | 30% | 100% | 30% | 30% | 100% | 30% | 100% | 100% | 100% | 100% | 30% | 100% | 100% | 15% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | #13: 30%; #14: 100%; #15: 100%; #16: 100%; #17: 100%; #18: 30%
Individual Committed Effort
Mert Onur Yıldırım | 43 | 22 | 30 | 28 | 37 | 34 | 31 | 18 | 23 | 25 | 27 | 28 | 21 | 21 | 22 | 22 | 14 | 27 | - | 13 | 26
Ömer Büyükçelik | 29 | 20 | 23 | 31 | 31 | 49 | 26 | 16 | 5 | 3 | 10 | 0 | 15 | 23 | 11 | 18 | 11 | 11 | 49 | 11 | 22
Bülent Tayfun | - | - | - | - | - | - | 0 | 8 | 18 | 17 | 16 | 17 | 13 | - | 21 | 15 | 12 | 24 | 32 | 24 | 28
Mert Yıldırım | - | - | - | - | - | - | 0 | 2 | 11 | 16 | 13 | 22 | 14 | 16 | 18 | 15 | 12 | 23 | 25 | 25 | 6
Gamze Özavcı | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 8 | 10 | 11
Eren Şentürk | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 25
Mansur Ekici | 9 | 23 | 24 | 27 | 33 | 36 | 31 | 25 | 31 | 34 | 28 | 35 | 15 | 3 | 24 | 19 | 13 | 16 | 30 | 22 | -
Uğur Cibaroğlu | - | - | - | 26 | 14 | 18 | 16 | 18 | 21 | - | - | - | - | - | - | - | - | - | - | - | -
Ahmet Can Ergiyen | - | - | - | - | - | - | - | - | 0 | 20 | 18 | 21 | 11 | 23 | 18 | 14 | 13 | - | - | - | -
Evren Baykan | - | - | 0 | - | - | - | - | 0 | - | 0 | 0 | 0 | - | - | - | - | - | - | - | - | -
Alper Önal | #7: 4; #1: 8
Hümeyra Doğuş | - | - | - | - | - | - | 5 |  | - | - | - | - | - | - | - | - | - | - | - | - | -
Individual Done Effort
Mert Onur Yıldırım | 11 | 11 | 27 | 32 | 37 | 34 | 31 | 22 | 3 | 22 | 23 | 33 | 20 | 5 | 19 | 22 | 17 | 28 | - | 16 | 13
Ömer Büyükçelik | 16 | 12 | 19 | 38 | 35 | 53 | 26 | 31 | 11 | 6 | 5 | 3 | 15 | 30 | 19 | 24 | 19 | 11 | 43 | 25 | 12
Bülent Tayfun | - | - | - | - | - | - | 8 | 6 | 9 | 16 | 7 | 15 | 13 | 7 | 21 | 18 | 15 | 19 | 21 | 38 | 25
Mert Yıldırım | - | - | - | - | - | - | - | 0 | 11 | 13 | 8 | 6 | 9 | 15 | 15 | 22 | 10 | 14 | 10 | 21 | 6
Gamze Özavcı | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 3 | 3 | 16
Eren Şentürk | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 23
Mansur Ekici | 5 | 8 | 16 | 29 | 33 | 36 | 38 | 25 | 13 | 26 | 26 | 48 | 10 | 3 | 25 | 25 | 6 | 19 | 22 | - | -
Uğur Cibaroğlu | - | - | - | 5 | 11 | 3 | 7 | 10 | 21 | - | - | - | - | - | - | - | - | - | - | - | -
Ahmet Can Ergiyen | - | - | - | - | - | - | - | - | 2 | 7 | 5 | 18 | 11 | 0 | 21 | 17 | 13 | - | - | - | -
Evren Baykan | 5 | - | 7 | - | - | - | - | 2 |  | 0 | 0 | 0 | - | - | - | - | - | - | - | - | -
Alper Önal | #7: 4; #1: 12
Hümeyra Doğuş | bar: #7 to #20
Individual Commit Rate
Mert Onur Yıldırım | 25.58% | 50% | 90% | 114.3% | 100% | 100% | 100% | 122.2% | 13.04% | 88% | 85.19% | 117.9% | 95.24% | 23.81% | 86.36% | 100% | 121.4% | 103.7% | #VALUE! | 123.1% | 50%
Ömer Büyükçelik | 55.17% | 60% | 82.61% | 122.6% | 112.9% | 108.2% | 100% | 193.8% | 220% | 200% | 50% | #DIV/0! | 100% | 130.4% | 172.7% | 133.3% | 172.7% | 100% | 87.76% | 227.3% | 54.55%
Bülent Tayfun | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #DIV/0! | 75% | 50% | 94.12% | 43.75% | 88.24% | 100% | #VALUE! | 100% | 120% | 125% | 79.17% | 65.62% | 158.3% | 89.29%
Mert Yıldırım | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0% | 100% | 81.25% | 61.54% | 27.27% | 64.29% | 93.75% | 83.33% | 146.7% | 83.33% | 60.87% | 40% | 84% | 100%
Gamze Özavcı | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 37.5% | 30% | 145.5%
Eren Şentürk | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 92%
Mansur Ekici | 55.56% | 34.78% | 66.67% | 107.4% | 100% | 100% | 122.6% | 100% | 41.94% | 76.47% | 92.86% | 137.1% | 66.67% | 100% | 104.2% | 131.6% | 46.15% | 118.8% | 73.33% | 113.6% | #VALUE!
Uğur Cibaroğlu | #VALUE! | #VALUE! | #VALUE! | 19.23% | 78.57% | 16.67% | 43.75% | 55.56% | 100% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ahmet Can Ergiyen | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #DIV/0! | 35% | 27.78% | 85.71% | 100% | 0% | 116.7% | 121.4% | 100% | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Evren Baykan | #VALUE! | #VALUE! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alper Önal | #7: 100%; #1: 150%; #2: #DIV/0!; #3: #DIV/0!; #4: #DIV/0!; #5: #DIV/0!; #6: #DIV/0!; #7: #DIV/0!; #13: #DIV/0!
Hümeyra Doğuş | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Design Metrics
Commited | #7: 57; #1: 76; #2: 50; #3: 53; #4: 39; #5: 51; #6: 57
Emerged | #7: 8; #1: 3; #2: 2; #3: 2; #4: 0; #5: 13; #6: 3
Total | #7: 65; #1: 79; #2: 52; #3: 55; #4: 39; #5: 64; #6: 60
Done | #7: 49; #1: 45; #2: 52; #3: 55; #4: 39; #5: 54; #6: 60
Plan Accuracy | #7: 85.96%; #1: 59.21%; #2: 104%; #3: 103.8%; #4: 100%; #5: 105.9%; #6: 105.3%
Sprint Goal KR Focused Effort | #21: 31
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on E20: Valentine's day -Orhun Turan

## Korriban
DataForce - Korriban
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 28.12-10.01 | 11.01-24.01 | 25.01-07.02 | 08.02-21.02 | 22.02-06.03 | 07.03-20.03 | 21.03-03.04 | 04.04-24.04 | 25.04-08.05 | 09.05-22.05 | 23.05-05.06 | 6.06-26.06 | 27.06-10.07 | 11.07-24.07 | 25.07-07.08 | 08.08-21.08 | 22.08-04.09 | 05.09-18.09 | 19.09-02.10
Sprint Name | Farewell Scala Dad 🎄 | 24Q1K2 - Peak Shining Dance | 24Q1K3 - this is bur(R) | 24Q1K4 - D1R | 24Q1K5 - Le QArasan | 24Q1K6 - Sezeysi | 24Q1K7 - Ananas Semsiye Kabak | 24Q2K1 - Endless Meetings | 24Q2K2 - 7 Yetmez 8 Olsun | 24Q2K3 - 1 Ispartalı | 24Q2K4 - Kafa Kalmadı | 24Q2K5 - Şaka Mı!!!??? | 24Q2K6 - To Be Groomed | 24Q3K1 - Nasil Yeneceksin | 24Q3K2 - Yenilik Ateşi | 24Q3K3 - Hoşgeldin Bilal 🚀🤸‍♂️ | 24Q3K4 - Sıfırdan Sonsuza | 24Q3K5 - Fallen Leaf Search | 24Q3K6 - Wedding Break
Total Effort In the Sprint | 110 | 129 | 139 | 142 | 172 | 174 | 124 | 228 | 216 | 208 | 212 | 188 | 204 | 126 | 198 | 127 | 110 | 136 | 119 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Commited | 110 | 126 | 133 | 136 | 157 | 168 | 114 | 198 | 181 | 162 | 193 | 173 | 173 | 110 | 167 | 113 | 97 | 122 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Emerged | 0 | 3 | 6 | 6 | 15 | 6 | 10 | 30 | 35 | 46 | 19 | 15 | 31 | 16 | 31 | 14 | 13 | 14 | 10 | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E>
Emerged Rate | 0% | 2.326% | 4.317% | 4.225% | 8.721% | 3.448% | 8.065% | 13.16% | 16.2% | 22.12% | 8.962% | 7.979% | 15.2% | 12.7% | 15.66% | 11.02% | 11.82% | 10.29% | 8.403% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Done Bug Effort | 7 | 45 | 39 | 32 | 44 | 19 | 18 | 22 | 32 | 24 | 26 | 25 | 74 | 18 | 7 | 34 | 28 | 28 | 25 | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E>
Commited Bug Effort | 12 | 48 | 36 | 27 | 33 | 16 | 18 | 9 | 37 | 37 | 26 | 17 | 79 | 26 | 11 | 42 | 30 | 41 | 31 | <INPUT> | <INPUT> | <INPUT> | <INPUT> | <INPUT> | <INPUT> | <INPUT>
Emerged Bug Effort | 0 | 0 | 3 | 5 | 11 | 3 | 0 | 13 | 8 | 5 | 8 | 8 | 5 | 0 | 0 | 0 | 3 | 0 | 0 | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E>
Done Pool Effort | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Done Pool Bug Effort | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Dev Tasks Done Effort | 54 | 109 | 117 | 66 | 81 | 33 | 43 | 80 | 96 | 162 | 150 | 105 | 130 | 48 | 80 | 107 | 81 | 89 | 81 | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E>
All Tasks Done Effort | 89 | 113 | 140 | 143 | 159 | 154 | 114 | 157 | 120 | 163 | 175 | 150 | 154 | 67 | 141 | 117 | 97 | 102 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Released Effort | 46 | 104 | 117 | 63 | 81 | 33 | 43 | 64 | 75 | 162 | 150 | 92 | 125 | 34 | 70 | 103 | 70 | 84 | 78 | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E> | <INPUT-E>
Undone PBI Effort | 21 | 13 | -7 | -7 | -2 | 14 | 0 | 41 | 61 | -1 | 18 | 23 | 19 | 43 | 26 | -4 | 0 | 20 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Comitted Releasable Dev Tasks | 75 | 87 | 131 | 68 | 75 | 36 | 46 | 112 | 147 | 143 | 139 | 139 | 168 | 101 | 141 | 110 | 82 | 112 | 137 | <INPUT> | <INPUT> | <INPUT> | <INPUT> | <INPUT> | <INPUT> | <INPUT>
Sprint Goal | Locale KR QA camp readiness | Completing Locale KR QA Camp and Completing all SIM tasks | Starting research for Locale Limitations, PCD API and SR API latency/load problems. | Completing 300+ Locale tech design and initiating Variant Management research. | Completing variant management tech design and initializing category and sub catalog collection research. | Finalizing catalog schema research KR. | Grand opening of Locale KR and fixing XML Parser Mysql Usage related problems. | Preparing catalog integration KR development plan and serving product attributes via GSS | Creating Micro Frontend Application for Catalog Integration Wizard and migrating Product Attributes to GSS | Completing Introduction and Business Details pages of Catalog Wizard and developing Dynamic Filters without System Rules | Completing XML Integration Drraft Mode and Catalog Integration Wizard Locale Page | XML multicurrency support and Completing Product Attribute Page & Catalog Intro of Wizard. | Completing Onboarding Wizard > XML Settings. | Completing XML Access Auth and Product Attributes Mapping pages on Catalog Integration Wizard | Completing Product Attributes Pages for Catalog Integration and Updating Vetro for New Fields | Completing Product Attributes Mapping and Integration Status for Catalog Integration Wizard. | Completing Data Planning Change Flows. | Developing Catalog Integration Change Flows and Completing ES Migration Preparation | Completing Change Flows for Catalog Integration Wizard
Goal Achieved (0/1) | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 80.91% | 89.68% | 105.3% | 105.1% | 101.3% | 91.67% | 100% | 79.29% | 66.3% | 100.6% | 90.67% | 86.71% | 89.02% | 60.91% | 84.43% | 103.5% | 100% | 83.61% | 74.31% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Bug/Development Ratio | 12.96% | 41.28% | 33.33% | 48.48% | 54.32% | 57.58% | 41.86% | 27.5% | 33.33% | 14.81% | 17.33% | 23.81% | 56.92% | 37.5% | 8.75% | 31.78% | 34.57% | 31.46% | 30.86% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Shipping Accuracy | 85.19% | 95.41% | 100% | 95.45% | 100% | 100% | 100% | 80% | 78.12% | 100% | 100% | 87.62% | 96.15% | 70.83% | 87.5% | 96.26% | 86.42% | 94.38% | 96.3% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Partner Focus | 68.18% | 69.05% | 98.5% | 50% | 47.77% | 21.43% | 40.35% | 56.57% | 81.22% | 88.27% | 72.02% | 80.35% | 97.11% | 91.82% | 84.43% | 97.35% | 84.54% | 91.8% | 125.7% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 39.09% | 34.92% | 41.35% | 75% | 35.03% | 60.71% | 38.6% | 39.39% | 46.41% | 43.21% | 41.97% | 51.45% | 30.64% | 42.73% | 28.14% | 30.09% | 26.8% | 38.52% | 38.53% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 30% | 30% | 100% | 100% | 30% | 100% | 30% | 15% | 100% | 85% | 100% | 100% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [13 empty] | 30% | 30% | 100% | 100% | 100% | 100%
Individual Committed Effort - All | 139 | 141 | 176 | 181 | 193 | 204 | 145 | 211 | 190 | 179 | 215 | 220 | 204 | 123 | 216 | 142 | 122 | 155 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Individual Committed Effort | 110 | 126 | 133 | 136 | 157 | 168 | 114 | 198 | 181 | 162 | 193 | 173 | 173 | 110 | 167 | 113 | 97 | 122 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0
abdullah.alrifai | 0 | 31 | [5 empty] | 50 | 39 | 45 | 51 | 48 | 50 | 47 | 49 | 31 | 48 | 44 | 49
Ceren Çakır | [10 empty] | 13 | 13 | 10 | 7 | 5 | 3 | 10 | 13 | 5
erhan.tolek | 0 | 0 | 24 | 27 | 13 | 18 | 18 | 3 | 3 | 6 | 3 | 16 | 10 | 1 | 5 | 0 | 10 | 8
Jamil Najafov | 24 | 32 | 39 | 38 | 48 | 55 | 26 | 26 | 34 | 30 | 40 | 37 | 32 | 29 | 39 | 26 | 15 | 29 | 27
kadir.pir | 5 | 0
kasim.temel | 23
Murat Cakmak | 37 | 34 | [5 empty] | 34 | 29 | 37 | 42 | 38 | 40 | 34 | 40 | 25
nihad.mammadli | 8 | 3 | 19
Rafet Topçu |  |  | 52 | 51 | 54 | 58 | 46 | 44 | 40 | 50 | 60 | 50 | 51 |  | 39 | 31 | 34 | 49 | 33
Seza Akgün |  |  | 42 | 47 | 55 | 55 | 42 | 44 | 39
Umut Yasin Colak | 16 | 12 | 0 | 18 | 23 | 18 | 13 | 10 | 6 | 11 | 6 | 18 | 11 | 5 | 39 | 26 | 5 | 12 | 23
Yasin Guzel | 26 | 29
Individual Done Effort - All | 92 | 134 | 156 | 199 | 198 | 185 | 137 | 177 | 131 | 178 | 190 | 181 | 181 | 83 | 151 | 125 | 125 | 130 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Individual Done Effort | 89 | 113 | 140 | 143 | 159 | 154 | 114 | 157 | 120 | 163 | 175 | 150 | 154 | 67 | 141 | 117 | 97 | 102 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0
abdullah.alrifai | 0 | 29 | [5 empty] | 46 | 37 | 40 | 46 | 29 | 34 | 26 | 49 | 31 | 44 | 34 | 38
Ceren Çakır | [11 empty] | 8 | 2 | 7 | 0 | 0 | 10 | 12 | 5
erhan.tolek | 0 | 8 | 16 | 27 | 5 | 18 | 18 | 3 | 0 | 5 | 3 | 0 | 4 | 4 | 5 | 3 | 10 | 8
Jamil Najafov | 24 | 34 | 45 | 40 | 63 | 60 | 26 | 34 | 5 | 37 | 44 | 38 | 34 | 28 | 47 | 26 | 15 | 26 | 24
kadir.pir | 0 | 0
kasim.temel | 7
Murat Cakmak | 37 | 21 | [5 empty] | 8 | 8 | 34 | 43 | 33 | 32 | 13 | 6 | 25
nihad.mammadli | 0 | 0
Rafet Topçu |  |  | 53 | 51 | 46 | 44 | 48 | 23 | 24 | 52 | 42 | 50 | 54 |  | 39 | 35 | 38 | 42 | 19
Seza Akgün |  |  | 42 | 52 | 50 | 50 | 40 | 46 | 46
Umut Yasin Colak | 3 | 13 | 0 | 29 | 34 | 13 | 5 | 17 | 11 | 10 | 12 | 23 | 21 | 5 | 5 | 5 | 8 | 8 | 18
Yasin Guzel | 21 | 29
Sprint Goal Contribution (Comitted) - All | 43 | 51 | 55 | 102 | 55 | 102 | 44 | 78 | 84 | 70 | 81 | 89 | 53 | 47 | 60 | 34 | 26 | 47 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal Contribution (Comitted) | 43 | 44 | 55 | 102 | 55 | 102 | 44 | 78 | 84 | 70 | 81 | 89 | 53 | 47 | 47 | 34 | 26 | 47 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0
abdullah.alrifai |  | 5 | [5 empty] | 21 | 21 | 31 | 21 | 26 | 5 | 13 | 13 | 13 | 21 | 13 | 21
erhan.tolek | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ceren Çakır | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jamil Najafov | 21 | 21 | 21 | 34 | 21 | 34 | 0 | 5 | 8 | 0 | 13 | 16 | 13 | 13 | 13 | 13 | 5 | 13 | 13
kadir.pir | 0 | 0
kasim.temel | 8
Murat Cakmak | 14 | 5 | [5 empty] | 0 | 18 | 5 | 21 | 13 | 13 | 21 | 21 | 8
nihad.mammadli | 0 | 0 | 0
Rafet Topçu |  |  | 21 | 34 | 13 | 34 | 18 | 18 | 19 | 34 | 26 | 34 | 22 |  | 0 | 0 | 0 | 21 | 8
Seza Akgün |  |  | 13 | 34 | 21 | 34 | 26 | 34 | 18 | 0 |  | 0
Umut Yasin Colak | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0
Yasin Guzel | 0 | 13
Sprint Goal Contribution (Delivered) - All | 43 | 54 | 55 | 102 | 47 | 102 | 5 | 65 | 24 | 70 | 81 | 63 | 53 | 26 | 39 | 34 | 26 | 47 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal Contribution (Delivered) | 43 | 39 | 55 | 102 | 47 | 102 | 5 | 65 | 24 | 70 | 81 | 63 | 53 | 26 | 39 | 34 | 26 | 47 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0
abdullah.alrifai |  | 5 | [5 empty] | 21 | 0 | 31 | 21 | 13 | 5 | 13 | 13 | 13 | 21 | 13 | 21
Ceren Çakır | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
erhan.tolek | 0 | 8 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jamil Najafov | 21 | 21 | 21 | 34 | 21 | 34 | 0 | 5 | 0 | 0 | 13 | 16 | 13 | 13 | 13 | 13 | 5 | 13 | 13
kadir.pir | 0 | 0
kasim.temel | 8
Murat Cakmak | 14 | 0 | [5 empty] | 0 | 5 | 5 | 21 | 0 | 13 | 0 | 0 | 8
nihad.mammadli | 0 | 0 | 0
Rafet Topçu |  |  | 21 | 34 | 13 | 34 | 5 | 5 | 1 | 34 | 26 | 34 | 22 |  | 13 | 0 | 0 | 21 | 8
Seza Akgün |  |  | 13 | 34 | 13 | 34 | 0 | 34 | 18 | 0
Umut Yasin Colak | 0 | 7 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yasin Guzel | 0 | 13
Sprint Goal KR Focused Effort
All Hands Summary | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 28.12-10.01 | 11.01-24.01 | 25.01-07.02 | 08.02-21.02 | 22.02-06.03 | 07.03-20.03 | 21.03-03.04 | 04.04-24.04 | 25.04-08.05 | 09.05-22.05 | 23.05-05.06 | 6.06-26.06 | 27.06-10.07 | 11.07-24.07 | 25.07-07.08 | 08.08-21.08 | 22.08-04.09 | 05.09-18.09 | 19.09-02.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Name | Farewell Scala Dad 🎄 | 24Q1K2 - Peak Shining Dance | 24Q1K3 - this is bur(R) | 24Q1K4 - D1R | 24Q1K5 - Le QArasan | 24Q1K6 - Sezeysi | 24Q1K7 - Ananas Semsiye Kabak | 24Q2K1 - Endless Meetings | 24Q2K2 - 7 Yetmez 8 Olsun | 24Q2K3 - 1 Ispartalı | 24Q2K4 - Kafa Kalmadı | 24Q2K5 - Şaka Mı!!!??? | 24Q2K6 - To Be Groomed | 24Q3K1 - Nasil Yeneceksin | 24Q3K2 - Yenilik Ateşi | 24Q3K3 - Hoşgeldin Bilal 🚀🤸‍♂️ | 24Q3K4 - Sıfırdan Sonsuza | 24Q3K5 - Fallen Leaf Search | 24Q3K6 - Wedding Break | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal Achieved (0/1) | Locale KR QA camp readiness ✓ | Completing Locale KR QA Camp and Completing all SIM tasks ✓ | Starting research for Locale Limitations, PCD API and SR API latency/load problems. ✓ | Completing 300+ Locale tech design and initiating Variant Management research. ✓ | Completing variant management tech design and initializing category and sub catalog collection research. ✓ | Finalizing catalog schema research KR. ✓ | Grand opening of Locale KR and fixing XML Parser Mysql Usage related problems. ✗ | Preparing catalog integration KR development plan and serving product attributes via GSS ✗ | Creating Micro Frontend Application for Catalog Integration Wizard and migrating Product Attributes to GSS ✗ | Completing Introduction and Business Details pages of Catalog Wizard and developing Dynamic Filters without System Rules ✓ | Completing XML Integration Drraft Mode and Catalog Integration Wizard Locale Page ✓ | XML multicurrency support and Completing Product Attribute Page & Catalog Intro of Wizard. ✗ | Completing Onboarding Wizard > XML Settings. ✓ | Completing XML Access Auth and Product Attributes Mapping pages on Catalog Integration Wizard ✗ | Completing Product Attributes Pages for Catalog Integration and Updating Vetro for New Fields ✗ | Completing Product Attributes Mapping and Integration Status for Catalog Integration Wizard. ✓ | Completing Data Planning Change Flows. ✓ | Developing Catalog Integration Change Flows and Completing ES Migration Preparation ✓ | Completing Change Flows for Catalog Integration Wizard ✓ | ✗ | ✗ | ✗ | ✗ | ✗ | ✗ | ✗
Sprint Goal Effort (%) | 39.09% | 34.92% | 41.35% | 75% | 35.03% | 60.71% | 38.6% | 39.39% | 46.41% | 43.21% | 41.97% | 51.45% | 30.64% | 42.73% | 28.14% | 30.09% | 26.8% | 38.52% | 38.53% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Team Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 30% | 30% | 100% | 100% | 30% | 100% | 30% | 15% | 100% | 85% | 100% | 100% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on F28: @didem.akgun@useinsider.com @tufan.cetiner@useinsider.com KR research'leri ele alırsak, committed releasable dev tasks 75 + 21 + 21 + 13 oluyor. KR Research'ler Partner Focus'tan sayılmıyor buradaki formüle göre. FYI. _Assigned to didem.akgun@useinsider.com_ -Jamil Najafov Research taskları partner focus'tan exclude edilmeli zaten, committed releasable dev tasks'a research'ler eklenmediyse doğru hesaplamışsınız demektir. fyi -Didem Akgun
Note on M23: Smokelar kubedan dolayı patladı ve release bir gün ertelendi. Urgent bakılması gereken bug olmayan konular da genel olarak aksattı.
Note on M24: Smoklar patladı mail reco ile ilgili -Jamil Najafov
Note on N23: Yine smoke'lar son ana kadar sorun oldu.
Note on O40: 2 gun tatil ve sunum hazirligi. diger herkes 1 gun tatil.
Note on P47: Burada ben 39 almamıştım fyi -Umut Yasin Colak
Note on Q47: QA taskbar üzerimde başladığımızdan bu tarz bir hata oluşuyor fyi -Umut Yasin Colak

## Vikings - WhatsApp
Vikings-WhatsApp
Quarter | Q1 | [5 empty] | Q2 |  |  |  |  | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April | May |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 5.01 | 18.01 | 2.02 | 16.02 | 1.03 | 15.03 | 29.03 - 25.04 | 26.04 - 09.05 | 10.05 - 23.05 | 26.05 - 24.06 | 24.06 - 04.07 | 05.07 - 19.07 | 20.07 - 01.08 | 02.08 - 16.08 | 16.08 - 30.08 | 02.09 - 12.09 | 13.09 - 26.09 | 27.09 - 10.10
Sprint Name | WA20: Efexor 75mg 💥 | WA21: Bjorn the Half Kyrgyz 👶 | WA22: System of a Down 💥 | WA23: Hoşgeldin Mertco 🎨 | WA24: single_ladies.mp4 👯 | WA25: Hoş geldin Aysun! 🍀 | WA26: Hayırlı Bayramlar 🍬 | WA27: Hoş Geldin Ahmet 😀 | WA28: Uyuya daldım 🐱 | WA29: Sinan Tatile Çıksın 🌞 | WA30 - Let's Go Turkey 🇹🇷 | WA31: Şampiyon Türkiye 🇹🇷 🏆 | WA32: Tüm 🇰🇷Halkı Davetlidir | WA33: No Time To Retreat 🎡 | WA34: Son yüzük bükücü 💍 | WA35: Dert Free 🫠 | WA36 - Hoş Geldin Göktuğ ☄️ | WA37: Kimin Datası Buuuu!
Total Effort In the Sprint | 118 | 134 | 126 | 149 | 145 | 149 | 214 | 188 | 154 | 218 | 161 | 185 | 176 | 130 | 172 | 168 | 169 | 164
Commited | 112 | 127 | 112 | 147 | 141 | 146 | 194 | 170 | 144 | 186 | 161 | 165 | 162 | 117 | 165 | 160 | 159 | 155
Emerged | 6 | 7 | 14 | 2 | 4 | 3 | 20 | 18 | 10 | 32 | 0 | 20 | 14 | 13 | 7 | 8 | 10 | 9
Emerged Rate | 5.085% | 5.224% | 11.11% | 1.342% | 2.759% | 2.013% | 9.346% | 9.574% | 6.494% | 14.68% | 0% | 10.81% | 7.955% | 10% | 4.07% | 4.762% | 5.917% | 5.488%
Done Bug Effort | 16 | 6 | 11 | 9 | 7 | 4 | 20 | 10 | 15 | 39 | 10 | 13 | 15 | 11 | 12 | 13 | 6 | 10
Commited Bug Effort | [6 empty] | 10
Emerged Bug Effort | [6 empty] | 10
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 69 | 18 | 51 | 34 | 37 | 21 | 102 | 43 | 53 | 94 | 68 | 71 | 70 | 35 | 66 | 46 | 40 | 50
All Tasks Done Effort | 114 | 54 | 111 | 110 | 110 | 77 | 177 | 136 | 137 | 175 | 121 | 157 | 144 | 102 | 145 | 108 | 110 | 112
Released Effort | 24 | 15 | 34 | 21 | 20 | 12 | 86 | 32 | 40 | 67 | 61 | 38 | 64 | 23 | 41 | 28 | 36 | 20
Undone PBI Effort | 4 | 80 | 15 | 39 | 35 | 72 | 37 | 52 | 17 | 43 | 40 | 28 | 32 | 28 | 27 | 60 | 59 | 52
Comitted Releasable Dev Tasks | 68 | 83 | 53 | 64 | 70 | 69 | 99 | 68 | 59 | 94 | 75 | 68 | 77 | 46 | 73 | 91 | 82 | 73
Sprint Goal | Be Consistent on Overall Analytics, Launch New Segmentation and New Usage Page for All Partners | Live Support Video and Document on WhatsApp for VikingsAnkara | Releasing Video and Document for All Partners | Launch Supporting Video and Document, Update DS Package, and Research for Enigma | Launch External Link Tracking with Feature Flag, CI/CD Automation & Media Support Automation, User Testing for Drop and Undelivered Metrics New Design | Launch External Link Tracking for VikingsAnkara & External Link Tracking QA Camp & Subscriber Page Discovery | - Launch External Link Tracking for VikingsAnkara & External Link Tracking QA Camp - Increase MPS Limit - Enigma Transition | External Link Tracking QA Camp Fixes & Enigma QA Camp & Live Enigma for Beta Partners | External Link Tracking Live & Refined Delivery Insights Research | Enigma Live for All Partners & Refined Delivery Insight Live for VikingsAnkara | Complete Segment, Export and Delivery Pending for Refined Delivery Insight | Refined Delivered Insights KR will be Live for All Partners | Eliminate Non-Contracted Message Costs Live for VikingsAnkara & Finalizing Entity Breakdown Design for Usage Analytics | QA Camp and Fixes for Eliminate Non-Contracted Message Costs | Carousel Template Ready for Development | Create a Template with Carousel Template | Launch a campaign with Carousel Template on VikingsAnkara | Campaign Creation and Message Send Live for Vikingsankara
Goal Achieved (0/1) | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 101.8% | 42.52% | 99.11% | 74.83% | 78.01% | 52.74% | 91.24% | 80% | 95.14% | 94.09% | 75.16% | 95.15% | 88.89% | 87.18% | 87.88% | 67.5% | 69.18% | 72.26%
Bug/Development Ratio | 23.19% | 33.33% | 21.57% | 26.47% | 18.92% | 19.05% | 19.61% | 23.26% | 28.3% | 41.49% | 14.71% | 18.31% | 21.43% | 31.43% | 18.18% | 28.26% | 15% | 20%
Shipping Accuracy | 34.78% | 83.33% | 66.67% | 61.76% | 54.05% | 57.14% | 84.31% | 74.42% | 75.47% | 71.28% | 89.71% | 53.52% | 91.43% | 65.71% | 62.12% | 60.87% | 90% | 40%
Partner Focus | 60.71% | 65.35% | 47.32% | 43.54% | 49.65% | 47.26% | 51.03% | 40% | 40.97% | 50.54% | 46.58% | 41.21% | 47.53% | 39.32% | 44.24% | 56.88% | 51.57% | 47.1%
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 29% | 40% | 37.5% | 27% | 37.59% | 27% | 35.57% | 14.12% | 20.65% | 28.57% | 18.63% | 18.18% | 18.52% | 25.64% | 18.18% | 38.75% | 40.25% | 41.29% | 0% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation 3 Dev, 2 QA, 2 Des | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 30% | 30% | 30% | 30% | 30% | 30% | 100% | 85% | 85% | 100% | 85% | 85% | 85% | 100% | 85% | 30% | 30% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [11 empty] | 0% | 0% | 100% | 100% | 0% | 0% | 0%
Individual Committed Effort
Yavuz | 30 | 34 | 28 | 28 | 26 | 27 | 39 | 28 | 27 | 37 | 24 | 21 | 27 | 21 | 25 | 28 | 21 | 27
Sinan | 27 | 30 | 28 | 29 | 16 | 30 | 34 | 32 | 25 | 28 | 24 | 26 | 25 | 16 | 32 | 33 | 31 | 23
Samat | 13 | 21 | 14 | 18 | 18 | 17 | 29 | 22 | 10 | 20 | 21 | 20 | 21 | 9 | 21 | 19 | 24 | 19
Ahmet | [7 empty] | - | 8 | 14 | 18 | 20 | 18 | 13 | 18 | 18 | 19 | 19
Shahla | 10 | 11 | 13 | 15 | 15 | 11 | 14 | 17 | 14 | 13 | 8 | 9 | 10 | 9 | 9 | 8 | 7 | 11
Ömer | 7 | 10 | 9 | 15 | 9 | 10 | 13 | 16 | 8 | 14 | 11 | 18 | 9 | 10 | 10 | 8 | 5 | 8
Aydın | 25 | 21 | 20 | 24 | 26 | 20 | 34 | 26 | 26 | 31 | 25 | 28 | 26 | 16 | 24 | 23 | 26 | 22
Mertcan |  |  |  | 18 | 21 | 28 | 23 | 29 | 26 | 29 | 30 | 23 | 26 | 23 | 26 | 23 | 26 | 26
Aslıhan | [6 empty] | 8
Individual Done Effort
Yavuz | 30 | 16 | 31 | 20 | 7 | 6 | 43 | 25 | 23 | 40 | 19 | 18 | 24 | 15 | 24 | 26 | 18 | 21
Sinan | 27 | 3 | 28 | 15 | 15 | 7 | 36 | 19 | 25 | 33 | 24 | 28 | 25 | 13 | 32 | 3 | 14 | 20
Samat | 14 | 1 | 9 | 10 | 15 | 7 | 27 | 15 | 8 | 17 | 19 | 20 | 22 | 9 | 19 | 12 | 5 | 11
Ahmet | [7 empty] | - | 8 | 9 | 13 | 16 | 9 | 10 | 9 | 9 | 11 | 8
Shahla | 10 | 11 | 13 | 13 | 16 | 7 | 7 | 14 | 11 | 10 | 3 | 8 | 7 | 6 | 6 | 5 | 6 | 4
Ömer | 8 | 2 | 10 | 10 | 10 | 3 | 3 | 8 | 10 | 3 | 1 | 13 | 5 | 10 | 5 | 7 | 4 | 0
Aydın | 25 | 21 | 20 | 24 | 26 | 18 | 34 | 26 | 26 | 34 | 12 | 28 | 26 | 16 | 24 | 23 | 26 | 22
Mertcan |  |  |  | 18 | 21 | 26 | 23 | 29 | 26 | 29 | 30 | 26 | 26 | 23 | 26 | 23 | 26 | 26
Aslıhan | [6 empty] | 2
Salimcan | [5 empty] | 3
Dev Planning Accuracy | 101.4% | 23.53% | 97.14% | 60% | 61.67% | 27.03% | 103.9% | 71.95% | 91.43% | 100% | 86.21% | 94.25% | 87.91% | 79.66% | 87.5% | 51.02% | 50.53% | 68.18%
QA Planning Accuracy | 105.9% | 61.9% | 104.5% | 76.67% | 108.3% | 47.62% | 37.04% | 66.67% | 95.45% | 48.15% | 21.05% | 77.78% | 63.16% | 84.21% | 57.89% | 75% | 83.33% | 21.05%
Des Planning Accuracy | 100% | 100% | 100% | 100% | 100% | 91.67% | 100% | 100% | 100% | 105% | 76.36% | 105.9% | 100% | 100% | 100% | 100% | 100% | 100%
Sprint Goal KR Focused Effort
Team Happines | 0.5 | 0 | 0 | 0 | 1 | 0 | 1 | 1 |  |  |  | 1 | 0 |  |  |  | 1
Committed Dev Sprint Effort |  |  |  | 75 | 60 | 74 | 102 | 82 | 70 | 99 |  | 71 | 70
ux_improvement labeled tasks' comitted effort |  |  |  | 8 | 5 | 10 | 18 |  |  |  |  | 2 | 7
UX İmprovement (committed) percentage |  |  |  | 10.67% | 8.333% | 13.51% | 17.65%
Done Dev Sprint Effort | [6 empty] | 106 | 59 | 64 | 99
ux_improvement labeled tasks' done effort | [6 empty] | 2 | 11 | 7
UX İmprovement (done) percentage |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | 1.887% | 18.64% | 10.94%
| Jan |  | Feb |  | March
| WA20: Efexor 75mg 💥 | WA21: Bjorn the Half Kyrgyz 👶 | WA22: System of a Down 💥 | WA23: Hoşgeldin Mertco 🎨 | WA24: single_ladies.mp4 👯 | WA25: Hoş geldin Aysun! 🍀
Goal Achieved (0/1) | 100%
Advanced Sprint Goal Success | 100% | 30% | 30% | 30% | 30% | 30%
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0% Should be calculated according to dev. But if designers and QAs are also contributing to SG then we should add them as well.
Note on A77: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on B23: couldn't deploy segmentation task because automation fix was need and we noticed it in the last day of the sprint
Note on C23: Couldn't resolve the problem in the task
Note on E23: 2/3 Done. We took the DS package update task because it was blocking our next KR and we faced problems with updating it.
Note on F23: 2/3 Done. We are taking CTA KR next sprint as well
Note on G23: we couldn't finish CTA tasks
Note on H67: @yavuz.oraltay@useinsider.com @zhanara.kolbaeva@useinsider.com burasini soyle hesaplayacagiz dev.lerin aldigi uxi / dev.lerin aldigi toplam efor. Burayi hesaplayarak gidelim hedefi yakalamak icin -Aydin Algan
Note on I31: 24/96 = 25% SG effort according to dev effort -Zhanara Kolbaeva

## Vikings - SMS
Vikings - SMS
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 |  |  |  |  | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates
Sprint Name | SMS #20 | SMS #21 | SMS #22 | SMS #23 | SMS #24 | SMS #25 | SMS #26 |  | SMS #27 | SMS #28 | SMS #29 | SMS #30 | SMS #31 | SMS #32 | SMS #33 | SMS #34 | SMS #35 | SMS #36 | SMS #37 | SMS #38 | SMS #39 | SMS #40
Total Effort In the Sprint | 127 | 141 | 134 | 130 | 134 | 150 | 169 |  | 151 | 169 | 172 | 72 | 154 | 133 | 161 | 268 | 180 | 172 | 177
Commited | 120 | 134 | 128 | 127 | 126 | 138 | 159 |  | 141 | 149 | 148 | 69 | 134 | 130 | 152 | 246 | 155 | 158 | 167 | 166
Emerged | 7 | 7 | 6 | 3 | 8 | 12 | 10 | 0 | 10 | 20 | 24 | 3 | 20 | 3 | 9 | 22 | 25 | 14 | 10 | -166 | 0 | 0 | 0 | 0 | 0
Emerged Rate | 5.512% | 4.965% | 4.478% | 2.308% | 5.97% | 8% | 5.917% | 0% | 0% | 11.83% | 13.95% | 4.167% | 12.99% | 2.256% | 5.59% | 8.209% | 13.89% | 8.14% | 5.65%
Done Bug Effort | 8 | 11 | 12 | 0 | 3 | 8 | 11 |  | 16 | 4 | 12 | 7 | 0 | 11 | 2 | 6 | 28 | 6 | 12
Commited Bug Effort | 6 | 11 | 8 | 0 | 0 | 4 | 6 |  | 14 | 3 | 5 | 4 | 0 | 11 | 1 | 2 | 20 | 5 | 8 | 6
Emerged Bug Effort | 2 | 0 | 4 | 0 | 3 | 4 | 5 | 0 | 2 | 1 | 7 | 3 | 0 | 0 | 3 | 11 | 8 | 1 | 4 | -6 | 0 | 0 | 0 | 0 | 0
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 66 | 83 | 78 | 53 | 70 | 86 | 97 |  | 85 | 67 | 85 | 22 | 56 | 68 | 50 | 125 | 71 | 99 | 73
All Tasks Done Effort | 116 | 108 | 121 | 115 | 114 | 142 | 151 |  | 134 | 119 | 118 | 43 | 109 | 100 | 81 | 195 | 117 | 154 | 111
Released Effort | 54 | 54 | 75 | 42 | 70 | 58 | 77 |  | 48 | 57 | 62 | 22 | 48 | 42 | 42 | 112 | 59 | 75 | 50
Undone PBI Effort | 11 | 33 | 13 | 15 | 20 | 8 | 18 | 0 | 17 | 50 | 54 | 29 | 45 | 33 | 80 | 76 | 63 | 18 | 66
Comitted Releasable Dev Tasks | 67 | 79 | 81 | 60 | 77 | 74 | 98 |  | 86 | 85 | 101 | 40 | 72 | 81 | 92 | 155 | 90 | 99 | 100 | 75
Sprint Goal | Add-On Structure Live | MMS Do List & Design Part | MMS Finalization | MMS: Usage Analytics QA Camp Preview Improvements | - Open MMS Feature via Gachapon Toggle - MMS QA Camp UX Improvements - Campaign Prioritization New Sending Structure for SMS | Campaign Prioratization Live + Test DONE | Enigma |  | Rich Text Input Design Enigma Kalan Tasklar Overall Conversation | - Double Opt-in - Rich Text Input (aka Superinput v2) Support - Rich Text Input V2 Design & Writing - MMS image size - [Enigma-WhatsApp-SMS] Speed optimizations for overall and related analytics | - SMS Pending for Delivery - Pending For Delivery Automation Coverage - Rich Text Input V2 Unsubscribe Sentence Design - SMS Drop structure Gonzales API Migration | No Goal due to bayram | - Set Default MPS for Turkey, UK BR and Thailand Partners - RTI Implementing Smart Encoding feature - RTI Implementing Rich Text Input with feature flag - RTI Implementing Dynamic Attributes feature - KR Discovery ¦ Silent Hours | Quiet Hours, RTI Usability Test, [BE], [FE] Overall Conversion Page, RTI ¦ Adding MMS Feature, | Conversion Duration Settings Page Remains, Quiet Hours | Conversion Duration Settings Page Remains, Quiet Hours | Improvement of Sinch & Twilio Logs, [Research] Analytics API | [BE] Analytics API - Campaign Stats Endpoint, [BE] Analytics API - Infra | ✅ Overall - Analytics API, ✅ OTP & Transactional API - Analytics API ✅ Cloud Watch Implementation | - Analytics API Automation ¦ Transactional & Verify cases, - Analytics API Automation ¦ Campaign & Overall cases, - Change Infrastructure for New Provider, - QA Camp Outputs Issues, [DOC] - Analytics API Support, - Campaign Analytics Api Validations, - [Research] Create New Integration for Infobip
Goal Achieved (0/1) | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 96.67% | 80.6% | 94.53% | 90.55% | 90.48% | 102.9% | 94.97% | 0% | 95.04% | 79.87% | 79.73% | 62.32% | 81.34% | 76.92% | 53.29% | 79.27% | 75.48% | 97.47% | 66.47%
Bug/Development Ratio | 12.12% | 13.25% | 15.38% | 0% | 4.286% | 9.302% | 11.34% | 0% | 18.82% | 5.97% | 14.12% | 31.82% | 0% | 16.18% | 4% | 4.8% | 39.44% | 6.061% | 16.44%
Shipping Accuracy | 81.82% | 65.06% | 96.15% | 79.25% | 100% | 67.44% | 79.38% | 0% | 56.47% | 85.07% | 72.94% | 100% | 85.71% | 61.76% | 84% | 89.6% | 83.1% | 75.76% | 68.49%
Partner Focus | 55.83% | 58.96% | 63.28% | 47.24% | 61.11% | 53.62% | 61.64% | 0% | 60.99% | 57.05% | 68.24% | 57.97% | 53.73% | 62.31% | 60.53% | 63.01% | 58.06% | 62.66% | 59.88%
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 28% | 29% | 39% | 51% | 46% | 38% | 30% | 0% | 44% | 40% | 24% | 3% | 27% | 35.38% | 14.28% | 36.8% | 16.77% | 18.24% | 23% | 18% | 0% | 0% | 0% | 0% | 0%
Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 100% | 30% | 100% | 100% | 100% | 100% | 100% | 0% | 30% | 100% | 85% | 15% | 100% | 100% | 85% | 100% | 85% | 85% | 70% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [8 empty] | SMS #32: 100%; SMS #33: 0%; SMS #34: 100%; SMS #35: 0%; SMS #36: 0%; SMS #37: 0%
Individual Committed Effort
İdem | 24 | 26 | 21 | 23 | 21 | 26 | 28 |  | 21 | 31 | 21 | 13 | 24 | 28 | 30 | 33 | 21 | 28 | 25
Kayahan | 27 | 34 | 32 | 31 | 36 | 28 | 45 |  | 30 | 32 | 30 | 17 | 28 | 32 | 28 | 54 | 32 | 27 | 31
Salimcan | 18 | 21 | 21 | 19 | 22 | 21 | 15 |  | 24 | 27 | 22 | - | 19 | 16 | 16 | 25 | 19 | 20 | 21
Barış | 27 | 31 | 33 | 31 | 29 | 34 | 51 |  | 33 | 28 | 37 | 19 | 34 | 21 | 36 | 55 | 36 | 28 | 35
Deniz | - | - | - | - | - | - | - |  | 5 | 8 | 15 | - | 19 | 17 | 23 | 44 | 19 | 29 | 31
Ergin | 24 | 22 | 21 | 23 | 18 | 29 | 20 |  | 17 | 15 | 15 | 8 | 11 | 14 | 12 | 21 | 14 | 16 | 16
Ozkan | - | - | - | - | - | - | - |  | 11 | 8 | 8 | 8 | 9 | 5 | 7 | 15 | 12 | 19 | 13
Individual Done Effort
İdem | 24 | 5 | 21 | 23 | 26 | 26 | 28 |  | 21 | 31 | 21 | 13 | 24 | 28 | 17 | 15 | 16 | 28
Kayahan | 26 | 34 | 35 | 24 | 27 | 37 | 48 |  | 32 | 24 | 25 | 10 | 23 | 32 | 10 | 41 | 33 | 26
Salimcan | 20 | 16 | 16 | 14 | 22 | 24 | 10 |  | 27 | 11 | 17 | - | 11 | 14 | 12 | 19 | 7 | 13
Barış | 25 | 34 | 33 | 31 | 26 | 34 | 50 |  | 28 | 34 | 33 | 11 | 27 | 13 | 24 | 62 | 31 | 34
Deniz | - | - | - | - | - | - | - |  | 5 | 3 | 10 | - | 8 | 9 | 10 | 25 | 16 | 26
Ergin | 21 | 17 | 16 | 23 | 13 | 21 | 15 |  | 17 | 11 | 7 | 8 | 13 | 3 | 7 | 22 | 9 | 19
Ozkan | - | - | - | - | - | - | - |  | 4 | 5 | 5 | 0 | 3 | 1 | 1 | 3 | 2 | 6
Sprint Goal KR Focused Effort
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%

## Kraken
Kraken |  | <<<
Quarter | Q1 | [5 empty] | Q2 | [5 empty] | Q3 | [6 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  | June |  | July |  | Aug |  | Sep |  |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | #1 05.01 - 19.01 | #2 19.01 - 02.02 | #3 02.02 - 16.02 | #4 16.02 - 01.03 | #5 01.03 - 15.03 | #6 15.03 - 29.03 | #7 29.03 - 19.04 | #8 19.04 - 03.05 | #9 03.05 - 17.05 | #10 17.05 - 03.06 | #11 03.06 - 14.06 | #11 14.06 - 28.06 | #12 28.06 - 12.07 | #13 12.07 - 26.07 | #14 26.07 - 09.08 | #15 09.08 - 23.08 | #16 23.08 - 06.09 | #17 06.09 - 20.09 | #18 20.09 - 04.10 | #19 04.10 - 18.10
Sprint Name | Welcome Berkay, Bye Sezer | Highway to Hell #45 | Tests Ran Away #46 | Nightmare #47 | HandEren #48 | Welcome Mariia and Rahmetul | Emre can take 2 more tasks | Ceku, Sakız & Sonia #51 | I am not familiar with this | Aziz Yıldırım #53 | Oppa Jose #54 | Welcome Çoruh & Lokman | Politically Correct #56 | Let me Test You #57 | BugZip #58 | Global Threat #59 | Return of the Jedi #60 | Karate Kid #61 | 3 Musketeers #62 | Much More Better #63
Total Effort In the Sprint | 406 | 420 | 458 | 431 | 404 | 391 | 350 | 370 | 351 | 343 | 355 | 252 | 390 | 376 | 374 | 294 | 343 | 411 | 499 | 441
Commited | 392 | 396 | 409 | 352 | 362 | 347 | 320 | 328 | 333 | 293 | 333 | 209 | 340 | 340 | 333 | 251 | 305 | 369 | 414 | 399
Emerged | 14 | 21 | 21 | 79 | 42 | 42 | 27 | 63 | 18 | 71 | 6 | 52 | 50 | 36 | 49 | 43 | 43 | 47 | 94 | 46
Emerged Rate | 3.448% | 5% | 4.585% | 18.33% | 10.4% | 10.74% | 7.714% | 17.03% | 5.128% | 20.7% | 1.69% | 20.63% | 12.82% | 9.574% | 13.1% | 14.63% | 12.54% | 11.44% | 18.84% | 10.43% | 0% | 0% | 0% | 0% | 0% | 0%
Done Bug Effort | 29 | 14 | 40 | 76 | 58 | 38 | 24 | 74 | 16 | 52 | 73 | 43 | 72 | 93 | 40 | 32 | 40 | 30 | 95 | 86
Commited Bug Effort | 28 | 5 | 9 | 36 | 22 | 15 | 29 | 39 | 15 | 20 | 73 | 30 | 58 | 53 | 50 | 11 | 52 | 29 | 60 | 50
Emerged Bug Effort | 6 | 21 | 28 | 74 | 36 | 21 | 27 | 42 | 4 | 35 | 3 | 24 | 24 | 40 | 5 | 24 | 5 | 29 | 32 | 46
Done Pool Effort
Done Pool Bug Effort
Releasable Done Effort | 122 | 183 | 243 | 217 | 158 | 161 | 89 | 125 | 112 | 199 | 198 | 48 | 163 | 81 | 38 | 35 | 73 | 123 | 130 | 129
All Tasks Done Effort | 250 | 293 | 369 | 350 | 275 | 345 | 181 | 214 | 186 | 267 | 241 | 135 | 320 | 194 | 149 | 101 | 202 | 227 | 397 | 292
Done Development Effort | 159 | 204 | 293 | 291 | 199 | 269 | 115 | 141 | 128 | 224 | 198 | 72 | 224 | 115 | 80 | 56 | 127 | 127 | 225 | 193
Released Effort | 122 | 183 | 54 | 217 | 158 | 106 | 89 | 125 | 112 | 199 | 169 | 48 | 153 | 81 | 38 | 35 | 73 | 123 | 130 | 105
Undone PBI Effort | 156 | 127 | 89 | 81 | 129 | 59 | 169 | 156 | 165 | 136 | 114 | 125 | 70 | 182 | 225 | 193 | 141 | 197 | 102 | 186
Comitted Releasable Effort | 233 | 247 | 244 | 177 | 236 | 263 | 217 | 168 | 206 | 216 | 256 | 131 | 202 | 237 | 164 | 141 | 152 | 288 | 263 | 221
Sprint Goal | Finishing the UI for the integration hub. | Finishing the common BE structure for Integration Hub. | Completing the Integration Hub BETA. | Removing all the blockers to deploy integration hub. | Getting the integration hub ready for all beta users. | Finishing the webhook KR without Test API. | Getting Data Stream KR completed. | Finishing the data stream for the BETA partners. | Finishing rewrite of the live user sync from Shopify to Insider | Finishing UCD to Shopify User Sync Core Structure | Finishing Live User Sync + Web Pixel | Finish User Sync Tasks | Integration Hub Live, User Sync | Opening New User Structure to All Partners | Finding how to solve App Pixel, Finishing User Sync | Moving user sync back to monitoring | Moving User Sync KR to Monitoring | User Sync Robustness Task | Finishing User Sync | Finishing Tech Designs for New KR and Doing the Rest of the KR Planning
Goal Achieved (0/1) | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 63.78% | 73.99% | 90.22% | 99.43% | 75.97% | 99.42% | 56.56% | 65.24% | 55.86% | 91.13% | 72.37% | 64.59% | 94.12% | 57.06% | 44.74% | 40.24% | 66.23% | 61.52% | 95.89% | 73.18% | 0% | 0% | 0% | 0% | 0% | 0%
Bug/Development Ratio | 18.24% | 6.863% | 13.65% | 26.12% | 29.15% | 14.13% | 20.87% | 52.48% | 12.5% | 23.21% | 36.87% | 59.72% | 32.14% | 80.87% | 50% | 57.14% | 31.5% | 23.62% | 42.22% | 44.56% | 0% | 0% | 0% | 0% | 0% | 0%
Shipping Accuracy | 100% | 100% | 22.22% | 100% | 100% | 65.84% | 100% | 100% | 100% | 100% | 85.35% | 100% | 93.87% | 100% | 100% | 100% | 100% | 100% | 100% | 81.4% | 0% | 0% | 0% | 0% | 0% | 0%
Partner Focus | 59.44% | 62.37% | 59.66% | 50.28% | 65.19% | 75.79% | 67.81% | 51.22% | 61.86% | 73.72% | 76.88% | 62.68% | 59.41% | 69.71% | 49.25% | 56.18% | 49.84% | 78.05% | 63.53% | 55.39% | 0% | 0% | 0% | 0% | 0% | 0%
Shipping Plan Accuracy | 52.36% | 74.09% | 22.13% | 122.6% | 66.95% | 40.3% | 41.01% | 74.4% | 54.37% | 92.13% | 66.02% | 36.64% | 75.74% | 34.18% | 23.17% | 24.82% | 48.03% | 42.71% | 49.43% | 47.51% | 0% | 0% | 0% | 0% | 0% | 0%
Bug Score
Sprint Goal KR Effort (%) | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 35.97% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 22.7% | 34.9% | 38.4% | 18.18% | 17% | 37% | 20% | 4.65% | 29.42% | 26.29% | 39.8% | 54.4% | 26% | 31% | 32% | 42% | 32% | 32% | 24% | 35.97% | 0% | 0% | 0% | 0% | 0% | 0%
# Team Member Participation (2 Des, 6 Dev) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 15% | 30% | 100% | 85% | 85% | 100% | 15% | 85% | 85% | 85% | 30% | 30% | 85% | 30% | 30% | 30% | 100% | 30% | 85% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [12 empty] | 100% | 30% | 30% | 30% | 100% | 30% | 100% | 100%
Individual Committed Effort
Berna Ertenli | 55 | 55 | 45 | 44 | 45 | 34 | 37 | 42 | 34 | 6 | 29 | 25 | 29 | 29 | 29 | 29 | 34 | 42 | 34 | 42 | 34
Melis Çalkıvık | 34 | 34 | 44 | 36 | 39 | 29 | 37 | 36 | 34 | 29 | 21 | 21 | 34 | 34 | 34 | 26 | 26 | 29 | 36 | 39 | 34
Demetrius King | [18 empty] | 47 | 34 | 30
Dmitri Kotikov | 48 | 47 | 39 | 41 | 41 | 39 | 47 | 34 | 42 | 45 | 53 | 15 | 45 | 47 | 42 | 29 | 39 | 42 | 42 | 39 | 40
Emre Işık | 39 | 39 | 50 | 37 | 54 | 55 | 37 | 45 | 47 | 27 | 45 | 30 | 43 | 45 | 46 | 34 | 13 | 50 | 36 | 41 | 40
Enes Menekşe | [18 empty] | 11 | 14 | 11
Eray Akartuna | 62 | 80 | 74 | 61 | 42 | 43 | 58 | 56 | 53 | 62 | 58 | 60 | 50 | 51 | 56 | 25 | 32 | 34 | 42 | 21 | 21
Maksym Modestov | 29 | 31 | 31 | 31 | 42 | 34 | 37 | 38 | 34 | 42 | 38 | 27 | 43 | 41 | 39 | 30 | 38 | 37 | 41 | 34 | 36
Rahmetullah Yiğit | 0 | 0 | 0 | 0 | 0 | 11 | 15 | 16 | 17 | 10 | 20 | 17 | 26 | 27 | 28 | 21 | 21 | 21 | 19 | 25 | 25
Recep Bıyıklı | 48 | 52 | 66 | 60 | 49 | 47 | [6 empty] | 55
Rıdvan Berkay Çetin | 36 | 58 | 60 | 42 | 50 | 55 | 52 | 47 | 56 | 65 | 55 | 0 | 55 | 50 | 34 | 39 | 37 | 52 | 48 | 50 | 50
Sezer Güven | 34 | [15 empty] | 38 | 32 | 40 | 39 | 40
Total QA Effort | 7 | 0 | 0 | 0 | 0 | 8 | 11
Eren Anar | [7 empty] | 8 | 10 | 8 | 11 | 11 | 6 | 10 | 9 | 3 | 11 | 0 | 3 | 9 | 9
Hande Kılıç | [7 empty] | 6 | 6 | 0 | 0 | 0 | 3 | 3 | 5 | 0 | 3 | 6 | 6 | 3 | 4
Lokman Günay | [13 empty] | 0 | 5 | 5 | 4 | 6 | 4 | 4 | 4
Mariia Izio | [7 empty] | 0 | 0 | 0 | 3 | 3 | 6 | 3 | 6 | 0 | 3 | 8 | 5 | 5 | 5
QA Testing Efforts | - | - | - | - | - | - | - | 36 | 33 | 32 | 28 | 23 |  | 43 |  | 21 | 48 | 45 | 28-64 | 62 | 44
Individual Done Effort
Berna Ertenli | 55 | 55 | 45 | 23 | 45 | 34 | 37 | 42 | 21 | 6 | 8 | 25 | 29 | 29 | 26 | 16 | 13 | 43 | 34 | 34
Melis Çalkıvık | 34 | 34 | 31 | 36 | 26 | 29 | 29 | 31 | 34 | 29 | 21 | 21 | 34 | 34 | 34 | 5 | 26 | 29 | 36 | 39
Demetrius King | [18 empty] | 42 | 0
Dmitri Kotikov | 14 | 0 | 47 | 62 | 59 | 52 | 47 | 44 | 16 | 40 | 14 | 7 | 29 | 16 | 34 | 29 | 10 | 37 | 34 | 44
Emre Işık | 0 | 14 | 58 | 46 | 54 | 39 | 36 | 20 | 19 | 29 | 46 | 34 | 42 | 29 | 25 | 21 | 13 | 2 | 46 | 39
Enes Menekşe | [17 empty] | 4 | 8 | 11
Eray Akartuna | 60 | 69 | 46 | 37 | 29 | 61 | 18 | 26 | 50 | 49 | 45 | 3 | 34 | 1 | 6 | 3 | 11 | 13 | 21 | 0
Maksym Modestov | 8 | 26 | 23 | 41 | 8 | 34 | 3 | 4 | 30 | 34 | 38 | 14 | 43 | 17 | 7 | 2 | 25 | 24 | 35 | 4
Rahmetullah Yiğit | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 14 | 10 | 12 | 14 | 20 | 9 | 8 | 0 | 16 | 8 | 19 | 22
Recep Bıyıklı | 14 | 39 | 60 | 67 | 54 | 47
Rıdvan Berkay Çetin | 29 | 56 | 59 | 37 | 0 | 41 | 4 | 47 | 34 | 62 | 43 | 0 | 56 | 43 | 0 | 19 | 50 | 33 | 69 | 52
Sezer Güven | 34 | [15 empty] | 21 | 18 | 41 | 36
Eren Anar | 2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 10 | 8 | 11 | 17 | 27 | 13 | 6 | 6 | 14 | 6 | 6 | 6
Hande Kılıç | [7 empty] | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lokman Günay | [13 empty] | 0 | 0 | 0 | 3 | 3 | 0 | 0
Mariia Izio | [7 empty] | 0 | 12 | 0 | 3 | 3 | 6 | 3 | 3 | 0 | 0 | 8 | 6 | 5
QA Testing Efforts | - | - | - | - | - | - | - | - | 29 | 20 | 14 | 6 | 18 |  |  | 5
Sprint Guardian | Recep | Rıdvan | Dmitri | Emre | Maksym | Recep | Rıdvan | Dmitri | Emre | Maksym | Rahmetullah | Dmitri |  | Rıdvan
Sprint Goal KR Focused Effort
Note on A25: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A34: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on B21: 250 Total Done 89 Des Done 2 QA Done 37 Re Done 122 Released -Berna Ertenli
Note on B23: 392 Total 89 Des 7 QA 63 Re 233 Rel -Berna Ertenli
Note on B24: https://winsider.atlassian.net/browse/IPR-783?atlOrigin=eyJpIjoiZjg3ZTJkODQ2NmJiNDE1YTljYTYzYzM0MzQ2MjQxMjUiLCJwIjoiaiJ9 -Berna Ertenli
Note on C20: 293 Done 89 Des -Berna Ertenli
Note on C21: 293 Done 89 Des 21 Res -Berna Ertenli
Note on C23: 396 Total 89 Des 60 Re 247 Rel -Berna Ertenli
Note on C24: https://winsider.atlassian.net/browse/IPR-783?atlOrigin=eyJpIjoiZjg3ZTJkODQ2NmJiNDE1YTljYTYzYzM0MzQ2MjQxMjUiLCJwIjoiaiJ9 -Berna Ertenli
Note on D19: Awaiting for release status was counted as done due to deployment cancelation ---- Awaiting for release status was counted as done due to deployment cancelation. -Berna Ertenli
Note on D20: 369 Done 76 Des -Berna Ertenli
Note on D21: 147SP Awaiting 34SP Ready for Release 8Sp Rejected -Zhanara Kolbaeva
Note on D23: 409 Total 89 Des 76 Re 244 Rel -Berna Ertenli
Note on D24: https://winsider.atlassian.net/browse/IPR-783?atlOrigin=eyJpIjoiZjg3ZTJkODQ2NmJiNDE1YTljYTYzYzM0MzQ2MjQxMjUiLCJwIjoiaiJ9 -Berna Ertenli
Note on E20: 350 Done 59 Des -Berna Ertenli
Note on E21: 350 Done 59 Des 74 Res -Berna Ertenli
Note on E23: 352 Total 80 Des 95 Re 177 Re -Berna Ertenli
Note on E24: https://winsider.atlassian.net/browse/IPR-783?atlOrigin=eyJpIjoiZjg3ZTJkODQ2NmJiNDE1YTljYTYzYzM0MzQ2MjQxMjUiLCJwIjoiaiJ9 -Berna Ertenli
Note on F20: 275 Done 76 Des -Berna Ertenli
Note on F21: 275 Done 76 Des 26 Res 15 Rej -Berna Ertenli
Note on F23: 362 Total 84 Des 42 Re 236 Re -Berna Ertenli
Note on F24: https://winsider.atlassian.net/browse/IPR-783?atlOrigin=eyJpIjoiZjg3ZTJkODQ2NmJiNDE1YTljYTYzYzM0MzQ2MjQxMjUiLCJwIjoiaiJ9 -Berna Ertenli
Note on G20: 332SP All Done tasks 63SP Des -Berna Ertenli
Note on G21: 332SP All Done tasks 63SP Des 3SP Rejected 13Sp Research 55SP Ready For Release (counted as Done due to deployment cancelation) ---- 332SP All Done tasks 63SP Des 3SP Rejected 13Sp Research 55SP Ready For Release (counted as Done due to deployment cancelation) -Berna Ertenli
Note on G23: 347 Com 63 Des 21 Res -Berna Ertenli
Note on G24: https://winsider.atlassian.net/browse/IPR-821?atlOrigin=eyJpIjoiY2Q0MDY2ZTVkZjI2NDA5ODhmZDMzOTlkNWI3YzY3YzMiLCJwIjoiaiJ9 -Berna Ertenli
Note on H20: 181 Done 66 Des -Berna Ertenli
Note on H21: 181 Done 66 Des 21 Res 5 Rej -Berna Ertenli
Note on H23: 320 Com 74 Des 29 Res -Berna Ertenli
Note on H24: https://winsider.atlassian.net/browse/IPR-821?atlOrigin=eyJpIjoiY2Q0MDY2ZTVkZjI2NDA5ODhmZDMzOTlkNWI3YzY3YzMiLCJwIjoiaiJ9 -Berna Ertenli
Note on I20: 214 Done 73 Des -Berna Ertenli
Note on I21: 214 Done 73 Des 13 Res 3 Rej -Berna Ertenli
Note on I23: 328 Com 78 Des 68 Res 14 QA -Berna Ertenli
Note on I24: https://winsider.atlassian.net/browse/IPR-821?atlOrigin=eyJpIjoiZDY4ZGRkMWVjNjMzNDk5NGI4YjExMjFlMmQzYTE0MGQiLCJwIjoiaiJ9 -Berna Ertenli
Note on I33: https://winsider.atlassian.net/browse/SD-104535 https://winsider.atlassian.net/browse/SD-101824 https://winsider.atlassian.net/browse/SD-100834 - Wanted to finish this KR without distracting the focus -Berna Ertenli @omer@useinsider.com ile geriye dönük baktığımızda kr ı done a götürmek için bu taskta yapılmıştı. bunu goal yüzdesine dahil ediyoruz https://winsider.atlassian.net/browse/SD-104834 -Eray Akartuna
Note on J20: 186 Done 55 Des 3 QA -Berna Ertenli
Note on J21: 186 Done 55 Des 3 QA 3 Rej 13 Res -Berna Ertenli
Note on J23: 333 Com 64 Des 47 Res 16 QA -Berna Ertenli
Note on J24: https://winsider.atlassian.net/browse/IPR-1996?atlOrigin=eyJpIjoiNDA5NzBlMzIwZTNhNDk3ZGJkODAwNWRiMTNjZGMxYzUiLCJwIjoiaiJ9 -Berna Ertenli
Note on J56: "+" ones are the ready for release ones -Berna Ertenli
Note on J60: 13+3 -Berna Ertenli
Note on J63: 24+26 -Berna Ertenli
Note on J65: 8+6 -Berna Ertenli
Note on K18: 267 Done 35 Des 3 Rej 8 QA 22 Res -Berna Ertenli
Note on K20: 267 Done 35 Des 8 QA -Berna Ertenli
Note on K21: 165 Done 19 Des 21 Research 8 QA 3 Rejected -Zhanara Kolbaeva Update: 233 Done 35 Des 3 Rej 8 QA 22 Res -Berna Ertenli
Note on K23: 293 Com 35 Des 34 Res 8 QA -Berna Ertenli
Note on K24: https://winsider.atlassian.net/browse/SD-105862 https://winsider.atlassian.net/browse/SD-105861 https://winsider.atlassian.net/browse/SD-105859 https://winsider.atlassian.net/browse/SD-105869 https://winsider.atlassian.net/browse/SD-105868 -Berna Ertenli https://winsider.atlassian.net/browse/IPR-1996?atlOrigin=eyJpIjoiNDA5NzBlMzIwZTNhNDk3ZGJkODAwNWRiMTNjZGMxYzUiLCJwIjoiaiJ9 -Berna Ertenli
Note on L18: 241 Done 29 Des 14 QA -Berna Ertenli
Note on L21: Deployment cancelled - 198 - 29 -Berna Ertenli
Note on L23: 333 Com 50 Des 13 Res 14 QA -Berna Ertenli
Note on L24: https://winsider.atlassian.net/browse/SD-106470 - 55 https://winsider.atlassian.net/browse/SD-106577 - 13 https://winsider.atlassian.net/browse/SD-106581 - 5 https://winsider.atlassian.net/browse/SD-106588 - 8 https://winsider.atlassian.net/browse/SD-106584 - 21 https://winsider.atlassian.net/browse/SD-106579 - 5 -Berna Ertenli KR - https://winsider.atlassian.net/browse/IPR-1996 -Berna Ertenli
Note on L63: 21 + 24 -Berna Ertenli
Note on L65: 7 + 5 -Berna Ertenli
Note on M18: 135 Done 46 Des 17 QA 24 Rej -Berna Ertenli
Note on M20: 135 Done 46 Des 17 QA -Berna Ertenli
Note on M23: 209 Com 46 Des 18 Res 14 QA -Berna Ertenli
Note on M24: https://winsider.atlassian.net/browse/SD-106891 - 13 https://winsider.atlassian.net/browse/SD-106998 - 13 https://winsider.atlassian.net/browse/SD-106582 - 55 https://winsider.atlassian.net/browse/SD-106470 - 0 -Berna Ertenli KR https://winsider.atlassian.net/browse/IPR-1996?atlOrigin=eyJpIjoiNDA5NzBlMzIwZTNhNDk3ZGJkODAwNWRiMTNjZGMxYzUiLCJwIjoiaiJ9 -Berna Ertenli
Note on N18: 320 Done 63 Des 33 QA 22 Rej 39 Res -Berna Ertenli
Note on N20: 320 Done 63 Des 33 QA -Berna Ertenli
Note on N23: 340 Com 63 Des 15 QA 60 Res -Berna Ertenli
Note on N24: https://winsider.atlassian.net/browse/SD-105631 -8 https://winsider.atlassian.net/browse/SD-106582 - 21 https://winsider.atlassian.net/browse/SD-105864 - 5 https://winsider.atlassian.net/browse/SD-107194 - 13 https://winsider.atlassian.net/browse/SD-102650 - 8 https://winsider.atlassian.net/browse/SD-106998 - 8 https://winsider.atlassian.net/browse/SD-105632 - 5 -Berna Ertenli KR https://winsider.atlassian.net/browse/IPR-1996 https://winsider.atlassian.net/browse/IPR-783 -Berna Ertenli
Note on O8: +1 var -Berna Ertenli
Note on O18: 194 Done 63 Des 16 QA 31 Rej 3 Res -Berna Ertenli
Note on O20: 194 Done 63 Des 16 QA -Berna Ertenli
Note on O23: 340 Com 63 Des 16 QA 24 Res -Berna Ertenli
Note on O24: https://winsider.atlassian.net/browse/SD-108079 - 2 https://winsider.atlassian.net/browse/SD-107622 - 8 https://winsider.atlassian.net/browse/SD-108074 - 1 https://winsider.atlassian.net/browse/SD-108086 - 13 https://winsider.atlassian.net/browse/SD-108028 - 21 https://winsider.atlassian.net/browse/SD-108049 - 3 https://winsider.atlassian.net/browse/SD-107621 - 8 https://winsider.atlassian.net/browse/SD-108030 - 5 -Berna Ertenli https://winsider.atlassian.net/browse/IPR-1996 - KR -Berna Ertenli
Note on P18: 149 Done 60 Des 9 QA 8 Rej 34 Res -Berna Ertenli
Note on P20: 149 Done 60 Des 9 QA -Berna Ertenli
Note on P23: 333 Com 63 Des 25 QA 81 Res -Berna Ertenli
Note on P24: https://winsider.atlassian.net/browse/IPR-1996?atlOrigin=eyJpIjoiYTNjNDRhZmZiMTYxNGY5Njk2MDUzZmI3NDFmN2M2ZTciLCJwIjoiaiJ9 -Berna Ertenli
Note on Q18: 101 Done 21 Des 6 QA 21 Res 18 Awaiting Release -Berna Ertenli
Note on Q20: 101 Done 21 Des 6 QA 18 Awaiting Release -Berna Ertenli
Note on Q23: 251 Com 55 Des 8 QA 47 Res -Berna Ertenli
Note on Q24: https://winsider.atlassian.net/browse/IPR-1996?atlOrigin=eyJpIjoiYTNjNDRhZmZiMTYxNGY5Njk2MDUzZmI3NDFmN2M2ZTciLCJwIjoiaiJ9 - KR -Berna Ertenli https://winsider.atlassian.net/browse/SD-108028 -21 https://winsider.atlassian.net/browse/SD-108086 - 13 https://winsider.atlassian.net/browse/SD-107622 - 3 https://winsider.atlassian.net/browse/SD-104667 - 21 https://winsider.atlassian.net/browse/SD-109089 - 21 https://winsider.atlassian.net/browse/SD-107621 - 0 -Berna Ertenli
Note on R18: 202 Done 39 Des 17 QA 33 Rej 21 Res 19 Awaiting Rel. -Berna Ertenli
Note on R20: 202 Done 39 Des 17 QA 19 Awaiting Rel. -Berna Ertenli
Note on R23: 299 Com 60 Des 21 QA 71 Res -Berna Ertenli
Note on R24: https://winsider.atlassian.net/browse/IPR-1996?atlOrigin=eyJpIjoiZTJhYzRjNGVkMTg1NDBjN2EzZWY3YTE4NzI0YzdlYzYiLCJwIjoiaiJ9 - KR -Berna Ertenli https://winsider.atlassian.net/browse/SD-107621 - 0 https://winsider.atlassian.net/browse/SD-107622 - 0 https://winsider.atlassian.net/browse/SD-108086 - 0 https://winsider.atlassian.net/browse/SD-109541 - 42 (21, 13,8) https://winsider.atlassian.net/browse/SD-108028 - 8 https://winsider.atlassian.net/browse/SD-109089 - 1 https://winsider.atlassian.net/browse/SD-109605 - 21 -Berna Ertenli
Note on S18: 227 Done 71 Des 4 Rej 26 Ready for Release 3 Awaiting Rel. -Berna Ertenli
Note on S20: 227 Done 71 Des 26 Awaiting Rel. 3 Ready for Rel. -Berna Ertenli
Note on S23: 369 Com 61 Des 20 QA 0 Res -Berna Ertenli
Note on S24: https://winsider.atlassian.net/browse/DT-21088 - 21 https://winsider.atlassian.net/browse/SD-109993 - 8 https://winsider.atlassian.net/browse/SD-109559 - 45 https://winsider.atlassian.net/browse/SD-109985 - 2 https://winsider.atlassian.net/browse/SD-108028 - 0 https://winsider.atlassian.net/browse/SD-110127 - 13 https://winsider.atlassian.net/browse/SD-110117 - 13 https://winsider.atlassian.net/browse/SD-110172 - 8 https://winsider.atlassian.net/browse/SD-110097 - 21 -Berna Ertenli KR - https://winsider.atlassian.net/browse/IPR-1996 -Berna Ertenli
Note on T18: 397 Done 70 Des 3 Rej 92 Res 12 QA 61 Ready for Rel. 29 Awaiting Rel. -Berna Ertenli
Note on T20: 397 Done 70 Des 12 QA 61 Ready for Rel. 29 Awaiting Rel. -Berna Ertenli
Note on T23: 414 Com 70 Des 18 QA 63 Res -Berna Ertenli
Note on T24: https://winsider.atlassian.net/browse/SD-109559 - 21 https://winsider.atlassian.net/browse/SD-110812 - 21 https://winsider.atlassian.net/browse/SD-110172 - 3 https://winsider.atlassian.net/browse/SD-110097 - 13 https://winsider.atlassian.net/browse/SD-110811 - 13 https://winsider.atlassian.net/browse/SD-110645 - 8 -Berna Ertenli KR - https://winsider.atlassian.net/browse/IPR-1996 -Berna Ertenli
Note on U21: deployment cancelled 5 times during this sprint - 24 Ready for Release 21 Awaiting Release -Didem Akgun
Note on U23: 399 Com 81 Des 21 QA 76 Res -Berna Ertenli
Note on U24: https://winsider.atlassian.net/browse/DT-21748 - 34 https://winsider.atlassian.net/browse/SD-111212 - 21 https://winsider.atlassian.net/browse/SD-111211 - 34 https://winsider.atlassian.net/browse/SD-111213 - 8 https://winsider.atlassian.net/browse/DT-21746 - 34 https://winsider.atlassian.net/browse/DT-21744 - 5 -Berna Ertenli KR - https://winsider.atlassian.net/browse/IPR-18979 -Berna Ertenli
Note on U28: 24 sp ready for released -Didem Akgun

## Liron
Liron
Quarter | Q1 | [6 empty] | Q2 | [5 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  |  | April |  | May |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 28/12/2023 - 12/01/2024 | 12/01/2024 - 26/01/2024 | 26/01/2024 - 09/02/2024 | 09/02/2024 - 23/02/2024 | 23/02/2024 - 08/03/2024 | 08/03/2024 - 22/03/2024 | 22/03/2024 - 05/04/2024 | 05/04/2024 - 19/04/2024 | 19/04/2024 - 03/05/2024 | 03/05/2024 - 17/05/2024 | 17/05/2024 - 31/05/2024 | 31/05/2024 - 14/06/2024 | 14/06/2024 - 5/07/2024 | 05/07/2024 - 19/07/2024 | 19/07/2024 - 02/08/2024 | 02/08/2024 - 16/08/2024 | 16/08/2024 - 02/09/2024 | 02/09/2024 - 13/09/2024 | 13/09/2024 - 26/09/2024 | 26/09/2024 - 11/10/2024 | 11/10/2024 - 25/10/2024
Sprint Name | Liron - 24Q1 - Sprint#1 | Liron - 24Q1 - Sprint#2 | Liron - 24Q1 - Sprint#3 | Liron - 24Q1 - Sprint#4 | Liron - 24Q1 - Sprint#5 | Liron - 24Q1 - Sprint#6 | Liron - 24Q1 - Sprint#7 | Liron - 24Q2 - Sprint#1 | Liron - 24Q2 - Sprint#2 | Liron - 24Q2 - Sprint#3 | Liron - 24Q2 - Sprint#4 | Liron - 24Q2 - Sprint#5 | Liron - 24Q2 - Sprint#6 | Liron - 24Q3 - Sprint#1 | Liron - 24Q3 - Sprint#2 | Liron - 24Q3 - Sprint#3 | Liron - 24Q3 - Sprint#4 | Liron - 24Q3 - Sprint#5 | Liron - 24Q3 - Sprint#6 | Liron - 24Q4 - Sprint#1 | Liron - 24Q4 - Sprint#2
Total Effort In the Sprint | 198 | 232 | 276 | 286 | 307 | 284 | 249 | 108 | 230 | 308 | 296 | 231 | 247 | 162 | 188 | 160 | 196 | 150 | 95 | 93
Commited | 180 | 228 | 213 | 250 | 235 | 246 | 217 | 103 | 221 | 267 | 270 | 218 | 224 | 152 | 173 | 149 | 175 | 125 | 95 | 90
Emerged | 18 | 32 | 26 | 36 | 72 | 35 | 32 | 5 | 9 | 41 | 26 | 13 | 23 | 10 | 15 | 11 | 21 | 25 | 0 | 3
Emerged Rate | 10% | 10% | 10% | 12.59% | 23.45 | 12.3% | 16.06% | 5.56% | 2.64% | 13.31% | 8.78% | 5.63% | 9.31 | 6.17% | 7.98% | 6.88% | 10.71% | 16.67% | 0% | 3.23%
Done Bug Effort | 40 | 38 | 51 | 33 | 31 | 47 | 27 | 19 | 45 | 53 | 26 | 54 | 38 | 36 | 12 | 25 | 12 | 33 | 10 | 11
Commited Bug Effort | 39 | 41 | 46 | 18 | 21 | 49 | 25 | 21 | 39 | 37 | 13 | 51 | 23 | 29 | 8 | 23 | 9 | 27 | 10 | 11
Emerged Bug Effort | 6 | 6 | 5 | 15 | 10 | 6 | 15 | 1 | 6 | 16 | 14 | 3 | 15 | 7 | 4 | 10 | 3 | 6 | 0 | 0
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 130 | 186 | 193 | 198 | 121 | 163 | 111 | 50 | 143 | 170 | 152 | 163 | 195 | 161 | 168 | 121 | 142 | 74 | 61 | 53
All Tasks Done Effort | 146 | 186 | 230 | 218 | 223 | 202 | 184 | 93 | 174 | 178 | 262 | 184 | 226 | 161 | 178 | 147 | 152 | 113 | 69 | 53
Released Effort | 37 | 81 | 124 | 101 | 85 | 58 | 77 | 14 | 93 | 97 | 89 | 33 | 94 | 73 | 42 | 30 | 100 | 51 | 30 | 8
Undone PBI Effort | 52 | 69 | 46 | 68 | 89 | 77 | 65 | 15 | 56 | 130 | 34 | 47 | 21 | 1 | 10 | 13 | 44 | 37 | 26 | 40
Comitted Releasable Dev Tasks | 159 | 212 | 213 | 209 | 135 | 197 | 136 | 60 | 177 | 225 | 160 | 171 | 193 | 152 | 163 | 123 | 165 | 165 | 87 | 71
Sprint Goal | Being able to filter campaigns by Group Level Access on the Campaign Listing Page of Web Templates | Being ready for the beta process in GLA KR - Being ready for the new partner activation on Gachapon | - Finalizing the development phase for GLA KR - Making the New Tab ready for current partners and completing the test partners' transition | - Finalizing the development of Gachapon Update KR and completing the Current Partner Transition P1 - Enabling Structure for PaG and Lead Collection templates - Finalizing the Enigma transition for Custom Segments | - Finalizing Web Suite Pricing Package Update KR - Completing the Instory Enigma Research - Completing the DS Component Updates except Data Table | - Finalizing the development of Enigma Transition KR - Being ready to launch Structures to all partners | - Enabling Structures for all partners - Finalizing the UCD Tech Design tasks - Completing the partner transition for Enigma KR | - Finalizing the Improving Export Variation Duration Tech Design P.1 | - Finalizing the Image URL Generator KR (x) - Completing the Tech Design and first step of Export Variation | - Launching Skywalker Improvement - Local Environment to be ready for Export Duration KR | - Kube and Export System to be ready to fetch CSV - Finalizing the development of the Image URL Generation KR | Panel design to be ready to download and CSV files from creation until saving to be ready | - Export Duration: Email sent to real users - UCD: Necessary environments to be ready | - Test partners are able to download data from url. - Completing the first part of the BE service. | - Finalizing the development of Export Duration KR - Finalizing the Kube creation and Segment Page P.1 | - Finalizing the happy path flow on Segment page | - Finalizing the development tasks of UCD transition | - Finalizing the development of UCD Transition KR - Finalizing the required development on Pandora for unsafe-eval | - Finalizing the "Removing the unsafe-eval" KR | - Finalizing the development of "Removing the unsafe-eval" KR | - Being ready for the AI-Based Text Generation KR Grooming
Goal Achieved (0/1) | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 81.11% | 81.58% | 108% | 87.2% | 94.89% | 82.11% | 84.79% | 90.29% | 78.73% | 66.67% | 97.04% | 84.4% | 100.9% | 105.9% | 102.9% | 98.66% | 86.86% | 90.4% | 72.63% | 58.89%
Bug/Development Ratio | 30.77% | 20.43% | 26.42% | 16.67% | 25.62% | 28.83% | 24.32% | 38% | 31.47% | 31.18% | 17.11% | 33.13% | 19.49% | 22.36% | 7.143% | 20.66% | 8.451% | 44.59% | 16.39% | 20.75%
Shipping Accuracy | 28.46% | 43.55% | 64.25% | 51.01% | 70.25% | 35.58% | 69.37% | 28% | 65.03% | 57.06% | 58.55% | 20.25% | 48.21% | 45.34% | 25% | 24.79% | 70.42% | 68.92% | 49.18% | 15.09%
Partner Focus | 88.33% | 92.98% | 100% | 83.6% | 57.45% | 80.08% | 62.67% | 58.25% | 80.09% | 84.27% | 59.26% | 78.44% | 86.16% | 100% | 94.22% | 82.55% | 94.29% | 132% | 91.58% | 78.89%
Bug Ratio | 22.22% | 16.67% | 23.94% | 13.2% | 13.19% | 19.11% | 12.44% | 18.45% | 20.36% | 19.85% | 9.63% | 24.77% | 16.96% | 23.68% | 6.936% | 16.78% | 6.857% | 26.4% | 10.53% | 12.22%
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 18% | 30.26% | 31% | 36.8% | 33% | 17.07% | 25.81% | 28.16% | 29.86% | 29.96% | 25.93% | 35.78% | 38.84% | 51.97% | 57.23% | 40.27% | 65.71% | 57.6% | 44.21% | 14.44% | 0% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 70% | 30% | 100% | 100% | 30% | 70% | 85% | 70% | 30% | 30% | 85% | 100% | 30% | 100% | 100% | 100% | 30% | 30% | 30% | 85% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [12 empty] | 30% | 100% | 100% | 100% | 30% | 30% | 30%
[Tech tasks] committed ¦ Unit Tests | [8 empty] | 21 | 11 | 8 | 11 | 5 | 13 | 13 | 19 | 10 |  |  | 0
[Tech tasks] done ¦ Unit Tests | [8 empty] | 21 | 8 | 0 | 11 | 8 | 13 | 13 | 14 | 10 |  |  | 0
[Tech tasks] committed ¦ Security | [8 empty] | 7 | 13 | 0 | 13 | 21 | 0 | 0 | 0 | 21 |  |  | 5
[Tech tasks] done ¦ Security | [8 empty] | 7 | 13 | 3 | 13 | 21 | 3 | 0 | 0 | 0 |  |  | 5
[Tech tasks] committed ¦ Tech Debts | [8 empty] | 0 | 8 | 8 | 0 | 16 | 8 | 8 | 0 | 8 |  |  | 3
[Tech tasks] done ¦ Tech Debts | [8 empty] | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 3
Committed Unit Tests in Q
Committed Security in Q
Commited Tech Debts in Q
Sprint Goal Effort | 32 | 69 | 67 | 92 | 79 | 42 | 56 | 29 | 66 | 80 | 70 | 78 | 87 | 79 | 99 | 60 | 115 | 72 | 42 | 13
Retro board link | link | link | link | link | link | link | link | link | link | link | link | link | link | link | link | link | link | link | link | link
Individual Committed Effort
Arda Berrun Karaca | [11 empty] | 5 | 12
Aziza Kasenova | 36 | 41 | 39 | 34 | 18 | 32 | 34 | 24 | 29 | 45 | 43 | 36 | 37
Fatih Ertugral | - | 44 | 55 | 54 | 55 | 57 | 46 | 16 | 36 | 49 | 55 | 53 | 55 | 55 | 56 | 42 | 50 | 49 | 51 | 51
Sahin Deniz | 42 | 41 | 10 | 46 | 49 | 45 | 42 | 18 | 34 | 49 | 49 | 51 | 43
Tugay İlik | - | - | - | 8 |  |  | 8 |  | 9 |  | 8 |  |  | - | - | - | - | - | - | -
Semih Ünal | 42 | 42 | 45 | 34 | 40 | 42 | 23 | 14 | 45 | 44 | 44 | 40 | 46 | 47 | 52 | 39 | 51 | 43 | 15 | 40
Samet Sevindi |  | - | 5
Samet Yıldırım | 15 | 19 | 24 | 26 | 23 | 25 | 27 | 12 | 25 | 33 | 33 | 33 | 26 | 34 | 32 | 31 | 35
Umur Akbulut | [11 empty] | 5 | 5 | 23 | 31 | 32 | 39 | 35
Individual Done Effort
Arda Berrun Karaca | [11 empty] | 5 | 7
Aziza Kasenova | 36 | 43 | 39 | 39 | 18 | 30 | 38 | 25 | 32 | 34 | 49 | 36 | 41
Fatih Ertugral | - | 18 | 60 | 55 | 70 | 49 | 35 | 16 | 26 | 31 | 55 | 45 | 51 | 55 | 48 | 43 | 47 | 47 | 51 | 28
Sahin Deniz | 36 | 26 | 19 | 19 | 39 | 26 | 33 | 18 | 7 | 23 | 50 | 25 | 48
Tugay İlik | - | - | - | 0 |  |  | 8 |  | 9 |  | 10 |  |  | 3 | - | - | - | - | - | -
Semih Unal | 45 | 42 | 46 | 42 | 40 | 43 | 27 | 16 | 45 | 47 | 44 | 40 | 48 | 47 | 61 | 44 | 52 | 39 | 18 | 43
Samet Sevindi | 7 | 2 | 5 |  | 5 |  | 2
Samet Yildirim | 16 | 19 | 14 | 16 | 14 | 10 | 16 | 12 | 25 | 12 | 23 | 30 | 18 | 33 | 31 | 36 | 14
Umur Akbulut | [12 empty] | 8 | 23 | 35 | 24 | 39 | 27
average committed | 33.75 | 37.4 | 29.6667 | 33.6667 | 37 | 40.2 | 30 | 16.8 | 29.6667 | 44
sum committed | 135 | 187 | 178 | 202 | 185 | 201 | 180 | 84 | 178 | 220
10% | 13.5 | 18.7 | 17.8 | 20.2 | 18.5 | 20.1 | 18 | 8.4 | 17.8 | 22
Merged effort | [8 empty] | 122
Shipping Accuracy with merged only | [8 empty] | 85.31%
Individual Done Effort - %
Aziza Kasenova | 100 | 104.878 | 100 | 114.7059 | 100 | 93.75 | 111.7647 | 104.1667 | 110.3448 | 75.5556 | 113.9535 | 100 | 110.8108 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Fatih Ertugral |  | 40.9091 | 109.0909 | 101.8519 | 127.2727 | 85.9649 | 76.087 | 100 | 72.2222 | 63.2653 | 100 | 84.9057 | 92.7273 | 100 | 85.7143 | 102.381 | 94 | 95.9184 | 100
Sahin Deniz | 85.7143 | 63.4146 | 190 | 41.3043 | 79.5918 | 57.7778 | 78.5714 | 100 | 20.5882 | 46.9388 | 102.0408 | 49.0196 | 111.6279 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Yaman Ozdemir | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Tugay İlik | [6 empty] | 100 |  | 100
Semih Ünal | 107.1429 | 100 | 102.2222 | 123.5294 | 100 | 102.381 | 117.3913 | 114.2857 | 100 | 106.8182 | 100 | 100 | 104.3478 | 100 | 117.3077 | 112.8205 | 101.9608 | 90.6977 | 120
Samet Yıldırım | 106.6667 | 100 | 58.3333 | 61.5385 | 60.8696 | 40 | 59.2593 | 100 | 100 | 36.3636 | 69.697 | 90.9091 | 69.2308 | 97.0588 | 96.875 | 116.129 | 40 | #DIV/0!
Umur Akbulut | [9 empty] | #DIV/0! | #DIV/0! | 0 | 160 | 100 | 112.9032 | 75 | 100 | 77.1429
Sprint Goal KR Focused Effort
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A29: Done Bug/All Committed -Didem Akgun
Note on A33: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on B33: sprint'te olan toplam dev. 6, %33 -Didem Akgun
Note on C33: 4/7, %57 -Didem Akgun
Note on D33: 4/7 -Didem Akgun
Note on E33: 5 devs out of 6, 37% -Aziza Kasenova
Note on F33: 5 devs -Aziza Kasenova
Note on G33: 2 devs -Didem Akgun
Note on H8: uyusmuyor -Aziza Kasenova
Note on H33: 4/7 -Aziza Kasenova
Note on I8: different from pickle bc of Yaman's SEL task -Aziza Kasenova
Note on I20: do we need to calculate rejected ones here, @didem.akgun@useinsider.com ? -Aziza Kasenova 15 with SEL task -Aziza Kasenova nope rejected ones and sel tasks are not included -Didem Akgun
Note on J19: Aziza: check -Aziza Kasenova
Note on J33: 3/6 -> 50% -Aziza Kasenova
Note on K34: yine ayni hata var burada, @didem.akgun@useinsider.com -Aziza Kasenova %30 gelmiş 15 K30'dan 15 K31'den. hatayı göremedim -Didem Akgun manually girdim ben 30u :D -Aziza Kasenova
Note on L33: 4/6 -Aziza Kasenova
Note on M33: 3/6 -Aziza Kasenova
Note on N33: 4/7 -Aziza Kasenova
Note on O7: Mert'in 8 efor -> ilerledi. Samet'in 1 efor -> kaldı. Tugay extra 3 efor-> ilerletti. 8+3-1 = 10 -Semih Unal
Note on O33: 3/4 -Semih Unal Fatih, Semih, Samet -Semih Unal
Note on P33: 3/4 -Semih Unal Fatih, Semih, Umur -Semih Unal
Note on P46: 34+5+34+13+13 -Semih Unal
Note on Q33: 3 Umur, Fatih, Semih -Semih Unal
Note on R33: 4/4 -Semih Unal
Note on R36: https://winsider.atlassian.net/issues/?filter=15525&jql=labels%20%3D%20unit_test%20AND%20sprint%20%3D%2011179 -Semih Unal
Note on R38: https://winsider.atlassian.net/issues/?filter=15525&jql=labels%20%3D%20security_task%20AND%20sprint%20%3D%2011179 -Semih Unal
Note on R40: https://winsider.atlassian.net/issues/?filter=15525&jql=labels%20%3D%20tech_debt%20AND%20sprint%20%3D%2011179 -Semih Unal
Note on S33: 3/3 -Semih Unal
Note on T33: 3 -Semih Unal
Note on U33: 1 -Semih Unal fatih -Semih Unal
Note on V33: 1 -Semih Unal semih -Semih Unal

## Skeletors
Skeletors
Quarter | Q1 | [6 empty] | Q2 | [5 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  |  | April |  | May |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 28/12/2023 - 11/01/2024 | 11/01/2024 - 25/01/2024 | 25/01/2024 - 08/02/2024 | 08/02/2024 - 22/02/2024 | 22/02/2024 - 07/03/2024 | 07/03/2024 - 21/03/2024 | 21/03/2024 - 04/04/2024 | 04/04/2024 - 18/04/2024 | 18/04/2024 - 02/05/2024 | 02/05/2024 - 16/05/2024 | 16/05/2024 - 30/05/2024 | 30/05/2024 - 13/06/2024 | 13/06/2024 - 04/07/2024 | 04/07/2024 - 18/07/2024 | 18/07/2024 - 01/08/2024 | 01/08/2024 - 15/08/2024 | 15/08/2024 - 29/08/2024 | 29/08/2024 - 12/09/2024 | 13/09/2024 - 26/09/2024 | 26/09/2024 - 10/10/2024 | 10/10/2024 - 24/10/2024 | 24/10/2024 - 07/11/2024 | 07/11/2024 - 21/11/2024 | 21/11/2024 - 05/12/2024 | 05/12/2024 - 19/12/2024 | 19/12/2024 - 02/01/2024
Sprint Name | [2024][Q1] Skeletors #1 | [2024][Q1] Skeletors #2 | [2024][Q1] Skeletors #3 | [2024][Q1] Skeletors #4 | [2024][Q1] Skeletors #5 | [2024][Q1] Skeletors #6 | [2024][Q1] Skeletors #7 | [2024][Q2] Skeletors #1 | [2024][Q2] Skeletors #2 | [2024][Q2] Skeletors #3 | [2024][Q2] Skeletors #4 | [2024][Q2] Skeletors #5 | [2024][Q2] Skeletors #6 | [2024][Q3] Skeletors #1 | [2024][Q3] Skeletors #2 | [2024][Q3] Skeletors #3 | [2024][Q3] Skeletors #4 | [2024][Q3] Skeletors #5 | [2024][Q3] Skeletors #6 | [2024][Q4] Skeletors #1 | [2024][Q4] Skeletors #2 | [2024][Q4] Skeletors #3 | [2024][Q4] Skeletors #4 | [2024][Q4] Skeletors #5 | [2024][Q4] Skeletors #1 | [2024][Q4] Skeletors #6
Total Effort In the Sprint | 206 | 211 | 193 | 197 | 193 | 197 | 212 | 102 | 161 | 207 | 205 | 204 | 222 | 218 | 226 | 117 | 242 | 205 | 223 | 230
Commited | 184 | 187 | 189 | 177 | 181 | 187 | 183 | 97 | 149 | 198 | 191 | 167 | 201 | 196 | 179 | 114 | 199 | 194 | 203 | 195 | 181
Emerged | 20 | 11 | 4 | 20 | 12 | 8 | 29 | 5 | 12 | 9 | 14 | 37 | 23 | 22 | 47 | 5 | 43 | 14 | 29 | 35
Emerged Rate | 9.709% | 5.213% | 2.073% | 10.15% | 6.218% | 4.061% | 13.68% | 4.902% | 7.453% | 4.348% | 6.829% | 18.14% | 10.36% | 10.09% | 20.8% | 4.274% | 18% | 8.29% | 13% | 15%
Done Bug Effort | 8 | 34 | 48 | 45 | 79 | 34 | 42 | 9 | 36 | 36 | 24 | 52 | 43 | 30 | 78 | 23 | 56 | 24 | 58 | 50
Commited Bug Effort | 19 | 40 | 55 | 40 | 76 | 34 | 46 | 12 | 28 | 36 | 31 | 46 | 72 | 55 | 64 | 37 | 46 | 18 | 42 | 42
Emerged Bug Effort | 0 | 10 | 1 | 20 | 8 | 0 | 12 | 0 | 11 | 9 | 13 | 9 | 13 | 3 | 26 | 4 | 18 | 9 | 21 | 11
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 107 | 190 | 162 | 132 | 162 | 163 | 172 | 94 | 126 | 152 | 111 | 135 | 129 | 153 | 138 | 85 | 98 | 154 | 122 | 125
All Tasks Done Effort | 112 | 190 | 162 | 145 | 175 | 184 | 172 | 94 | 145 | 152 | 119 | 135 | 142 | 164 | 188 | 98 | 106 | 165 | 177 | 185
Released Effort | 21 | 53 | 57 | 55 | 57 | 122 | 101 | 17 | 63 | 55 | 44 | 55 | 64 | 77 | 91 | 49 | 61 | 55 | 40 | 21
Undone PBI Effort | 110 | 21 | 31 | 79 | 18 | 13 | 40 | 7 | 16 | 51 | 130 | 69 | 80 | 54 | 38 | 19 | 136 | 40 | 46 | 45
Comitted Releasable Dev Tasks | 170 | 174 | 184 | 164 | 168 | 166 | 183 | 92 | 125 | 189 | 183 | 159 | 178 | 183 | 129 | 99 | 186 | 177 | 118 | 112
Sprint Goal | Launching the first 4 templates with renewed design to the library! | Launching all template facelifting tasks in the sprint! | Finalizing all template facelifting tasks in the sprint | Enhanced template related issues will be resolved! Web SDK related issue will be resolved! | AWS tarafındaki structure’ın oluşturulması 3dilim'de social proof template'ını mobile template Store & AB'de görünmesi. | Enhanced Templates: Step function flow ile web ve mobile tarafında farklı statuslere sahip kampanyaların tespiti | Cron Job'ın Slack'e notification gönderiyor olması | Launching 5 new responsive templates to web and app templates | Finalizing the Ready-Made templates Establishing development readiness for Web SDK Integration Wizard | Web SDK Wizard yeni yapı 3dilim partnerinde görünür olması (backend çalışmayacak) | Web sdk wizard'ın tamuat (ve 3dilim) test partner(ler)inde live test yapılmaya hazır olması | Web SDK wizard'ın tamuat accountında "confirmation page" (son sayfa) hariç tamamen çalışıyor olması | Web SDK wizard tamuat partnerinde canlıda olması Test&preview developmentına hazır olunması | - App'te testing fonksiyonlarının approve'unun plan day'e kadar verilmesi - Currency api'in mobile team kullanımına hazır olması | Test&preview is ready for partner launch on scalability side Items for web&app consistency kr grooming and kr grooming done | - Enabling web sdk wizard for all new partners without any issue preventing usage - Adding the needed parameters for lead_collected | - SDK easy enablement will be provided - Partner tasks will be completed | - set as attribute task will be moved to done - dropdown tasks will be moved to done | - Tech Designin 2 aşamasından ilki (3 task) bitecek ve initial development belirlenecek. | - Completing the Part 2 of Domain Whitelist tech design and 2 initial development tasks.
Goal Achieved (0/1) | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 60.87% | 101.6% | 85.71% | 81.92% | 96.69% | 98.4% | 93.99% | 96.91% | 97.32% | 76.77% | 62.3% | 80.84% | 70.65% | 83.67% | 105% | 85.96% | 53.27% | 85.05% | 87.19% | 94.87% | 0% | 0% | 0% | 0% | 0% | 0%
Bug/Development Ratio | 7.477% | 17.89% | 29.63% | 34.09% | 48.77% | 20.86% | 24.42% | 9.574% | 28.57% | 23.68% | 21.62% | 38.52% | 33.33% | 19.61% | 56.52% | 27.06% | 57.14% | 15.58% | 47.54% | 40% | 0% | 0% | 0% | 0% | 0% | 0%
Shipping Accuracy | 19.63% | 27.89% | 35.19% | 41.67% | 35.19% | 74.85% | 58.72% | 18.09% | 50% | 36.18% | 39.64% | 40.74% | 49.61% | 50.33% | 65.94% | 57.65% | 62.24% | 35.71% | 32.79% | 16.8% | 0% | 0% | 0% | 0% | 0% | 0%
Partner Focus | 92.39% | 93.05% | 97.35% | 92.66% | 92.82% | 88.77% | 100% | 94.85% | 83.89% | 95.45% | 95.81% | 95.21% | 88.56% | 93.37% | 72.07% | 86.84% | 93.47% | 91.24% | 58.13% | 57.44% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Bug Ratio | 4.348% | 18.18% | 25.4% | 25.42% | 43.65% | 18.18% | 22.95% | 9.278% | 24.16% | 18.18% | 12.57% | 31.14% | 21.39% | 15.31% | 43.58% | 20.18% | 28.14% | 12.37% | 28.57% | 25.64% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 34% | 39.57% | 51% | 34% | 31% | 41% | 35% | 64.95% | 39.6% | 43.43% | 38.74% | 31.73% | 18.5% | 47% | 50% | 35% | 33% | 39% | 30% | 22% | 0% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 100% | 85% | 30% | 100% | 100% | 30% | 30% | 100% | 85% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [13 empty] | 30% | 100% | 100% | 30% | 30% | 100%
[Tech tasks] committed ¦ Unit Tests |  |  |  |  | . | [8 empty] | 8 | 11 | 8 | 21 | 21 | 8 | 5 | 15
[Tech tasks] done ¦ Unit Tests | [13 empty] | 0 | 11 | 8 | 0 | 13 | 8 | 0
[Tech tasks] committed ¦ Security | [13 empty] | 0 | 7 | 3 | 13 | 18 | 17 | 6 | 5
[Tech tasks] done ¦ Security | [13 empty] | 0 | 2 | 3 | 0 | 18 | 0 | 3
[Tech tasks] committed ¦ Tech Debts | [13 empty] | 18 | 13 | 8 | 16 | 13 | 13 | 34 | 0
[Tech tasks] done ¦ Tech Debts | [13 empty] | 0 | 0 | 8 | 3 | 0 | 13 | 34
[Tech tasks] committed ¦ UX Impr | [20 empty] | 19
[Tech tasks] done ¦ UX Impr
Retro Link | [12 empty] | Retro | Retro | Retro | Retro | Retro | Retro | Retro | Retro
Individual Committed Effort
Ahmet Aslan | 34 | 46 | 47 | 39 | 18 | 44 | 42 | 31 | 32 | 46 | 46 | 45 | 42
Aziza Kasenova | [13 empty] | 52 | 33 | 29 | 32 | 34 | 46 | 42 | 11
Yasin Can Tarlan | 54 | 52 | 47 | 50 | 59 | 52 | 50 | 29 | 46 | 58 | 47 | 51 | 68 | 53 | 54 | 20 | 56 | 55 | 46 | 48 | 51
Tugay İlik | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ugurcan Ertek | 45 | 50 | 53 | 52 | 58 | 53 | 50 | 19 | 37 | 51 | 55 | 47 | 47 | 50 | 50 | 20 | 53 | 46 | 52 | 50 | 50
Mert Adatepe | 40 | 39 | 42 | 38 | 46 | 40 | 41 | 18 | 34 | 43 | 43 | 24 | 44 | 41 | 39 | 33 | 43 | 42 | 42 | 38 | 33
Bilge Bavlı | [14 empty] | 3 | 12 | 15 | 17 | 17 | 17 | 20
Mert Sefa Yüksel | [8 empty] | 8 | 3 | 8 | 10 | 15 | 11 | 0 | 13 | 5 | 16 | 20 | 19 | 16
İsmail Kaya | [8 empty] | 6 | 6 | 8 | 3
Oktay Yedibela | [8 empty] | 4 | 7 | 8 | 3 | 5
Merve Sen | [12 empty] | 0 | 0
Kübra Durmez | [13 empty] | 0 | 13 | 10 | 10 | 12 | 9 | 13 | 15
Mert Kaplan | [19 empty] | 20 | 19
Individual Done Effort
Ahmet Aslan | 21 | 35 | 29 | 39 | 13 | 42 | 52 | 23 | 35 | 35 | 30 | 39 | 27
Aziza Kasenova | [13 empty] | 47 | 31 | 32 | 27 | 39 | 40 | 45
Yasin Can Tarlan | 50 | 50 | 51 | 50 | 58 | 54 | 50 | 29 | 47 | 58 | 48 | 34 | 35 | 27 | 56 | 20 | 4 | 50 | 41 | 55
Tugay İlik | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Ugurcan Ertek | 29 | 66 | 53 | 32 | 64 | 53 | 47 | 19 | 32 | 17 | 26 | 34 | 46 | 50 | 53 | 5 | 37 | 33 | 46 | 50
Mert Adatepe | 8 | 39 | 29 | 24 | 36 | 35 | 23 | 23 | 31 | 42 | 15 | 28 | 34 | 42 | 42 | 28 | 23 | 34 | 30 | 15
Bilge Bavlı | [14 empty] | 6 | 12 | 15 | 17 | 20 | 20
Mert Sefa Yüksel | [8 empty] | 0 | 0 | 8 | 0 | 5 | 6 | 3 | 8 | 0 | 6 | 8 | 7
İsmail Kaya | [8 empty] | 0 | 0 | 0 | 0
Oktay Yedibela | [8 empty] | 0 | 13 | 6 | 0 | 0
Merve Sen | [12 empty] | 0
Kübra Durmez | [13 empty] | 3 | 3 | 3 | 5 | 12 | 0 | 6
Mert Kaplan | [19 empty] | 17
Individual Done Effort - %
Sprint Goal KR Focused Effort
Note on A18: Releasable Done Tasks -Ugurcan Ertek
Note on A19: All done dev tasks -Ugurcan Ertek
Note on A20: Status is "released on prod" or "done" tasks -Ugurcan Ertek
Note on A21: Diff between total effort and dev done tasks -Ugurcan Ertek
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A33: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on B24: 3 out of 5 tasks are done -Didem Akgun
Note on B33: out of 4, %75 -Didem Akgun
Note on C27: - QA eksikliği, yetiştiremedik, aslında sprint güzel gitti. -Tugay İlik
Note on E27: deployment iptal olduğu için kalan tasklar oldu -Didem Akgun
Note on I27: affected by deployment freeze on 16.04 -Didem Akgun
Note on O23: Test&preview awaiting release'e geldi ancak approve verilemedi -Ugurcan Ertek
Note on O33: 3 -Aziza Kasenova
Note on O36: https://winsider.atlassian.net/browse/SD-104547 -Ugurcan Ertek
Note on O40: https://winsider.atlassian.net/browse/SD-104939 https://winsider.atlassian.net/browse/SD-103481 -Ugurcan Ertek
Note on P23: Grooming yapılacaktı ancak postpone edildi -Ugurcan Ertek
Note on P26: Bug'lara ağırlık verilen bir sprint oldu -Ugurcan Ertek
Note on P33: 3 -Ugurcan Ertek
Note on R23: Dropdown task zamanında bitirelemedi -Ugurcan Ertek
Note on S23: - Attribute task is rejected - Cant finalized dropdown modal -Ugurcan Ertek
Note on U27: deployment cancelled 3 days in a row -Didem Akgun
Note on U47: 42 -Ugurcan Ertek

## Scale-up
Scale-Up
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | [13 empty] | 04/07/2024-08/07/2024 | 08/07/2024-31/07/2024 | 31/07/2024-15/08/2024 | 15/08/2024-28/08/2024 | 28/08/2024-11/09/2024 | 11/09/2024-25/09/2024 | 25/09/2024-09/10/2024
Sprint Name | [13 empty] | [2024][Q3] #1 | [2024][Q3] #2 | [2024][Q3] #3 | [2024][Q3] #4 | [2024][Q3] #5 | [2024][Q3] #6 | [2024][Q4] #1
Total Effort In the Sprint | [13 empty] | 126 | 108 | 81 | 132 | 125 | 145 | 147
Commited | [13 empty] | 116 | 108 | 78 | 115 | 103 | 119 | 113
Emerged | [13 empty] | 10 | 0 | 3 | 17 | 22 | 26 | 34
Emerged Rate | 0% | [12 empty] | 7.94% | 0% | 4% | 12% | 12% | 18% | 23%
Done Bug Effort | [13 empty] | 8 | 3 | 0 | 2 | 9 | 9 | 39
Commited Bug Effort | [13 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 17
Emerged Bug Effort | [13 empty] | 10 | 0 | 0 | 2 | 9 | 12 | 30
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | [13 empty] | 40 | 77 | 39 | 106 | 39 | 119 | 84
All Tasks Done Effort | [13 empty] | 103 | 108 | 54 | 106 | 39 | 119 | 84
Released Effort | [13 empty] | 35 | 50 | 34 | 64 | 10 | 34 | 7
Undone PBI Effort | [13 empty] | 26 | 29 | 26 | 18 | 64 | 26
Comitted Releasable Dev Tasks | [13 empty] | 40 | 77 | 49 | 102 | 103 | 119 | 50
Sprint Goal | [13 empty] | Finalizing the Tech Analysis of the first KRs | Being able to 3rd page to the Lead Collection Onpage - Finalizing the Carrier Service development | Completing the necessary actions required for 3-Page templates - Completing the Dropdown components | Finalizing the panel design of Data Match rule | - Finalizing the development of Data Match Rule ❌ - Completing the 3-Page Lead Collection tasks ❌ | - Completing the development of List Checker - Being ready to launch the 3 Page Onpage Lead Collection template | - Finalizing the Partner Check P.1 for Insider Extension ✅︎ - Enabling the 3-Page Onpage Lead Collection for Partners ❌
Goal Achieved (0/1) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 0% | [12 empty] | 88.79% | 100% | 69.23% | 92.17% | 37.86% | 100% | 74.34%
Bug/Development Ratio | 0% | [12 empty] | 20% | 3.896% | 0% | 1.887% | 23.08% | 7.563% | 46.43%
Shipping Accuracy | 0% | [12 empty] | 87.5% | 64.94% | 87.18% | 60.38% | 25.64% | 28.57% | 8.333% | 0% | 0% | 0%
Partner Focus | [13 empty] | 34.48% | 71.3% | 62.82% | 88.7% | 100% | 100% | 44.25%
Bug Ratio | [13 empty] | 6.897% | 2.778% | 0% | 1.739% | 8.738% | 7.563% | 34.51%
Bug Score
Sprint Goal KR Effort (%) | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Sprint Goal Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 54% | 44.44% | 60% | 68.7% | 90.29% | 77% | 35% | 37% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 30% | 30% | 30% | 100% | 15% | 30% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [13 empty] | 100% | 100% | 30% | 30% | 30% | 100%
Individual Committed Effort
Ahmet Aslan | [13 empty] | 45 | 39 | 8 | 39 | 44 | 45 | 43 | 46
Şahin Deniz | [13 empty] | 52 | 48 | 44 | 47 | 37 | 48 | 40 | 44
Arda Berrun Karaca | [13 empty] | 19 | 21 | 26 | 29 | 22 | 26 | 30 | 35
Eda Taşyürek | [13 empty] | 5 | 8 |  | 5 | 10 | 9 | 10 | 10
Oktay Yedibela | [13 empty] | 13 | 8 |  | 13 | 13 | 11 | 16 | 16
Beyza Ozbek | [13 empty] | 47 | 50 |  | 52 | 50 | 58 | 52 | 55
Individual Done Effort
Ahmet Aslan | [13 empty] | 32 | 39 | 8 | 34 | 0 | 34 | 45
Şahin Deniz | [13 empty] | 52 | 48 | 18 | 49 | 8 | 48 | 50
Arda Berrun Karaca | [13 empty] | 19 | 21 | 28 | 23 | 31 | 37 | 21
Eda Taşyürek | [13 empty] | 5 | 5 | 4 | 3 | 5 | 11 | 10
Oktay Yedibela | [13 empty] | 13 | 3 | 0 | 0 | 13 | 14 | 11
Beyza Ozbek | [13 empty] | 47 | 13 | 26 | 31 | 29 | 58 | 39
Sprint Goal KR Focused Effort
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A33: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on O33: 3/3 -Didem Akgun
Note on P33: 2/3 -Didem Akgun
Note on Q33: 3/3 -Didem Akgun
Note on R33: 3/3 -Didem Akgun
Note on S33: 3/3 -Didem Akgun
Note on T27: deployment canceled 3 times during the sprint -Didem Akgun
Note on T33: 3/3 -Didem Akgun
Note on U27: sprintin son 2 günü deployment cancel oldu -Didem Akgun + otomasyonda tasklar çok uzun bekledi -Didem Akgun
Note on U33: 1/3 -Didem Akgun
Note on V33: 2/3 -Didem Akgun

## Contech
Contech
Quarter | Q1 | [5 empty] | Q2 | [5 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 28.12.2023 | 11.01.2024 | 25.01.2024 | 09.02.2024 | 22.02.2024 | 07.03.2024 | 21.03.2024 | 4.04.2024 | 25.04 - 16.05 | 16.05 - 30.05 | 31.05 - 14.06 | 14.06 - 05.07 | 05.07-18.07 | 18.07-01.08 | 01.08-22.08 | 22.08-05.09 | 05.09-19.09 | 19.09-03.10 | 03.10-17.10
Sprint Name | 🐉 Charizard #1 | Better Call Sezer #2 2024 | Talk like a Godfather #3 | Long Planning Sprint #4 | Hyperkube #5 | Full Automation #6 | Electricty Off - Q2 24 | Eid Mubarak #2 | Creative Name #3 | Amelia #4 | Contech Sprint #5 | Rest and Fail #6 | Aperol Sprint #1 | Edward Scissorhands #2 | Welcome Reza Abi #3 | Coming Like Ateş #4 | Prison Break #5 | QA Story Pointsss #6 | The Matrix Q4S1
Total Effort In the Sprint | 215 | 280 | 295 | 282 | 272 | 313 | 277 | 325 | 330 | 318 | 252 | 307 | 263 | 285 | 289 | 272 | 259 | 233 | 243
Commited | 197 | 242 | 269 | 253 | 240 | 257 | 225 | 294 | 234 | 271 | 228 | 268 | 226 | 259 | 271 | 227 | 197 | 201 | 208
Emerged | 13 | 38 | 26 | 29 | 32 | 60 | 52 | 47 | 107 | 47 | 24 | 31 | 37 | 28 | 38 | 34 | 41 | 38 | 13
Emerged Rate | 6.047% | 13.57% | 8.814% | 10.28% | 11.76% | 19.17% | 18.77% | 14.46% | 32.42% | 14.78% | 9.524% | 10.1% | 14.07% | 9.825% | 13.15% | 12.5% | 15.83% | 16.31% | 5.35%
Done Bug Effort | 57 | 53 | 41 | 51 | 85 | 82 | 54 | 89 | 60 | 88 | 46 | 83 | 69 | 67 | 30 | 48 | 55 | 83 | 64
Commited Bug Effort | 61 | 28 | 38 | 59 | 61 | 58 | 66 | 61 | 25 | 79 | 55 | 51 | 61 | 68 | 46 | 31 | 38 | 82 | 60
Emerged Bug Effort | 6 | 25 | 15 | 22 | 24 | 33 | 9 | 28 | 40 | 22 | 6 | 29 | 8 | 8 | 8 | 22 | 30 | 33 | 11
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 135 | 142 | 177 | 138 | 192 | 215 | 166 | 221 | 207 | 196 | 148 | 172 | 150 | 151 | 150 | 121 | 147 | 163 | 128
All Tasks Done Effort | 160 | 161 | 205 | 148 | 218 | 233 | 193 | 249 | 224 | 212 | 152 | 172 | 169 | 185 | 179 | 172 | 168 | 174 | 134
Released Effort | 62 | 134 | 82 | 65 | 163 | 178 | 124 | 153 | 190 | 140 | 131 | 122 | 95 | 125 | 89 | 83 | 123 | 126 | 66
Undone PBI Effort | [12 empty] | 94 | 100 | 127 | 87 | 67 | 72 | 74
Comitted Releasable Dev Tasks | 151 | 211 | 240 | 217 | 212 | 213 | 195 | 238 | 209 | 242 | 201 | 236 | 195 | 214 | 231 | 180 | 134 | 196 | 170
Sprint Goal | Refactoring the Unsubscribe Publisher | (CAU) API Coverages ¦ WhatsApp & SMS | Data Master onboarding Event Pause/Resume and Minor Coverages Data Master QA Camp Beta Partner release | Email Based Subscription Flow Gachapon Settings WA & SMS To Work with Suppression DB by default | (Unsubscribe API Case) (Contact Service) Profile Based Subscription Flow (Resubscribe API) (Contact Service) Profile Based Subscription Flow Bulk Upload - (Panel Coverages) Profile Based Subscription Flow (Panel Coverages) Profile Based Subscription Flow (QA Check) Lead collection campaigns coverage | Toggle Task - Skywalker ¦ Sidebar Redesign Project V2 Task - Skywalker Sidebar Redesign Project Search - Skywalker ¦ Sidebar Redesign Project Tech Design For Caching Mechanism ¦ SideBar | Audience Analytics - Message Frequency Dropdown Audience Analytics - MVP Development Part 3.4 implementation of filter for the green boxes Audience Analytics - MVP Development Part 3.3 - BE (Plugging Remaining Endpoint) Audience Analytics - MVP Development Part 3.2 - FE (Applying Segmentation to queries) | SD-104061 BE - Editing Dynamic Segments KR SD-101461 FE - Editing Dynamic Segments KR SD-101710 Audience Analytics MVP 2.0 Tech Design for Data Cache (MVP 2.0) KR SD-103914 Audience Analytics - Message Freq Dropdown Iteration KR SD-103088 Data Master ¦ Monitoring Results KR | SD-104863 Editing Dynamic Segments Improvements KR ✅︎ SD-104839 Fixed 3 duplicated requests to DB in Data master page KR ✅︎ SD-104575 Tech Design saved segment and segment exclusion KR ✅︎ SD-104065 Edit Segments Beta Partner Release KR ✅︎ SD-105340 BE - Segment Exclusion ¦ Create exclude Saved Segment Block KR ❌ SD-105329 FE - Segment Exclusion ¦ Create exclude Saved Segment Block KR ❌ | SD-105329 FE - Segment Exclusion ¦ Create exclude Saved Segment Block KR ✅︎ SD-105340 BE - Segment Exclusion ¦ Create exclude Saved Segment Block KR ✅︎ SD-105240 Datamaster - Minor UX Improvement - Data sample addition, notes UX improvement KR ✅︎ SD-105652 Data Master Grand Release KR ✅︎ SD-105620 Edit Segments Grand Release KR ✅︎ SD-105657 (Phase 1) Attribute Value Comparisons KR ✅︎ | SD-105781 FE - (Phase 1) Expression/Attribute Value Comparisons ¦ Contech KR ✅︎ SD-106375 BE - (Phase 1) Expression/Attribute Value Comparisons ¦ Contech KR ✅︎ SD-106516 HB Release (Phase 1) Expression/Attribute Value Comparisons ¦ Contech KR ✅︎ SD-106173 Open Segment Exclusion for Vogacloset KR ✅︎ SD-106416 BE - Dynamic Segment as a Filter KR 🟩 SD-106361 FE - Dynamic Segment as a Filter KR ❌ SD-106517 HB Release - Dynamic Segment as a Filter KR ❌ | SD-107020 (Segmentation Package) ( Create Page ) Expressions KR ❌ SD-107022 FE - (InOne) ( Create Page ) Expressions KR ❌ SD-106281 BE - (InOne) ( Create Page ) Expressions KR ✅︎ SD-106386 FE - (MVP) Listing Page - Expressions KR ✅︎ SD-107021 BE - (MVP) Listing Page - Expressions KR ✅︎ SD-106361 FE - Dynamic Segment as a Filter KR ✅︎ | SD-107790 - Dynamic Segments ✅︎ SD-107022 - Expressions ✅︎ SD-107020 - Expressions ❌ SD-106228 - New Subscriptions Flow KR❌ SD-106227 - New Subscriptions Flow KR✅︎ SD-106226 - New Subscriptions Flow KR❌ SD-105670 - New Subscriptions Flow KR✅︎ SD-107459 - New Subscriptions Flow✅︎ | SD-108207 - Auidence Analytics ❌ SD-104837 - Audience Analytics ❌ SD-108202 - Audience Analytics ✅︎ SD-108201 - Audience Analytics ✅︎ SD-106228 - New Subscriptions Flow ✅︎ SD-106226 - New Subscriptions Flow KR✅︎ | SD-108833- Auidence Analytics ❌ SD-108699- Audience Analytics ✅︎ SD-108278 - Audience Analytics ✅︎ SD-108207 - Audience Analytics ✅︎ SD-104837 - Audience Analytics ✅︎ SD-108013 - Expressions ✅︎ SD-108182 - Expressions ❌ SD-108703 - Expressions ✅︎ SD-108808 - Expressions ✅︎ SD-108829 - Expressions ❌ | SD-109437- Auidence Analytics ✅︎ (ready for release) SD-109386 - Audience Analytics ✅︎ SD-109372 - Audience Analytics ✅︎ SD-108833 - Audience Analytics ✅︎ | Completing all the post incident and bugs | Moving 2 KRs to Monitoring (Audience Analytics & Expressions) Doing all necessary actions for Profile-based Subs Finishing all bugs | Speed Improvement Tasks to be deployed
Goal Achieved (0/1) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 81.22% | 66.53% | 76.21% | 58.5% | 90.83% | 90.66% | 85.78% | 84.69% | 95.73% | 78.23% | 66.67% | 64.18% | 74.78% | 71.43% | 66.05% | 75.77% | 85.28% | 86.57% | 64.42% | 0% | 0% | 0% | 0% | 0% | 0%
Bug/Development Ratio | 42.22% | 37.32% | 23.16% | 36.96% | 44.27% | 38.14% | 32.53% | 40.27% | 28.99% | 44.9% | 31.08% | 48.26% | 46% | 44.37% | 20% | 39.67% | 37.41% | 50.92% | 50% | 0% | 0% | 0% | 0% | 0% | 0%
Shipping Accuracy | 45.93% | 94.37% | 46.33% | 47.1% | 84.9% | 82.79% | 74.7% | 69.23% | 91.79% | 71.43% | 88.51% | 70.93% | 63.33% | 82.78% | 59.33% | 68.6% | 83.67% | 77.3% | 51.56% | 0% | 0% | 0% | 0% | 0% | 0%
Partner Focus | 76.65% | 87.19% | 89.22% | 85.77% | 88.33% | 82.88% | 86.67% | 80.95% | 89.32% | 89.3% | 88.16% | 88.06% | 86.28% | 82.63% | 85.24% | 79.3% | 68.02% | 97.51% | 81.73% | 0% | 0% | 0% | 0% | 0% | 0%
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 26% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 10.66% | 8.678% | 16.36% | 17.39% | 30% | 26.46% | 23.11% | 27.55% | 30% | 16.97% | 27.63% | 27.24% | 33.63% | 30.12% | 30% | 9% | 37% | 50% | 16% | 26% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 100% | 100% | 100% | 85% | 100% | 85% | 85% | 85% | 30% | 85% | 15% | 15% | 30% | 30% | 30% | 85% | 100% | 100% | 70% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [12 empty] | 30% | 30% | 30% | 0% | 100% | 100%
Individual Committed Effort
Reza | [14 empty] | 32 | 40 | 37 | 41 | 35 | 45
Abdulrhman Al-mahaini | 41 | 45 | 47 | 34 | 30 | 36 | 47 | 50 | 46 | 48 | 41 | 46 | 15 | 29 | 51 | 49 | 32 | 37 | 35 | 38
Laith Atik | 38 | 37 | 44 | 39 | 40 | 49 | 47 | 50 | 42 | 50 | 44 | 50 | 44 | 42 | 18 | 36 | 36 | 39 | 35 | 34
Oleksandr Serhieiev | 15 | 47 | 45 | 41 | 49 | 50 | 51 | 59 | 41 | 51 | 45 | 46 | 46 | 50 | 47 | 36 | 36 | 38 | 35 | 34
Deniz Parlar | [17 empty] | 13 | 13 | 16
Sezer Güven | - | 23 | 32 | 39 | 39 | 39 | 35 | 52 | 41 | 43 | 21 | 49 | 41 | 50 | 46 | -
Kenan Asadov | 39 | 39 | 40 | 39 | 42 | 46 | 15 | 48 | 39 | 50 | 50 | 45 | 49 | 46 | 50 | 32 | 32 | 5 | 35 | 37
Sefa Alp | - | 20 | 27 | 25 | 9 | 6 | -
Ridvan Berkay Cetin | 31
Evgeny | 8 | 6 | 8 | 8 | 8 | 8 | 8 | 11 | 5 | 3 | 8 | 8 | 8 | 9 | 11 | 11 | 0 | 6 | 5 | 0
Hossin | 16 | 15 | 18 | 20 | 14 | 15 | 14 | 16 | 12 | 21 | 11 | 16 | 13 | 21 | 15 | 13 | 13 | 14 | 10 | 8
Yevheniia | 9 | 10 | 8 | 8 | 9 | 8 | 8 | 8 | 8 | 5 | 5 | 8 | 10 | 10 | 12 | 10 | 11 | 8 | 5 | 7
Individual Done Effort
Reza | [14 empty] | 16 | 45 | 66 | 41 | 36
Abdulrhman Al-mahaini | 38 | 34 | 36 | 26 | 36 | 47 | 48 | 42 | 29 | 31 | 44 | 40 | 17 | 34 | 50 | 49 | 15 | 27 | 29
Laith Atik | 33 | 13 | 21 | 17 | 44 | 46 | 47 | 41 | 54 | 36 | 47 | 48 | 25 | 29 | 10 | 20 | 19 | 46 | 22
Oleksandr Serhieiev | 15 | 23 | 32 | 25 | 36 | 42 | 31 | 57 | 51 | 40 | 16 | 37 | 46 | 47 | 11 | 24 | 34 | 36 | 7
Ridvan Berkay Cetin | 31
Deniz Parlar | [17 empty] | 13 | 0
Kenan Asadov | 18 | 31 | 46 | 42 | 42 | 51 | 12 | 43 | 51 | 44 | 39 | 35 | 37 | 25 | 33 | 25 | 31 | 0 | 34
Sefa Alp | - | 12 | 10 | 0 | 6 | 3
Sezer Güven | - | 29 | 27 | 28 | 28 | 26 | 28 | 38 | 22 | 45 | 2 | 12 | 25 | 16 | 40
Evgeny | 8 | 3 | 10 | 8 | 8 | 2 | 8 | 8 | 2 | 0 | 0 | 0 | 8 | 9 | 8 | 0 | 0 | 0 | 0
Hossin | 8 | 8 | 15 | 0 | 10 | 12 | 11 | 12 | 10 | 16 | 0 | 0 | 0 | 14 | 0 | 5 | 0 | 5 | 3
Yevheniia | 9 | 8 | 8 | 2 | 8 | 4 | 8 | 8 | 8 | 0 | 4 | 0 | 11 | 11 | 11 | 4 | 3 | 6 | 3
Sprint Goal KR Focused Effort
Done Average |  | 142 | 172 | 138 | 192 | 215 | 166 | 221 | 207 | 196 | 148 | 172 | 150 | 151 | 160
QA Average |  | 19 | 33 | 10 | 26 | 18 | 27 | 28 | 20 | 16 | 4 | 0 | 19 | 34 | 19
Done Average (wout kenan) and reza is avg 35 SP | [6 empty] | 161 | 175 | 169 | 142 | 142 | 160 | 123 | 145 | 106
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on B20: 37 sp in Awaiting Release
Note on B32: apo
Note on B39: on vacation
Note on B43: on vacation
Note on C32: apo
Note on D20: 123 SP in Ready For Release
Note on D27: 123 SP in Ready For Release
Note on D32: laith hossin oleksandr sezer
Note on E20: 71 SP in in Ready For Release
Note on E32: apo laith oleks
Note on F20: 55 SP in in Ready For Release
Note on F32: kenan sezer oleks laith evgeny
Note on G20: 55 story points in Ready For Release
Note on G31: omer abi will make some communication about this ratio
Note on G32: apo kenan oleks laith
Note on G41: 1 days leave
Note on H20: 69 story points in Ready For Release
Note on H32: laith oleks sezer
Note on H41: 2 days leave
Note on I20: 68 story points in Ready For Release
Note on I22: 35 SP QA task 21 SP Research task
Note on I32: apo laith kenan oleks sezer
Note on J20: 34 SP in Ready For Release
Note on J32: laith apo kenan sezer
Note on K20: 72 SP in Ready For Release
Note on K32: laith apo sezer oleks kenan
Note on L20: 20 SP in Ready For Release
Note on L32: all the team
Note on M20: 50 SP in Ready For Release
Note on M32: kenan oleks sezer
Note on N32: olek kenan sezer laith
Note on O20: 23 SP Ready for Release, 3 SP Awaiting Release -Didem Akgun
Note on O32: sezer, oleks, apo, laith, kenan -Didem Akgun
Note on P20: 25 ready for, 28 awaiting release -Didem Akgun
Note on P32: apo, sezer, kenan -Didem Akgun
Note on P38: Vacationing
Note on Q20: 26 AR, 12 RFR -Didem Akgun
Note on Q32: laith, oleks, kenan -Didem Akgun
Note on R23: due to low QA capacity (1 QA was off whole sprint) & amount of incident and bug tasks -Didem Akgun
Note on R32: apo,laith,kenan,reza,oleks -Didem Akgun
Note on S32: all devs. -Didem Akgun
Note on T20: deployment cancelled 5 days during the sprint -Didem Akgun
Note on T32: reza, laith -Didem Akgun

## Myhtbusters
Mythbusters
Quarter | Q1 | [5 empty] | Q2 | [5 empty] | Q3 | [5 empty] | Q4 | [6 empty] | AVERAGE SP | TOTAL SP
Month | Jan |  | Feb |  | March |  | April |  | May |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 05/01/2024 -19/01/2024 | 19/01/2024 - 02/02/2024 | 02/02/2024 - 16/02/2024 | 16/02/2024 - 01/03/2024 | 01/03/2024 - 15/03/2024 | 15/03/2024 - 29/03/2023 | 29/03/2024 - 19/03/2024 | 19/03/2024 - 03/05/2024 | 03/05/2024 - 17/05/2024 | 17/05/2024-31/05/2024 | 31/05/2024-14/06/2024 | 14/06/2024-05/07/2024
Sprint Name | Mythbusters 24#1 | Mythbusters 24#2 | Mythbusters 24#3 | Mythbusters 24#4 | Mythbusters 24#5 | Mythbusters 24#6 | Mythbusters 24#7 | Mythbusters 24#8 | Mythbusters 24#9 | Mythbusters 24#10 | Mythbusters 24#11 | Mythbusters 24#12 | Mythbusters 24#13 | Mythbusters 24#14 | Mythbusters 24#15 | Mythbusters 24#16 | Mythbusters 24#17
Total Effort In the Sprint | 294 | 306 | 267 | 279 | 234 | 278 | 291 | 244 | 256 | 168 | 218 | 261 |  | 211 | 346 | 227 | 203 | 258
Commited | 262 | 230 | 244 | 218 | 202 | 232 | 264 | 208 | 200 | 141 | 174 | 224 |  | 190 | 252 | 163 | 171 | 203 | 172
Emerged | 22 | 30 | 22 | 22 | 32 | 46 | 48 | 44 | 34 | 23 | 44 | 49 |  | 24 | 68 | 56 | 32 | 44
Emerged Rate | 7.483% | 9.804% | 8.24% | 7.885% | 13.68% | 16.55% | 16.49% | 18.03% | 13.28% | 13.69% | 20.18% | 18.77% | 0% | 11.37% | 19.65% | 24.67% | 15.76% | 17.05%
Done Bug Effort | 59 | 33 | 27 | 38 | 36 | 24 | 69 | 36 | 58 | 51 | 24 | 61 |  | 19 | 53 | 44 | 58 | 44
Commited Bug Effort | 70 | 46 | 55 | 44 | 34 | 29 | 49 | 47 | 45 | 46 | 24 | 54 |  | 44 | 44 | 48 | 38 | 40
Emerged Bug Effort | 0 | 1 | 0 | 2 | 2 | 25 | 15 | 11 | 29 | 5 | 8 | 37 |  | 16 | 26 | 8 | 19 | 28
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 193 | 181 | 184 | 211 | 154 | 145 | 175 | 93 | 154 | 109 | 103 | 122 |  | 44 | 161 | 114 | 141 | 106 | 87
All Tasks Done Effort | 204 | 193 | 194 | 244 | 187 | 146 | 177 | 98 | 196 | 128 | 103 | 142 |  | 60 | 182 | 132 | 170 | 127 | 111
Released Effort | 99 | 100 | 147 | 157 | 123 | 74 | 82 | 85 | 111 | 86 | 60 | 84 |  | 34 | 95 | 65 | 101 | 66 | 29
Undone PBI Effort | 86 | 76 | 73 | 34 | 51 | 143 | 127 | 157 | 61 | 40 | 89 | 135 |  | 135 | 133 | 90 | 27 | 115 | 82
Comitted Releasable Dev Tasks | 244 | 211 | 238 | 202 | 188 | 227 | 259 | 190 | 176 | 141 | 167 | 211 |  | 176 | 233 | 157 | 126 | 148 | 114
Sprint Goal | 1. Enigma API transition tasks to be Ready for Release (SD-99617, SD-99618) 2. Analytics Consistency tasks to be AR (SD-98486, SD-89382, SD-89380, SD-98483, SD-98485). | 1. Enigma API KR to be released on PROD and ready for UAT camp (SD-99715, SD-100216); 2. Template library to be AR (SD-99004, SD-100391, SD-98725, SD-99003) | 1. Template Library (SD-100810 Released, SD-98727, SD-100813, SD-98662, SD-100966 Awaiting Release) | Template Library is working on production and user is able to create/edit templates in HTML editor (SD-100811, SD-101206, SD-99005, SD-101205, SD-101210, SD-101409, SD-101468). | 1. Template Library - PM can edit template in HTML editor and use this custom template in the campaign (MVP scope to be done); 2. Enigma API - Mythbusters part of KR blockers to be released on PROD. Template Library: SD-102258 SD-102046 SD-102093 SD-102098 SD-102335 SD-102335 SD-101210 SD-102244 Enigma API blocker: SD-101454 SD-101453 | 1. Template Library: MVP scope done and available for UAT camp (SD-101210 Released; SD-103146, SD-102723, SD-102725, SD-102498, SD-101454). | 1. Template Library: Be able to store all possible Stripo template configs (recommendation, unsubscribe) ✅ 2. Create an endpoint to collect the mobile revenue from UCD create endpoint. ❌ | 1. Template Library Complete Stripo and get ready for migration❌ 2. Conversion from app to be live ❌ | 1. Template Library Complete Stripo and get ready for migration❌ 2. Conversion from app to be live ❌ | Email Template Library is ready for Beta (release all beta blockers) ✅ | ETL blockers and improvements to be released and feature opened for beta partners.✅ | 1. Open template library for 2nd batch of beta partners and resolve any blockers for the feature usage if any. ✅ (used a work around instead) 2. Resolving dependency on DS -- Micro-frontend tasks are awaiting release. ❌ |  | 1. Migration of Email and Architect templates for ETL (batch 1-4) to be completed ❌ 2. ETL related tasks to be released ❌ | 1. Release ETL tasks and get ready for all partners migration (SD-108817, SD-108174, SD-106625, SD-106904, SD-106905) ❌; 2. Fix Enigma blockers (SD-105007, SD-104431, SD-108738, SD-108737)✅ . | 1. Get closed to Enigma transition: release tasks on prod (SD-105010, SD-105005, SD-109332, SD-105006, SD-104149, SD-109008) ❌; | 1. Enigma API blockers to be released and QA camp done ✅ ; 2. Mobile App Conversion task to be live.✅ | 1. Finish Enigma blockers, get ready for 1st batch transition ❌
Goal Achieved (0/1) | 100% | 100% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 77.86% | 83.91% | 79.51% | 111.9% | 92.57% | 62.93% | 67.05% | 47.12% | 98% | 90.78% | 59.2% | 63.39% | 0% | 31.58% | 72.22% | 80.98% | 99.42% | 62.56% | 64.53%
Bug/Development Ratio | 30.57% | 18.23% | 14.67% | 18.01% | 23.38% | 16.55% | 39.43% | 38.71% | 37.66% | 46.79% | 23.3% | 50% | 0% | 43.18% | 32.92% | 38.6% | 41.13% | 41.51% | 0%
Shipping Accuracy | 51.3% | 55.25% | 79.89% | 74.41% | 79.87% | 51.03% | 46.86% | 91.4% | 72.08% | 78.9% | 58.25% | 68.85% | 0% | 77.27% | 59.01% | 57.02% | 71.63% | 62.26% | 33.33%
Partner Focus | 93.13% | 91.74% | 97.54% | 92.66% | 93.07% | 97.84% | 98.11% | 91.35% | 88% | 100% | 95.98% | 94.2% | #DIV/0! | 92.63% | 92.46% | 96.32% | 73.68% | 72.91% | 66.28%
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 17.56% | 46.52% | 30% | 45% | 38% | 22% | 35.98% | 39% | 35% | 41% | 30% | 25% | 0% | 27% | 34.13% | 55% | 36% | 21% | 33% | 0% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 85% | 100% | 100% | 30% | 30% | 85% | 30% | 30% | 30% | 100% | 100% | 0% | 0% | 15% | 30% | 30% | 100% | 15% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [12 empty] | 0% | 15% | 30% | 30% | 100% | 15% | 15%
Individual Committed Effort
Andrew | 38 | 51 | 50 | 50 | 47 | 63 | 75 | 61 | 31 | 8 | 37 | 43 | 23 | 56 |  | 33 | 33 | 0 | 0 | [6 empty] | 38.8333 | 699
Anton | 44 | 38 | [23 empty] | 41 | 82
Doğukan | 49 | 37 | 62 | 53 | 48 | 55 | 52 | 39 | 39 | 42 | 37 | 58 | 37 | 29 |  | 40 | 10 | 40 | 0 | [6 empty] | 40.3889 | 727
Emre | 34 | 39 | 56 | 47 | 45 | 58 | 69 | 53 | 49 | 37 | 28 | 55 | 47 | 23 |  | 30 | 47 | 33 | 42 | [6 empty] | 44 | 792
İrem | 41 | 44 | 70 | 52 | 56 | 56 | 52 | 45 | 38 | 13 | 39 | 32 | 21 | 21 |  | 33 | 39 | 35 | 39 | [6 empty] | 40.3333 | 726
Aslıhan | [9 empty] | 36 | 20 | 23 | 27 | 31 |  | 22 | 25 | 21 | 30 | [6 empty] | 26.1111 | 235
Enes | 8 | 8 | 3 | 10 | 3 | 5 | 5 | 10 | 5 | 0 | 2 | 5 | 8 | 11 |  | 6 | 0 | 21 | 13 | [6 empty] | 6.8333 | 123
Nikita | 12 | 5 |  | 1 | 3 | 0 |  |  | 3 | 0 | 5 | 8 | 15 | 16 |  | 1 | 1 | 0 | 0 | [6 empty] | 4.6667 | 70
Sinem | 39 | 21 | [23 empty] | 30 | 60
Gorkem |  |  |  | 5 | [7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0.625 | 5
Rostyslav | [8 empty] | 8 | 5 |  | 0 | 0 | 0 |  | 0 | 3 | 0 | 0 | [6 empty] | 1.7778 | 16
Vitalii | [16 empty] | 8 | 53 | 48
Individual Done Effort | [25 empty] | 20.1691
Andrew | 35 | 48 | 22 | 77 | 55 | 58 | 67 | 27 | 19 | 21 | 29 | 22 |  | 1 | 41 | 22 | 34 | 0 | 0 | [6 empty] | 32.1111 | 578
Anton | 26 | 12 | [23 empty] | 19 | 38
Doğukan | 20 | 24 | 62 | 47 | 51 | 19 | 8 | 8 | 29 | 13 | 8 | 16 |  | 10 | 47 | 31 | 1 | 1 | 0 | [6 empty] | 21.9444 | 395
Emre | 34 | 47 | 25 | 30 | 8 | 32 | 69 | 24 | 41 | 34 | 30 | 32 |  | 10 | 21 | 25 | 55 | 14 | 29 | [6 empty] | 31.1111 | 560
İrem | 44 | 52 | 75 | 57 | 48 | 35 | 26 | 34 | 44 | 13 | 16 | 37 |  | 8 | 36 | 30 | 31 | 38 | 13 | [6 empty] | 35.3889 | 637
Aslıhan | [8 empty] | 21 | 28 | 20 | 15 |  | 15 | 16 | 19 | 22 | 6 | 22 | [6 empty] | 18.4 | 184
Enes | 3 | 12 | 7 | 25 | 22 | 0 |  | 5 | 28 | 14 | 0 | 14 |  | 3 | 18 | 5 | 8 | 26 | 17 | [6 empty] | 12.1765 | 207
Sinem | 34 | 21 | [23 empty] | 27.5 | 55
Nikita | 8 | 0 | 0 | 8 | 3 | 1 | 1 |  | 3 | 0 | 0 | 6 |  | 13 | 3 | 0 | 6 | 0 | 0 | [6 empty] | 3.0588 | 52
Görkem |  |  | 3 | 0 |  |  |  |  | 8 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 11
Rostyslav | [8 empty] | 3 | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0.8 | 8
Vitalii | [16 empty] | 21 | 42 | 30
Sprint Goal KR Focused Effort
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on B32: 3 out of 6 -Didem Akgun
Note on E23: 1 task remained only, 6 tasks done -Didem Akgun
Note on F23: 8 tasks done - 1 uat - 1 in prog. - MVP Scope = HTML Editor -Didem Akgun
Note on G23: HTML Editor MVP Scope + QA Camp findings were done + enigma task was blocked that is why as a team decision goal is success -Didem Akgun
Note on M32: 2 devs out of 5 -Didem Akgun
Note on R49: 21 knowledge sharing -Irem Ekser
Note on R52: 8 sp rejected -Irem Ekser
Note on R55: qa camp -Irem Ekser
Note on R60: 21 knowledge sharing -Irem Ekser
Note on S14: +13 sp : emerged & removed -Irem Ekser
Note on S42: +8 sp release plan -Irem Ekser
Note on S55: + 8sp release plan -Irem Ekser

## Ghostbusters
Ghostbusters
Quarter | Q1 | [5 empty] | Q2 | [5 empty] | Q3 | [5 empty] | Q4 | [6 empty] | AVERAGE SP | TOTAL SP
Month | Jan |  | Feb |  | March |  | April |  | May |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | [6 empty] | 28.03 - 18.04 | 18.04 - 16.05
Sprint Name | Ghostbusters 24#1 | Ghostbusters 24#2 | Ghostbusters 24#3 | Ghostbusters 24#4 | Ghostbusters 24#5 | Ghostbusters 24#6 | Ghostbusters 24#7 | Ghostbusters 24#8 |  | Ghostbusters 24#10 | Ghostbusters 24#11 | Ghostbusters 24#12 | Ghostbusters 24#13 | Ghostbusters 24#14 | Ghostbusters 24#15 | Ghostbusters 24#16 | Ghostbusters 24#17 | Ghostbusters 24#18 | Ghostbusters 24#19
Total Effort In the Sprint | 218 | 298 | 269 | 315 | 321 | 326 | 407 | 652 | 652 | 375 | 380 | 407 | 276 | 319 | 350 | 221 | 343 | 338 | 266
Commited | 190 | 265 | 223 | 263 | 289 | 292 | 339 | 652 | 652 | 310 | 265 | 322 | 238 | 313 | 264 | 186 | 300 | 265 | 244
Emerged | 28 | 33 | 46 | 52 | 32 | 34 | 68 | 0 | 0 | 65 | 115 | 79 | 11 | 6 | 85 | 29 | 40 | 73 | 45
Emerged Rate | 14.74% | 12.45% | 20.63% | 19.77% | 11.07% | 11.64% | 20.06% | 0% | 0% | 20.97% | 43.4% | 24.53% | 5% | 2% | 24% | 13% | 13.33% | 21% | 17%
Done Bug Effort | 0 | 34 | 53 | 33 | 46 | 55 | 62 | 112 | 112 | 50 | 87 | 117 | 58 | 79 | 60 | 66 | 74 | 98 | 93
Commited Bug Effort |  | 21 | 53 | 11 | 35 | 55 | 39 | 146 | 146 | 76 | 54 | 78 | 58 | 92 | 54 | 76 | 42 | 106 | 77
Emerged Bug Effort |  | 13 | 0 | 22 | 11 | 21 | 28 |  |  | 8 | 41 | 60 | 5 | 6 | 32 | 0 | 34 | 68 | 16
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 97 | 158 | 174 | 191 | 181 | 214 | 295 | 436 | 436 | 210 | 171 | 267 | 157 | 136 | 175 | 146 | 195 | 179 | 185
All Tasks Done Effort | 107 | 177 | 189 | 202 | 228 | 248 | 311 | 461 | 461 | 222 | 187 | 270 | 166 | 137 | 189 | 151 | 198 | 179 | 193
Released Effort | 46 | 76 | 93 | 141 | 136 | 104 | 164 | 396 | 396 | 147 | 89 | 239 | 120 | 103 | 131 | 140 | 129 | 125 | 129
Undone PBI Effort | 83 | 131 | 86 | 114 | 61 | 44 | 96 | 147 | 147 | 153 | 211 | 137 | 95 | 138 | 161 | 70 | 145 | 164 | 99
Comitted Releasable Dev Tasks | 41 | 246 | 213 | 217 | 261 | 228 | 298 | 583 | 583 | 290 | 235 | 306 | 238 | 305 | 255 | 181 | 290 | 265 | 236
Sprint Goal | Localisation tasks to be awaiting release (SD-99093, SD-97413, SD-98509, SD-99589, SD-97399). | Localization feature to be testable in production, PM is able to launch multi-language campaign. | Localization feature to be testable in production, PM is able to launch multi-language campaign. | Localization feature to be testable in production, PM is able to launch multi-language campaign. | Create localization campaign and send it from launch step without any "tricks" | Localization: Resolving MVP blockers for validation and launch step. | Localization MVP to be ready for Live UAT Camp and opened for automation partners. | Localization:conduct Live UAT Camp and resolve blockers for Beta. | Localization:conduct Live UAT Camp and resolve blockers for Beta. | 1. Localization is stable and ready for Beta. 2. List-Unsubscribe task is live. | 1. Deliver View In Browser feature. 2. Product stabilisation (resolve SLA bugs + incident actions). Total SG effort 130S | 1. Releasing Automated Unsubscribe popup before Bayram starts; 2. Stabilization: resolving bug tasks. | 1. US Readiness task. 2. Bug tasks | 1. US Readiness task. 2. Bug tasks | Resolving Bugs. Stabilization sprint | Omnibus price, micro-fe, pony-express | Omnibus price, pony-express | Omnibus price, pony-express | pony-express
Goal Achieved (0/1) | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 56.32% | 66.79% | 84.75% | 76.81% | 78.89% | 84.93% | 91.74% | 70.71% | 70.71% | 71.61% | 70.57% | 83.85% | 69.75% | 43.77% | 71.59% | 81.18% | 66% | 67.55% | 79.1%
Bug/Development Ratio | 0% | 21.52% | 30.46% | 17.28% | 25.41% | 25.7% | 21.02% | 25.69% | 25.69% | 23.81% | 50.88% | 43.82% | 36.94% | 58.09% | 34.29% | 45.21% | 37.95% | 54.75% | 50.27%
Shipping Accuracy | 47.42% | 48.1% | 53.45% | 73.82% | 75.14% | 48.6% | 55.59% | 90.83% | 90.83% | 70% | 52.05% | 89.51% | 76.43% | 75.74% | 74.86% | 95.89% | 66.15% | 69.83% | 69.73%
Partner Focus | 21.58% | 92.83% | 95.52% | 82.51% | 90.31% | 78.08% | 87.91% | 89.42% | 89.42% | 93.55% | 88.68% | 95.03% | 100% | 97.44% | 96.59% | 97.31% | 96.67% | 100% | 96.72%
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 17.56% | 36.6% | 30.49% | 31.18% | 32.53% | 39% | 41% | 30% | 30% | 30.97% | 49.06% | 36% | 34% | 35% | 30% | 31% | 40% | 22% | 32% | 0% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 80% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 15% | 30% | 30% | 100% | 100% | 100% | 100% | 30% | 30% | 100% | 30% | 100% | 30% | 100% | 30% | 30% | 15% | 70% | 27% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [12 empty] | 30% | 100% | 30% | 30% | 15% | 85%
Individual Committed Effort
Individual Done Effort | [25 empty] | 41.9839
Deniz | 6 | 0 | 0 | 5 | 0 | 26 | 15 | 36 | 36 | 21 | 28 | 19 | 35 | 22 | 27 | 5 | 10 | 21 | 50 | [6 empty] | 19.0526 | 362
Sprint Goal Contribution | localization panel listing page | localization design step issues |  |  | (vacation) |  | toggles
Murat | 24 | 22 | 30 | 47 | 42 | 41 | 34 | 76 | 76 | 30 | 11 | 41 | 18 | 38 | 29 | 29 | 63 | 26 | 54 | [6 empty] | 38.4737 | 731
Sprint Goal Contribution | localization panel design step backend | localization design step issues, Pony express | terraform, pony express | Email Service - Localization Test Functionality, pony express | localization design step, pony express | [localization] launch step test email backend | pony express, terraform, enable recommendation
Vlad | 20 | 31 | 21 | 38 | 37 | 45 | 55 | 73 | 73 | 46 | 30 | 26 | 20 | 30 | 13 | 17 | 19 | 20 | 43 | [6 empty] | 34.5789 | 657
Sprint Goal Contribution | localization panel design step frontend | localization design step issues | Finish design step functionality, Fix design editors | [FE] Add design step validations [FE] Add skeleton values and loading statuses | localization launch step | [FE] implement launchV2 validations | launchV2 issues, unsubscribe issues
Vitalii | 43 | 58 | 50 | 24 | 58 | 50 | 100 | 113 | 113 | 50 | 48 | 62 | 43 | 38 | 63 | 10 | 16 | [8 empty] | 55.2353 | 939
Sprint Goal Contribution | localization content api backwards compatibility | Content API |  |  | localization launch step validations | [Localization] Campaign Duplicate feature | duplication endpoint, timer
Sinem | 0 | 45 | 65 | 71 | 73 | 56 | 83 | 96 | 96 | 63 | 30 | 74 | 47 | 72 | 51 | 61 | 89 | 92 | 25 | [6 empty] | 62.5789 | 1189
Sprint Goal Contribution |  |  |  | Honey Badger - Localization Test Functionality |  | [FE] fixes for launchV2: send later + recurring campaigns | content api
Hasan Alay | [16 empty] | 10 | 0 | 2 | [6 empty] | 4 | 12
Sprint Goal Contribution
Omer | 4 | 2 | 8 | 14 | 5 | 14 | 10 | 47 | 47 | - |  | 28 | 15 | [5 empty] | 11 | [6 empty] | 17.0833 | 205
Sprint Goal Contribution
QAs | 10 | 19 | 15 | 3 | 13 | 16 | 14 | 20 | 20 | 12
Elnara | 3 | 0 | 0 | 1 | 5 | 7 | 0 | 0 | 0 | 0
Görkem | 2 | 16 | 13 | 2 | 8 | 5 | 14 | 14 | 14 | 10
Oleksandr | [5 empty] | 3 | 0 | 3 | 3 | 0
Yunus Emre |  | 3 | 0 | 0 |  | 1 | 0 | 3 | 3 | 2
Tugba | 5 | 0 | 2 | 0
Total Done Effort | 107 | 177 | 189 | 202 | 228 | 248 | 311 | 461 | 461 | 222
Grooming Presenter | [11 empty] | Sinem | Vitalii | Murat | Deniz | Deniz | Vlad | Sinem | Deniz
Sprint Goal KR Focused Effort
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on D20: 18SP Awaiting 50SP Ready for Release 13SP Rejected
Note on E20: 18SP Awaiting 13SP Ready for Release
Note on G20: 47SP Awaiting Release 55SP Ready For Release
Note on G27: deployment got cancelled on March 25, 27
Note on H20: 47SP Awaiting 81SP Ready for Release 3SP Rejected
Note on H22: 17SP Research 24SP QA Tasks
Note on I8: 54SP QA tasks
Note on I23: 5/37 tasks are undone the rest are done. We couldn't open the feature to beta partners
Note on I31: SG effort: 193
Note on J8: 54SP QA tasks
Note on J23: 5/37 tasks are undone the rest are done. We couldn't open the feature to beta partners
Note on J31: SG effort: 193
Note on L23: 16SP View in Browser (KR) 54SP Bugs 57SP Incident Actions
Note on M20: awaiting release - 15 ready for release - 8 -Vlad Shusterman UPD: ar - 23 -Vlad Shusterman
Note on M22: QA tasks excluded -Vlad Shusterman with qa tasks - 330 -Vlad Shusterman
Note on N22: with QA tasks -Vlad Shusterman
Note on O22: with QAs tasks -Vlad Shusterman
Note on P9: recalculate emerged tasks -Vlad Shusterman
Note on T23: SD-111566 task wasn't completed, it's still in testing. main reason - kube issue. -Vlad Shusterman
Note on U32: calculate all empty values from this row -Vlad Shusterman

## Samaritan
Samaritan
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 | [6 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  |  | Oct |  | Nov |  | Dec
Sprint Start-End Dates | 27.12 - 10.01 | 10.01 - 24.01 | 24.01 - 07.02 | 07.02 - 21.02 | 21.02 - 06.03 | 06.03 - 20.03 | 20.03 - 03.04 | 03.04 - 17.04 | 17.04 - 01.05 | 01.05 - 15.05 | 15.05 - 29.05 | 29.05 - 07.06 | 07.06 - 26.06 | 26.06 - 10.07 | 10.07 - 24.07 | 24.07 - 07.08 | 07.08 - 21.08 | 21.08 - 04.09 | 04.09 - 18.09 | 18.09 - 02.10 | 02.10 - 16-10
Sprint Name | #394 - Samaritan | #396 - Samaritan | #398 - Samaritan | #400 - Samaritan | #402 - Samaritan | #404 - Samaritan | #406 - Samaritan - Broken 💔s | #408 - Samaritan - 💔 of GLU | #410 - Samaritan | #412 - Samaritan | #414 - Samaritan | #416 - Samaritan | #418 - Samaritan | #420 - Samaritan | #422 - Samaritan | #424 - Samaritan | #426 - Samaritan | #428 - Samaritan | #430 - Samaritan | #432 - Samaritan | #434 - Samaritan
Total Effort In the Sprint | 403 | 409 | 530 | 449 | 442 | 413 | 433 | 230 | 498 | 462 | 512 | 333 | 414 | 449 | 454 | 449 | 452 | 462 | 521 | 553 | 499
Commited | 376 | 380 | 467 | 394 | 387 | 382 | 403 | 197 | 403 | 401 | 409 | 292 | 334 | 377 | 399 | 444 | 435 | 411 | 452 | 504 | 460
Emerged | 27 | 29 | 63 | 55 | 55 | 31 | 30 | 33 | 95 | 61 | 103 | 41 | 80 | 72 | 55 | 35 | 17 | 51 | 69 | 49 | 39
Non-Bug Emerged | 16 | 12 | 61 | 44 | 49 | 4 | 17 | 27 | 75 | 32 | 66 | 23 | 46 | 65 | 50 | 22 | 9 | 30 | 49 | 1 | 7
Emerged Rate | 6.7% | 7.09% | 11.89% | 12.25% | 12.44% | 7.506% | 6.928% | 14.35% | 19.08% | 13.2% | 20.12% | 12.31% | 19.32% | 16.04% | 12.11% | 7.795% | 3.761% | 11.04% | 13.24% | 8.861% | 7.816% | 0% | 0% | 0% | 0% | 0%
Total Design Effort In the Sprint | 123 | 81 | 116 | 94 | 97 | 81 | 77 | 53 | 76 | 75 | 89 | 60 | 67 | 45 | 81 | 78 | 78 | 63 | 86 | 110 | 81
Commited Design Effort | 123 | 81 | 116 | 94 | 97 | 81 | 77 | 53 | 76 | 70 | 89 | 55 | 67 | 45 | 81 | 78 | 78 | 63 | 86 | 110 | 81
Done Design Effort | 123 | 81 | 116 | 94 | 97 | 81 | 77 | 43 | 76 | 70 | 77 | 47 | 67 | 45 | 81 | 78 | 78 | 63 | 86 | 110 | 81
Success Rate | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 86.52% | 85.45% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
UX Improvement (%) | [5 empty] | 2.066% | 2.174% | 6.015% | 7.56% | 11.97% | 8.462% | 5.714% | 6.404% | 1.049% | 0% | 22.13% | 6.443% | 5.747% | 1.366% | 9.391% | 13.58%
Done Bug Effort | 20 | 45 | 33 | 40 | 44 | 74 | 63 | 23 | 47 | 66 | 84 | 67 | 88 | 51 | 19 | 34 | 43 | 28 | 50 | 79 | 82
Commited Bug Effort | 9 | 35 | 33 | 34 | 39 | 59 | 50 | 17 | 36 | 47 | 60 | 62 | 56 | 46 | 14 | 32 | 40 | 7 | 43 | 47 | 50
Emerged Bug Effort | 11 | 17 | 2 | 11 | 6 | 27 | 13 | 6 | 20 | 29 | 37 | 18 | 34 | 7 | 5 | 13 | 8 | 21 | 20 | 48 | 32
Done Pool Effort | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Done Pool Bug Effort | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dev Tasks Done Effort | 242 | 238 | 288 | 212 | 279 | 147 | 207 | 105 | 324 | 311 | 252 | 216 | 290 | 318 | 309 | 328 | 339 | 344 | 367 | 349 | 243
All Tasks Done Effort | 385 | 364 | 437 | 346 | 420 | 302 | 347 | 175 | 447 | 391 | 413 | 291 | 357 | 342 | 420 | 406 | 417 | 407 | 453 | 438 | 324
Released Effort | 196 | 126 | 188 | 163 | 176 | 101 | 183 | 76 | 201 | 237 | 202 | 188 | 281 | 234 | 230 | 234 | 245 | 256 | 274 | 223 | 135
Undone PBI Effort | 18 | 38 | 91 | 98 | 21 | 99 | 86 | 55 | 42 | 71 | 73 | 16 | 47 | 107 | 34 | 43 | 35 | 47 | 68 | 94 | 196
Comitted Releasable Dev Tasks | 244 | 264 | 318 | 266 | 251 | 242 | 276 | 133 | 291 | 284 | 260 | 175 | 203 | 286 | 274 | 366 | 357 | 348 | 366 | 394 | 383
Sprint Goal | GLU: release On Even&Attribute starters + Exit Criteria to be awaiting release\nfix automation for Wait for Event&Attribute\n\nNBC: both tasks to be awaiting release (deployment deadline at 15th Jan) | GLU + NBC tasks to be awaiting release\nGLU wait for event attribute tasks to be released\nAutomation fix task to be done | GLU exit criteria to be deployed\nCanvas refactor + GLU + analytics refactor tasks to be awaiting release | GLU + Analytics Refactor +Saving Call an API Template + Canvas Refactor tasks to be awaiting release | GLU On dynamic date deployment\nFlagged GLU tasks, New Canvas, Analytics Refactor and Channel Metrics tasks to be awaiting release | GLU + New Canvas + Analytics Refactor tasks to be awaiting release + Automations for dynamic content | Canvas Refactor + Call an API Response tasks to be released\nGLU + Analytics Refactor tasks to be awaiting release | Smart Journey to be released\nGLU, Analytics Refactor and flagged fixes to be awaiting release | Consistent Coupons BE+FE release with feature flag\nGLU segmentation package to be released\nAutomation fixes to be released\nGLU tasks to be awaiting release | All sprint goal tasks to be deployed | All sprint goal tasks to be deployed | All sprint goal tasks to be deployed | All sprint goal tasks to be deployed | Paracetamol and View through Enigma Task to be AR, Others to be deployed | All goal tasks to be deployed except; VTC FE Research | View-through and Canvas tasks to be released Goal and Exit Criteria Improvements to be awaiting release | attribute change addition for exit/goals to be released canvas v2 journey versioning to be released view through conversion + kube fix + segmentation refactor + coupon integration tasks to be awaiting release | Canvas tasks to be deployed Creating tag API task to be awaiting release Research tasks to be completed | Expression tasks to be awaiting release AI analytics assistant+canvasv2+Inapp and onsite proceed users logic change tasks to be released | SD-11584- Awaiting Release All other goal tasks to be Released | Localization Research to be completed Export API tasks + Hepsiburada task + Event Conversion task to be released Automation Cases Fix to be completed
Goal Achieved (0/1) | 100% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 102.4% | 95.79% | 93.58% | 87.82% | 108.5% | 79.06% | 86.1% | 88.83% | 110.9% | 97.51% | 101% | 99.66% | 106.9% | 90.72% | 105.3% | 91.44% | 95.86% | 99.03% | 100.2% | 86.9% | 70.43%
Bug/Development Ratio | 8.264% | 18.91% | 11.46% | 18.87% | 15.77% | 50.34% | 30.43% | 21.9% | 14.51% | 21.22% | 33.33% | 31.02% | 30.34% | 16.04% | 6.149% | 10.37% | 12.68% | 8.14% | 13.62% | 22.64% | 33.74% | 0% | 0% | 0% | 0% | 0%
Shipping Accuracy | 80.99% | 52.94% | 65.28% | 76.89% | 63.08% | 68.71% | 88.41% | 72.38% | 62.04% | 76.21% | 80.16% | 87.04% | 96.9% | 73.58% | 74.43% | 71.34% | 72.27% | 74.42% | 74.66% | 63.9% | 55.56% | 0% | 0% | 0% | 0% | 0%
Partner Focus
Bug Score
Sprint Goal KR Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 38% | 43.16% | 40% | 44% | 42% | 64% | 35% | 36% | 43% | 34% | 52% | 44% | 39% | 35% | 43% | 40% | 36% | 35% | 42% | 40% | 37% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 100% | 100% | 30% | 30% | 100% | 30% | 30% | 30% | 100% | 85% | 100% | 100% | 100% | 30% | 100% | 100% | 100% | 100% | 100% | 30% | 30% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [13 empty] | 30% | 100% | 100% | 100% | 100% | 100%
Individual Committed Effort
Abdurrahman Said Aslan | 39 | 33 | 43 | 37 | 42 | 38 | 36 | 22 | 40 | 42 | 48 | 32 | 29 | 50 | 44 | 43 | 36 | 48 | 41 | 45 | 50
Ahmad Masabni | 40 | 41 | 49 | 38 | 41 | 42 | 39 | 25 | 48 | 53 | 0 | 37 | 43 | 60 | 49 | 51 | 44 | 38 | 53 | 52 | 52
Ahmet Kerem Gündüz | 47 | 35 | 42 | 50 | 55 | 44 | 43 | 29 | 42 | 36 | 52 | 29 | 46 | 45 | 47 | 47 | 44 | 21 | 44 | 47 | 47
Alper Önal | - | - | - | - | - | 5 | 16 | 8 | 13 | 16 | 13 | 8 | 13 | 13 | 4 | 0 | 10 | 16 | 13 | 13 | 0
Blazenko Davidoviç | 39 | 37 | 35 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Bríana Walsh | 0 | 35 | 24 | 14 | 0 | 25 | 16 | 13 | 5 | 21 | 25 | 20 | 18 | 29 | 27 | - | - | - | - | - | -
Beste Morgul | [16 empty] | 3 | 5 | 5 | 5 | 0
Can Karademir | [13 empty] | 5 | 5 | 5 | 5 | 5 | 2 | 3 | 5
Emre Kaya | 29 | 42 | 66 | 25 | 32 | 25 | 39 | 15 | 33 | 43 | 60 | 33 | 47 | 7 | 0 | 51 | 54 | 45 | 50 | 60 | 50
Evgeniy Areshkin | 29 | 43 | 48 | 42 | 42 | 38 | 47 | 24 | 50 | 21 | 52 | 36 | 47 | 49 | 50 | 50 | 42 | 49 | 42 | 58 | 65
Mustafa Çörekçi | 8 | 8 | 8 | 8 | 8 | 11 | 16 | 3 | 9 | 13 | 13 | 9 | 5 | 8 | 8 | 8 | 7 | 14 | 11 | 8 | 13
Nour Alsadat | 37 | 9 | 39 | 44 | 42 | 37 | 37 | 24 | 34 | 34 | 37 | 26 | 29 | 0 | 34 | 31 | 34 | 42 | 42 | 42 | 34
Oğuzhan Arnak | 38 | 44 | 34 | 44 | 37 | 43 | 44 | 20 | 50 | 49 | 50 | 35 | 28 | 57 | 43 | 51 | 50 | 20 | 50 | 53 | 53
Pelin Tok | 7 | 5 | 8 | 8 | 8 | 10 | 6 | 5 | 8 | 16 | 8 | 8 | 8 | 2 | 0 | 8 | 10 | 14 | 11 | 11 | 7
Pınar Tezcan | 29 | 33 | 46 | 37 | 37 | 40 | 31 | 0 | 22 | 40 | 43 | 0 | 0 | 45 | 41 | 44 | 43 | 39 | 41 | 44 | 20
Rashad Nasirli | 5 | 8 | 8 | 8 | 8 | 8 | 11 | 6 | 8 | - | - | - | - | - | - | - | - | - | - | - | -
Vitaly Schekin | 29 | 42 | 39 | 45 | 35 | 41 | 36 | 16 | 44 | 38 | 55 | 39 | 31 | 58 | 47 | 55 | 53 | 55 | 47 | 42 | 51
Individual Done Effort
Abdurrahman Said Aslan | 39 | 37 | 23 | 23 | 34 | 38 | 21 | 11 | 45 | 44 | 53 | 32 | 31 | 50 | 62 | 33 | 36 | 51 | 27 | 18 | 12
Ahmad Masabni | 40 | 44 | 34 | 54 | 41 | 25 | 40 | 28 | 54 | 48 | 0 | 38 | 48 | 61 | 49 | 61 | 44 | 30 | 49 | 57 | 14
Ahmet Kerem Gündüz | 47 | 35 | 42 | 50 | 55 | 44 | 43 | 29 | 42 | 36 | 52 | 16 | 46 | 45 | 47 | 47 | 44 | 21 | 44 | 47 | 47
Alper Önal | - | - | - | - | - | 5 | 16 | 10 | 17 | 16 | 30 | 9 | 13 | 16 | 4 | 13 | 10 | 16 | 15 | 14 | 15
Blazenko Davidoviç | 39 | 37 | 35 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Bríana Walsh | 0 | 35 | 24 | 14 | 0 | 25 | 16 | 13 | 5 | 21 | 25 | 20 | 18 | 29 | 27 | - | - | - | - | - | -
Beste Morgul | [16 empty] | 3 | 8 | 5 | 5 | 5
Can Karademir | [13 empty] | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 5
Emre Kaya | 30 | 39 | 66 | 16 | 24 | 22 | 39 | 15 | 47 | 44 | 65 | 36 | 57 | 7 | 25 | 51 | 54 | 51 | 51 | 68 | 42
Evgeniy Areshkin | 29 | 43 | 25 | 1 | 55 | 30 | 13 | 3 | 55 | 9 | 55 | 28 | 52 | 10 | 42 | 42 | 39 | 52 | 48 | 34 | 23
Mustafa Çörekçi | 8 | 8 | 8 | 10 | 8 | 3 | 16 | 0 | 14 | 20 | 13 | 9 | 5 | 8 | 8 | 8 | 7 | 14 | 11 | 9 | 0
Nour Alsadat | 37 | 9 | 39 | 44 | 42 | 37 | 40 | 24 | 34 | 34 | 38 | 31 | 21 | 0 | 34 | 31 | 34 | 42 | 42 | 42 | 34
Oğuzhan Arnak | 40 | 25 | 41 | 50 | 50 | 31 | 45 | 29 | 53 | 56 | 52 | 35 | 21 | 57 | 44 | 38 | 50 | 19 | 50 | 49 | 48
Pelin Tok | 3 | 5 | 8 | 8 | 8 | 10 | 11 | 5 | 8 | 8 | 8 | 11 | 8 | 2 | 0 | 8 | 5 | 14 | 13 | 11 | 7
Pınar Tezcan | 37 | 33 | 46 | 37 | 37 | 6 | 21 | 0 | 25 | 36 | 8 | 0 | 0 | 40 | 36 | 51 | 36 | 30 | 44 | 33 | 20
Rashad Nasirli | 5 | 13 | 8 | 0 | 8 | 8 | 11 | 6 | 8 | - | - | - | - | - | - | - | - | - | - | - | -
Vitaly Schekin | 31 | 43 | 58 | 53 | 57 | 43 | 29 | 15 | 45 | 38 | 52 | 44 | 55 | 62 | 34 | 58 | 50 | 62 | 50 | 48 | 57
Sprint Goal KR Focused Effort
Note on A31: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A39: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%

## Unix
Bytemasters - Unix
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 28/12 - 11/01 | 11/01 - 25/01 | 25/01 - 08/02 | 08/02 - 22/02 | 22/02 - 07/03 | 07/03 - 21/03 | 21/03 - 04/04 | 04/04 - 18/04 | 18/04 - 02/05 | 02/05 - 16/05 | 16/05 - 30/05 | 30/05 - 12/06 | 13/06 - 27/06 | 27/06 - 11/07 | 11/07 - 26/07 | 26/07 - 08/08 | 08/08 - 22/08 | 22/08 - 05/09 | 05/09 - 24/09 | 24/09 - 03/10
Sprint Name | #394 | #396 | #398 | #400 | #402 | #404 | #406 | #408 | #410 | #412 | #414 | #416 | #418 | #420 | #422 | #424 | #426 | #428 | #430 | #432
Total Effort In the Sprint | 347 | 451 | 416 | 445 | 620 | 594 | 386 | 264 | 449 | 418 | 411 | 414 | 234 | 460 | 502 | 469 | 345 | 490 | 546 | 511 | 541
Commited | 328 | 401 | 355 | 403 | 436 | 442 | 321 | 242 | 421 | 350 | 371 | 357 | 184 | 422 | 431 | 407 | 308 | 405 | 450 | 430 | 482
Emerged | 19 | 52 | 38 | 38 | 92 | 58 | 65 | 22 | 28 | 68 | 40 | 47 | 50 | 35 | 57 | 62 | 37 | 85 | 96 | 81 | 59
Non-Bug Emerged | 16 | 44 | 15 | 27 | 89 | 53 | 50 | 6 |  | 62 | 13 | 12 | 24 | 16 | 26 | 52 | 22 | 64 | 77 | 57 | 24
Emerged Rate | 5.476% | 11.53% | 9.135% | 8.539% | 14.84% | 9.764% | 16.84% | 8.333% | 6.236% | 16.27% | 9.732% | 11.35% | 21.37% | 7.609% | 11.35% | 13.22% | 10.72% | 17.35% | 17.58% | 15.85% | 10.91% | 0% | 0% | 0% | 0% | 0%
Total Design Effort In the Sprint | 96 | 94 | 95 | 99 | 110 | 99 | 105 | 41 | 95 | 76 | 73 | 53 | 21 | 31 | 39 | 37 | 0 | 32 | 34 | 0 | 0
Commited Design Effort | 96 | 94 | 95 | 99 | 109 | 99 | 105 | 41 | 95 | 76 | 68 | 53 | 21 | 31 | 39 | 37 | 0 | 32 | 34 | 0 | 0
Done Design Effort | 96 | 94 | 95 | 99 | 102 | 99 | 105 | 41 | 72 | 76 | 73 | 53 | 8 | 31 | 39 | 37 | 0 | 11 | 34 | 0 | 0
Success Rate | 100% | 100% | 100% | 100% | 93.58% | 100% | 100% | 100% | 75.79% | 100% | 107.4% | 100% | 38.1% | 100% | 100% | 100% | 0% | 34.38% | 100% | 0 | 0%
UX Improvement (%) |  |  |  | 13.66% | 1.229% | 12.59% | 12.41% | 27.08% | 29.26% | 19.7% | 28.53% | 14.51% | 22.22% | 36.21% | 19.83% | 22.07% | 2.128% | 9.239% | 8.038% | 18.94%
Done Bug Effort | 41 | 34 | 81 | 69 | 63 | 68 | 69 | 52 | 54 | 38 | 77 | 95 | 42 | 69 | 66 | 61 | 49 | 95 | 77 | 80 | 56
Commited Bug Effort | 56 | 35 | 67 | 58 | 56 | 82 | 57 | 38 | 55 | 33 | 63 | 60 | 34 | 50 | 44 | 59 | 37 | 82 | 68 | 59 | 50
Emerged Bug Effort | 3 | 9 | 23 | 11 | 13 | 5 | 15 | 16 | 18 | 6 | 27 | 35 | 26 | 19 | 31 | 10 | 15 | 21 | 19 | 24 | 35
Done Pool Effort | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Done Pool Bug Effort | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dev Tasks Done Effort | 211 | 295 | 254 | 371 | 401 | 314 | 301 | 190 | 378 | 295 | 284 | 325 | 171 | 384 | 330 | 322 | 271 | 343 | 396 | 324 | 318
All Tasks Done Effort | 243 | 329 | 285 | 400 | 401 | 314 | 339 | 238 | 402 | 331 | 278 | 341 | 175 | 426 | 429 | 365 | 307 | 385 | 412 | 324 | 374
Released Effort | 87 | 146 | 197 | 152 | 182 | 160 | 204 | 138 | 248 | 208 | 128 | 250 | 53 | 310 | 253 | 228 | 165 | 221 | 253 | 155 | 212
Undone PBI Effort | 104 | 122 | 131 | 45 | 219 | 434 | 182 | 126 | 201 | 210 | 283 | 164 | 181 | 150 | 249 | 241 | 180 | 269 | 293 | 356 | 329
Comitted Releasable Dev Tasks | 296 | 373 | 355 | 366 | 407 | 413 | 266 | 192 | 376 | 296 | 278 | 362 | 171 | 301 | 353 | 367 | 282 | 368 | 450 | 390 | 427
Sprint Goal | New Canvas + Group Level Access + Count Bubble + Overage Pricing + Control Group Tasks to be AR & Deploy Control Group | CG + Count Bubble + Pricing + Email ID + Troubleshooting + Character Count to AR + Deploy Group Level Access | Canvas Refactor Smart Journey CG to AR Deployment for Incident Task | CG Smart Canvas UTM Remove Class to be AR | Migration Tasks (Tech Debt + Hepsiburada) Canvas KR Smart Journey Pricing Tasks to AR | Canvas Smart Journey Evercopy tasks to AR | Canvas & Dmitry's & Incident Actions tasks to AR + Evercopy to be Deployed | Coupon + Hepsiburada segmentation + CG + Dynamic Content + Canvas to AR + Prevent sending empty dynamic content to Deploy | dynamic content to be deployed & glu + canvas + coupon + Whatsapp and CG to AR | whatsapp tasks to AR & localization + canvas + empty dynamic content to be deployed | Deployment for canvas v2 + prevent dynamic + testing ttl + localization + hepsiburada + segment support + reasoning & AR for credentials | Deployment for Canvas v2 + TıklaGelsin + Slack Clean-up + Localization & AR for Unsubs + Call an API | Evercopy + Html Editor + Canvas + Test message to be AR hepsiburada task to be Deployed | canvas v2 + call api + wait + cg + testing security to be done & extended path to be AR | canvas v2 + localization metadata + hepsiburadamerchant + us date + smart journey + template library to deployment & localization updates to AR | Localization + InApp/OnSite + Smart Journey + Canvas v2 + Ad Audiences + Template Library + Unique Event Conversion to be deployed | canvas v2 + unique conversion to Deployment + Expression & CG to AR | Expressions & Canvas v2 & Optimizer to Deployment + CG to be AR | CG logic change & Localization Validation & US Readiness & Export to AR & CG + Localization + Canvas v2 to Deployment | Localization to AR + A/B Split CG to Deployment | Localization & ABCG to AR + Arc-level CG & stripo & US email to Deployment
Goal Achieved (0/1) | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 74.09% | 82.04% | 80.28% | 99.26% | 91.97% | 71.04% | 105.6% | 98.35% | 95.49% | 94.57% | 74.93% | 95.52% | 95.11% | 100.9% | 99.54% | 89.68% | 99.68% | 95.06% | 91.56% | 75.35% | 77.59%
Bug/Development Ratio | 19.43% | 11.53% | 31.89% | 18.6% | 15.71% | 21.66% | 22.92% | 27.37% | 14.29% | 12.88% | 27.11% | 29.23% | 24.56% | 17.97% | 20% | 18.94% | 18.08% | 27.7% | 19.44% | 24.69% | 17.61% | 0% | 0% | 0% | 0% | 0%
Shipping Accuracy | 41.23% | 49.49% | 77.56% | 40.97% | 45.39% | 50.96% | 67.77% | 72.63% | 65.61% | 70.51% | 45.07% | 76.92% | 30.99% | 80.73% | 76.67% | 70.81% | 60.89% | 64.43% | 63.89% | 47.84% | 66.67% | 0% | 0% | 0% | 0% | 0%
Partner Focus
Bug Score
Sprint Goal KR Effort (%) | [20 empty] | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | bar: #394 to #432
Sprint Goal Effort (%) | 33.25% | 43.16% | 37% | 48.64% | 48.89% | 39.95% | 31.21% | 50% | 37.77% | 41.72% | 33% | 34.45% | 39.67% | 39.48% | 46.64% | 48.5% | 35.46% | 32% | 43% | 42% | 38% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 30% | 100% | 30% | 30% | 100% | 30% | 30% | 30% | 100% | 30% | 30% | 100% | 100% | 100% | 30% | 30% | 100% | 100% | 30% | 30% | 30% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | #420: 100%; #422: 30%; #424: 30%; #426: 100%; #428: 100%; #430: 30%
Individual Committed Effort
Abdullah Çanakçı | 0 | 40 | 47 | 66 | 60 | 53 | 44 | 35 | 58 | 47 | 47 | 50 | 29 | 57 | 59 | 52 | 38 | 55 | 57 | 56 | 54
Alexander Korotkov | 19 | 43 | 40 | 46 | 47 | 40 | 58 | 35 | 63 | 41 | 43 | 58 | 31 | 55 | 67 | 43 | 58 | 37 | 47 | 61 | 64
Ali Osman Menekşe | 55 | 61 | 47 | 44 | 62 | 57 | 20 | 25 | 50 | 62 | 47 | 31 | 10 | 34 | 54 | 46 | 36 | 55 | 50 | 49 | 62
Briana Walsh | 0 | 4 | 35 | 40 | 32 | 34 | 23 | 11 | 36 | 18 | 0 | 8 |  | 13
Dmitry Androsov | 47 | 60 | 49 | 16 | 47 | 48 | 45 | 24 | 65 | 60 | 52 | 61 | 23 | 60 | 59 | 55 | 42 | 53 | 65 | 56 | 63
Doğu Özcan | #428: 19; #430: 23; #432: 21 | 49
Enes Yenidoğan | 11 | 10 | 8 | 13 | 13 | 15 | 16 | 13 | 13 | 13 | 13 | 13 | 3 | 13 | 14 | 14 | 13 | 18 | 8 | 12 | 6
Ertuğrul Akça | 35 | 42 | 30 | 50 | 53 | 46 | 45 | 32 | 43 | 16 | 43 | 43 | 18 | 41 | 45 | 47 | 26 | 21 | 40 | 56 | 3
Gamze Nurcan Polat | 43 | 45 | 15 | 43 | 47 | 45 | 21 | 29 | 50 | 49 | 41 | 42 | 29 | 47 | 45 | 47 | 28 | 36 | 26 | 34 | 54
Işıl Hande Süer | #394: 34; #396: 24; #398: 30; #400: 32; #402: 30; #404: 29; #406: 35; #408: 14; #410: 29; #412: 9
Leyla Meram | 8 | 5 | 10 | 8 | 8 | 8 | 12 | 5 | 5 | 8 | 11 | 11 | 5 | 14 | 9 | 8 | 8 | 5 | 8 | 8 | 0
Mert Yıldırım | #394: 44; #396: 36; #398: 46; #400: 8; #402: 41; #404: 58
Nejdet Arslan | #394: 8; #396: 8; #398: 3; #400: 8
Seren Beskok | 47 | 41 | 31 | 35 | 32 | 31 | 32 | 11 | 34 | 33 | 34 | 13 | 0
Sercan Çakır | 53 | 46 | 49 | 55 | 50 | 63 | 46 | 28 | 68 | 56 | 36 | 39 | 31 | 49 | 61 | 48 | 37 | 55 | 77 | 63 | 63
Yaprak Demirci | 15 | 29 | 34 | 32 | 47 | 39 | 38 | 16 | 32 | 34 | 39 | 40 | 21 | 31 | 39 | 37 | 0 | 32 | 34
Zeyneb Yılmaz | 5 | 5 | 10 | 8 | 8 | 8 | 11 | 6 | 6 | 11 | 8 | 9 | 5 | 8 | 8 | 13 | 5 | 9 | 8 | 13 | 8
Ozan Karali | #420: 2; #422: 3; #424: 5; #426: 8; #428: 5; #430: 5; #432: 7 | 6
Yuriy Lykhusha | #420: 42; #422: 41; #424: 23; #426: 17; #428: 37; #430: 55; #432: 59 | 50
Individual Done Effort
Abdullah Çanakçı | 0 | 46 | 49 | 73 | 41 | 50 | 56 | 30 | 56 | 73 | 13 | 48 | 40 | 63 | 48 | 31 | 27 | 45 | 60 | 6 | 17
Alexander Korotkov | 13 | 8 | 27 | 12 | 47 | 6 | 8 | 35 | 63 | 7 | 35 | 58 | 33 | 36 | 64 | 40 | 55 | 37 | 52 | 58 | 44
Ali Osman Menekşe | 55 | 31 | 17 | 44 | 88 | 54 | 18 | 30 | 61 | 57 | 47 | 32 | 10 | 35 | 57 | 75 | 49 | 70 | 30 | 41 | 36
Briana Walsh | 68 | 35 | 35 | 40 | 32 | 34 | 23 | 11 | 36 | 18 | 0 | 8 |  | 13
Dmitry Androsov | 52 | 89 | 46 | 42 | 48 | 51 | 48 | 29 | 64 | 71 | 78 | 63 | 26 | 54 | 62 | 38 | 46 | 53 | 63 | 56 | 61
Doğu Özcan | #428: 0; #430: 12; #432: 28 | 34
Enes Yenidoğan | 3 | 12 | 8 | 13 | 10 | 10 | 13 | 5 | 16 | 13 | 16 |  | 3 | 18 | 6 | 14 | 13 | 18 | 13 | 12 | 9
Ertuğrul Akça | 27 | 42 | 36 | 52 | 54 | 12 | 48 | 40 | 39 | 13 | 43 | 36 | 18 | 45 | 49 | 47 | 27 | 3 | 19 | 19 | 5
Gamze Nurcan Polat | 43 | 25 | 17 | 45 | 57 | 41 | 21 | 29 | 53 | 49 | 34 | 45 | 29 | 51 | 49 | 26 | 19 | 37 | 30 | 12 | 54
Işıl Hande Süer | #394: 34; #396: 24; #398: 30; #400: 32; #402: 30; #404: 29; #406: 35; #408: 14; #410: 29; #412: 9
Leyla Meram | 8 | 0 | 10 | 8 | 10 | 8 | 14 | 6 | 6 | 0 | 11 | 14 |  | 14 | 9 | 0 | 10 | 10 | 8 | 8 | 3
Mert Yıldırım | #394: 18; #396: 15; #398: 16; #400: 48; #402: 28; #404: 34
Nejdet Arslan | #394: 0; #396: 3; #398: 3; #400: 0
Seren Beskok | 47 | 41 | 31 | 35 | 33 | 31 | 32 | 11 | 34 | 33 | 34 | 13
Sercan Çakır | 40 | 53 | 71 | 55 | 50 | 63 | 55 | 28 | 63 | 61 | 62 | 59 | 32 | 58 | 67 | 45 | 29 | 58 | 88 | 65 | 68
Yaprak Demirci | 15 | 29 | 34 | 32 | 39 | 39 | 38 | 16 | 32 | 34 | 39 | 40 | 8 | 31 | 39 | 37 | 0 | 11 | 34
Zeyneb Yılmaz | 5 | 5 | 10 | 8 | 8 | 8 | 11 | 6 | 2 | 11 | 3 | 9 | 5 | 8 | 5 | 13 | 5 | 9 | 3 | 8 | 8
Ozan Karali | #418: 3; #420: 2; #422: 3; #424: 6; #426: 8; #428: 5; #430: 3; #432: 7 | 7
Yuriy Lykhusha | #420: 42; #422: 33; #424: 29; #426: 19; #428: 40; #430: 55; #432: 90 | 37
Sprint Goal KR Focused Effort
Note on A31: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A39: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on H17: commit 33 effort total 55 effort into sprint done 33 effort
Note on I17: commit 52 done 47
Note on J17: commit 110 done 110
Note on J19: 8 effort removed from sprint
Note on J30: deployment goal is changed to AR
Note on K17: commit 65 done 65
Note on K19: 1 effort reduced from a task
Note on K30: canvas task was failed
Note on L17: committed 75 done 75
Note on M17: commit 47 done 38
Note on N17: commited 38 done 38
Note on O17: committed 109 done 88 rate 80%
Note on P17: committed 70 done 60 rate %80
Note on P30: Deployment of template lib is failed
Note on Q17: committed 81 done 50 rate %60
Note on S17: commited 34 done 21 rate 61%
Note on T17: committed 34
Note on U17: committed 75 done 75

## Minerva
Minerva
Quarter | Q1 | [5 empty] | Q2 | [6 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 04.01 - 18.01 | 18.01 - 02.02 | 02.02 - 16.02 | 16.02 - 01.03 | 01.03 - 15.03 | 15.03 - 29.03 | 29.03 - 05.04 | 15.04 - 26.04 | 26.04 - 10.05 | 10.05 - 24.05 | 24.05 - 07.06 | 07.06 - 20.06 | 20.06 - 04.07 | 04.07 - 19.07 | 19.07 - 02.08 | 02.08 - 16.08 | 16.08 - 30.08 | 30.08 - 13.09 | 13.09 - 27.09 | 27.09 - 11.10 | 11.10 -
Sprint Name | Pluto the Planet | Cosmic Cuddles | Celestial Acceleration | Meteorite Momentum | Interstellar Innovation | Galactic Odyssey | Stellar Feast Candy | Astral Adventures | Galactic Conversations | Quantum Quests | Black Hole Breakthrough | Cosmos Blaze | Starlight Dash | Galaxy Gateway | Lunar Leap | Aurora Amore | Stellar Voyage | Solar Flare | Stellar Symphony | Luna Solstice | Nova Nexus
Total Effort In the Sprint | 132 | 152 | 156 | 184 | 190 | 181 | 127 | 243 | 227 | 260 | 248 | 210 | 234 | 246 | 247 | 175 | 220 | 218 | 250 | 263 | 282 | 0 | 0 | 0 | 0 | 0
Commited | 126 | 152 | 156 | 167 | 190 | 178 | 127 | 240 | 214 | 259 | 241 | 189 | 234 | 233 | 242 | 165 | 207 | 218 | 242 | 260 | 274
Commited KR Effort | [19 empty] | 141 | 207
Emerged | 6 | 0 |  | 17 | 0 | 3 | 0 | 3 | 13 | 1 | 7 | 21 | 0 | 13 | 5 | 10 | 13 | 0 | 8 | 3 | 8
Emerged Rate | 4.545% | 0% | 0% | 9.239% | 0% | 1.657% | 0% | 1.235% | 5.727% | 0.3846% | 2.823% | 10% | 0% | 5.285% | 2.024% | 5.714% | 5.909% | 0% | 3.2% | 1.141% | 2.837% | 0% | 0% | 0% | 0% | 0%
Done Bug Effort | 0 | 0 | 0 | 14 | 26 | 24 | 0 | 5 | 0 | 16 | 4 | 0 | 13 | 0 | 5 | 5 | 0 | 0 | 13 | 3 | 3
Commited Bug Effort | 0 | 0 | 0 | 8 | 26 | 21 | 0 | 5 | 0 | 16 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0
Emerged Bug Effort | 0 | 0 | 0 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 8 | 3 | 3
Done Pool Effort | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Done Pool Bug Effort | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dev Tasks Done Effort | 111 | 139 | 135 | 163 | 190 | 181 | 127 | 222 | 201 | 239 | 245 | 189 | 205 | 222 | 247 | 175 | 212 | 204 | 224 | 221
All Tasks Done Effort | 111 | 139 | 135 | 163 | 190 | 181 | 127 | 222 | 201 | 239 | 245 | 189 | 205 | 222 | 247 | 175 | 212 | 204 | 224 | 221
Released Effort
Undone PBI Effort | 21 | 13 | 21 | 21 | 0 | 0 | 0 | 21 | 26 | 21 | 0 | 21 | 29 | 39 | 0 | 0 | 8 | 14 | 26 | 42
Comitted Releasable Dev Tasks
Sprint Goal | Implement wait decision & finalize filling starter elements prompt | Implement combined segments & complete tasks for filled elements | Releasing starter and wait element contents, completing smarter check interactions research | Releasing smart placement of Check Conditions/Interaction elements on journey structure, finalize prototype for Check Conditions content, iterate wait element contents | Releasing content for Check Condition and Check Interaction elements & Refining Starter Element prompt as a prototype | Release Revised Starters, Complete Prompt Iterations for Check and Wait Elements | Releasing Smart Journey Iterations (Wait & Price-drop) and Completing Actionable Insights Data Flow Research | Actionable Insights Q&A Research and Smart Journey Check Elements Improvements | - Completing Smart Journey Iterations - Releasing Journey Reasoning - Improving the Actionable Insights Prototype | Completing Insights Assistant Tech Design and Journey Edit Tech Design & Researches | Research for Journey Edit Mode and Insight Assistant + GPT-4o Support | Insight Assistant Research, Journey Edit Intent Detection, Smart Segment Multi-segment | - Deploying semi-functional Conversational Journey Endpoint - Functioning data prompt builder for Insight Assistant | Functional Insights Assistant Endpoint & Functional Conversational Journey Edit Actions | Fully Working Insights Assistant - Fully Working Conversational Journey with no FE Block | Finalizing the Development of Conversation Journey KR | Performance focused prompt engineering for all Smart Journey prompts | Improving Smart Journey & Initializing Content Generation | Implementing the Conversational Journey Content Phase | Query Generation Prototype Finalization | Completing Tech Designs and Product Data Integration Research
Goal Achieved (0/1) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 88.1% | 91.45% | 86.54% | 97.6% | 100% | 101.7% | 100% | 92.5% | 93.93% | 92.28% | 101.7% | 100% | 87.61% | 95.28% | 102.1% | 106.1% | 102.4% | 93.58% | 92.56% | 85% | 0% | 0% | 0% | 0% | 0% | 0%
Bug/Development Ratio | 0% | 0% | 0% | 8.589% | 13.68% | 13.26% | 0% | 2.252% | 0% | 6.695% | 1.633% | 0% | 6.341% | 0% | 2.024% | 2.857% | 0% | 0% | 5.804% | 1.357% | 0% | 0% | 0% | 0% | 0% | 0%
Shipping Accuracy | 88.1% | 91.45% | 86.54% | 97.6% | 100% | 101.7% | 100% | 92.5% | 93.93% | 92.28% | 101.7% | 100% | 87.61% | 95.28% | 102.1% | 106.1% | 102.4% | 93.58% | 92.56% | 85% | 0% | 0% | 0% | 0% | 0% | 0%
Partner Focus
Bug Score
Planned Sprint KR Effort (%) | [19 empty] | 54.23% | 75.55%
Sprint Goal KR Effort (%) | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 33% | 53% | 57.05% | 53.29% | 34.21% | 42.7% | 37.01% | 47.92% | 41.59% | 37.45% | 42.32% | 40.21% | 34.62% | 41.63% | 42.56% | 36.36% | 59.42% | 37.16% | 38.84% | 39.23% | 44.89%
Sprint Dev Participation | 4 | 5 | 4 | 5 | 5 | 5 | 0 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 6 | 0 | 0 | 0 | 0 | 0
Sprint Goal Dev Participation | 2 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 3 | 4 | 5 | 5 | 3 | 4 | 4 | 4 | 4 | 3
Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Advanced Sprint Goal Success | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 15% | 15% | 15% | 15% | 15%
Updated A. Sprint Goal Success | [13 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Individual Committed Effort
Alper Demirel | - | - | 0 | 18 | 33 | 34 |  | 31 | 34 | 34 | 39 | 26 | 37 | 44 | 50 | 26 | 32 | 35 | 50 | 47 | 43
Ceren Güzelgün | 42 | 42 | 50 | 39 | 36 | 42 |  | 47 | 34 | 34 | 47 | 29 | 42 | 34 | 29 | 34 | 42 | 40 | 35 | 26 | 42
Çağla Özen | 25 | 34 | 37 | 34 | 36 | 34 |  | 34 | 28 | 32 | 36 | 27 | 39 | 32 | 37 | 0 | 34 | 36 | 34 | 44 | 42
Deniz Parmaksız | 6 | 8 | 1 | 0 | 7 | 0 |  | 26 | 10 | 34 | 2 | 5 | 0 | 0 | 0 | 8 | 0 | 0 | 27 | 19 | 0
Didem Makaroğlu | - | - | - | - | 0 | 0 |  | 34 | 34 | 42 | 39 | 34 | 35 | 42 | 42 | 34 | 34 | 29 | 20 | 42 | 55
Muratcan Ünsal | 27 | 34 | 34 | 34 | 39 | 34 |  | 34 | 40 | 49 | 44 | 34 | 34 | 50 | 50 | 26 | 26 | 42 | 40 | 43 | 50
Şeyma Çavdar | 26 | 34 | 34 | 42 | 39 | 34 |  | 34 | 34 | 34 | 34 | 34 | 47 | 31 | 34 | 37 | 39 | 36 | 36 | 39 | 42
Ezgi Adıgüzel
Emre Öney
Individual Done Effort
Alper Demirel | - |  | 0 | 18 | 33 | 34 |  | 31 | 34 | 34 | 39 | 26 | 29 | 44 | 50 | 26 | 32 | 22 | 45 | 47
Ceren Güzelgün | 21 | 42 | 32 | 18 | 36 | 45 |  | 47 | 34 | 34 | 47 | 29 | 21 | 13 | 29 | 34 | 47 | 39 | 43 | 26
Çağla Özen | 25 | 34 | 34 | 34 | 36 | 34 |  | 34 | 28 | 32 | 36 | 27 | 39 | 29 | 37 | 0 | 34 | 36 | 34 | 44
Deniz Parmaksız | 10 | 8 | 1 | 14 | 7 | 0 |  | 29 | 10 | 35 | 4 | 5 | 0 | 0 | 5 | 18 | 0 | 0 | 14 | 19
Didem Makaroğlu | - | - | - | - | 0 | 0 |  | 34 | 34 | 42 | 39 | 34 | 35 | 42 | 42 | 34 | 34 | 29 | 12 | 42
Muratcan Ünsal | 24 | 21 | 34 | 34 | 39 | 34 |  | 13 | 27 | 28 | 46 | 34 | 34 | 50 | 50 | 26 | 26 | 42 | 40 | 1
Şeyma Çavdar | 31 | 34 | 34 | 45 | 39 | 34 |  | 34 | 34 | 34 | 37 | 34 | 47 | 44 | 34 | 37 | 39 | 36 | 36 | 42
Ezgi Adıgüzel
Emre Öney
Sprint Goal KR Focused Effort
PO Happiness | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 0 | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Team Happiness | 100% | 14.29% | 100% | 75% | 100% | 87.5% | 100% | -11.11% | 75% | 77.78% | 100% | 100% | 33.33% | 100% | 100% | 100% | 37.5% | 87.5% | -22.22% | 66.67%
Team Happiness about PM | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Team Members
Alper Demirel | - | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1
Ceren Güzelgün | 1 | - | 1 | 0 | 1 | 1 | 1 | -1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | - | 0 | 1 | 0 | 1
Çağla Özen | 1 | 0 | 1 | 1 | - | 1 | 1 | 0 | 1 | 1 | 1 | - | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1
1
Deniz Parmaksız | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | - | - | - | 0 | 0
Didem Makaroğlu | - | - | - | - | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1
Emre Öney | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | -1 | 1
Ezgi Adıgüzel | 1 | 0 | 1 | 0 | 1 | - | - | -1 | 1 | 1 | 1 | - | 1 | 1 | 1 | - | -1 | 1 | -1 | -1
Muratcan Ünsal | 1 | 0 | 1 | 1 | 1 | 1 | 1 | -1 | -1 | -1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1
Ozan Kızılkaya | 1 | -1 | - | 1 | 1 | 0 | 1 | 0 | -
Şeyma Çavdar | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1
Note on A25: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A36: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on B63: Ceren: 1 (güzel sprintti) Çağla: 1 (aynen) Ezgi: 1 Murat: 1 (security taskları da iyiydi) Ozan: 1 Şeyma: 1 -Ceren Guzelgun
Note on C67: İlk sprintimdi güzeldi her şey -Deniz Parmaksız
Note on C69: Çok şey öğrendim ama nötrüm -Deniz Parmaksız
Note on C71: Sprint sonu sıkıştı ancak goal çıktı, roadmap'e uygun gidiyoruz, çıktılar güzel. -Deniz Parmaksız
Note on C74: Sprint sonu test sıkışlığı -Deniz Parmaksız
Note on C75: Taskın fail olması, yoksa rahat 1di -Deniz Parmaksız
Note on C76: Sprint güzeldi ama takıma katkı sağlayamadım gibi -Deniz Parmaksız
Note on C77: Yetişti ama sıkıştıve yetişsin diye stres yaptım -Deniz Parmaksız
Note on D64: güneş yerinde her şey yolunda -Ceren Guzelgun
Note on D67: hızlı bi sprint oldu, ama öğreticiydi -Ceren Guzelgun
Note on D68: kişisel 0 takıma 1 -Ceren Guzelgun
Note on D69: ceren +1 -Ceren Guzelgun
Note on D71: slay bi sprintti ;)) -Ceren Guzelgun
Note on D74: olaysız bi sprintti, ekip olarak iyiyiz <3 -Ceren Guzelgun
Note on D75: etkisi olan tasklar yapmak güzel -Ceren Guzelgun
Note on D77: önemli feature'lar çıkardık, herkesin eline sağlık -Ceren Guzelgun
Note on E62: Burçin: 1 güzel karşılandım <3 -Ceren Guzelgun
Note on E64: burçin hoşgeldi <3 -Ceren Guzelgun
Note on E67: efso sprintti, çok şey öğrendim -Ceren Guzelgun
Note on E68: kişisel sprint -Ceren Guzelgun
Note on E74: taskım ilerlemediği için 0 -Ceren Guzelgun
Note on E75: yorucuydu ama güzeldi -Ceren Guzelgun
Note on E76: güzel sprint oldu, testler ilerledi -Ceren Guzelgun
Note on E77: murat +1 -Ceren Guzelgun
Note on F62: Burçin: 1 biraz daha detaya girdim Cansu: 1 Burçin'in olması müko -Ceren Guzelgun
Note on F67: yoğun ve öğretici bir sprintti -Ceren Guzelgun
Note on F68: mük -Ceren Guzelgun
Note on F71: sprint goal'ü önceden planlasak iyi olurdu, ama güzel sprintti -Ceren Guzelgun
Note on F72: güzel sprint -Ceren Guzelgun
Note on F75: yorucuydu ama tasklar çıktı -Ceren Guzelgun
Note on F76: güzel sprintti genel olarak -Ceren Guzelgun
Note on F77: herkesin eline sağlık -Ceren Guzelgun
Note on G62: Burçin: 1 güzeldi Cansu: 1 -Ceren Guzelgun
Note on G64: Deniz: Toplu KR grooming için ön hazırlık iyi olurdu -Ceren Guzelgun
Note on G67: İlk prototype taskımı aldım, güzeldi -Ceren Guzelgun
Note on G68: olaysız sprintti, okeiz -Ceren Guzelgun
Note on G69: benim için olaylıydı ama güzeldi :D -Ceren Guzelgun
Note on G71: herkesin eline sağlık -Ceren Guzelgun
Note on G72: öğretici ve güzel sprintti -Ceren Guzelgun
Note on G75: öğretici bir sprintti -Ceren Guzelgun
Note on G76: sprintte aktif olduğumu düşünmüyorum -Ceren Guzelgun
Note on G77: dörtlü pair güzeldi -Ceren Guzelgun
Note on I62: sprint biraz sona sıkıştı -Ceren Guzelgun 1'e daha yakınım -Ceren Guzelgun
Note on I64: promptların hazır olması güzeldi, qa tarafında çabuk aksiyon alındı, teşekkürler ediyoruz -Ceren Guzelgun
Note on I67: benim açımdan güzel sprintti, ama aksiyon bakımından zayıf kaldım. (sprint goal) -Ceren Guzelgun
Note on I68: sprint goal -Ceren Guzelgun
Note on I69: kişisel olarak iyiydi, ama goal fail -Ceren Guzelgun
Note on I71: çıktı olarak iyiydi ama goal fail -Ceren Guzelgun
Note on I72: güzel pair olduk, çıktılar iyi bi sprintti. goal'ün fail olmasına üzüldüm -Ceren Guzelgun
Note on I74: goal + sıkıntılı taskım -Ceren Guzelgun
Note on I75: goal fail, sprint de iyi değildi -Ceren Guzelgun
Note on I76: aynı sebepler -Ceren Guzelgun
Note on I77: kişisel iyi sprintti, goal sıkıntı oldu. fail olan taskla ilgili elimden geleni yaptım -Ceren Guzelgun
Note on J75: önceki sprintte kalan task sıkıntılı oldu -Ceren Guzelgun
Note on K62: Burçin: 1 yoğun bi sprintti, bol context switchli Cansu: 1 Same Same -Ceren Guzelgun
Note on K64: şeyma: burçin'e teşekkürlerimi iletiyorum ezgi: kalpli 1ler -Ceren Guzelgun
Note on K67: güzel bi sprintti -Ceren Guzelgun
Note on K69: farklı tasklar almak iyiydi -Ceren Guzelgun
Note on K71: 0-1 arasındaydım, okr belirsizlikleri sebepli -Ceren Guzelgun
Note on K72: yoğun ama faydalı bi sprintti -Ceren Guzelgun
Note on K74: yorucu bi sprintti ama güzeldi -Ceren Guzelgun
Note on K75: bi kaç sprinttir task kalıyor -Ceren Guzelgun
Note on L62: güzel sprintti, çıktılar -Ceren Guzelgun
Note on L64: teşekkürler ediyoruz <3 -Ceren Guzelgun
Note on L67: reviewler son güne kaldı, sprint sonu yoğundu -Ceren Guzelgun
Note on L68: alper +1 -Ceren Guzelgun
Note on L69: güzel sprintti -Ceren Guzelgun
Note on L71: task kalmadı, iyi çıktılı bir sprintti -Ceren Guzelgun
Note on L72: yoğun ve güzel bi sprintti -Ceren Guzelgun
Note on L73: daha aktif rol aldığım bir sprintti -Ceren Guzelgun
Note on L74: tasklar iyi dağıldı, yüküm azaldı <3 -Ceren Guzelgun
Note on L75: tüm tasklar çıktı güzel sprintti -Ceren Guzelgun
Note on L77: güzel bir sprintti -Ceren Guzelgun
Note on M62: hepinize katılmaca -Ceren Guzelgun
Note on M67: kısa ama faydalı sprintti -Ceren Guzelgun
Note on M68: alper +1 -Ceren Guzelgun
Note on N62: Servis olmadığı için task'lara uzak hissettim -Burcin Dikbasan
Note on N67: Sprinte kendini veremedi -Burcin Dikbasan
Note on N68: çıktıları iyiydi ama zor bir sprint oldu -Burcin Dikbasan
Note on N71: yoğun ve frustrated bir sprintti ama daha iyi olabilirdi -Burcin Dikbasan
Note on N74: QA süreçleri güzel ilerledi -Burcin Dikbasan
Note on N75: çıktılar güzeldi ama yorucuydu -Burcin Dikbasan
Note on O78: Özetle, yoğun, öğretici ve güzel bir sprintti -Alper Demirel
Note on P67: dolu bir sprintti, hep birlikte başardık -Ceren Guzelgun
Note on P68: alper +1 -Ceren Guzelgun
Note on P69: alper +1 -Ceren Guzelgun
Note on P71: yoğun bir sprintti, bekliyorduk da. ona rağmen iyi hallettik -Ceren Guzelgun
Note on P72: yoğun ve iyi bir sprintti -Ceren Guzelgun
Note on P73: iyi sprintti, ama testler son günlere fazla yığıldı -Ceren Guzelgun
Note on P74: yorucu ama dolu sprintti. emre + 1 -Ceren Guzelgun
Note on P75: yorumlara katılıyorum -Ceren Guzelgun
Note on P77: herkese +1 -Ceren Guzelgun
Note on Q69: 1 demise takımdan linç yiyeceği için 1 dedi -Burcin Dikbasan
Note on Q75: yoğundu ama güzeldi -Burcin Dikbasan
Note on R68: Beklenmedik bir sprint -Alper Demirel
Note on R69: Sprint dışı sebebi ile -Alper Demirel
Note on R72: Başı ile sonu planlanandan biraz farklı bir sprint, sonunda bir şeyler çıktı -Alper Demirel
Note on R73: Çok QA eforu yoktu -Alper Demirel
Note on R74: Otomasyon testlerinde eksik kaldık -Alper Demirel
Note on R77: Tasklar yorucu idi, daha güzel sprintler olduğundan 1'e yazık olmasın istedi -Alper Demirel
Note on S67: öyle :) -Ceren Guzelgun
Note on S72: öyle +1 -Ceren Guzelgun
Note on S75: dümdüz sprintti -Ceren Guzelgun
Note on T62: burçin: 1 çıktılar iyiydi, elinize sağlık <3 cansu: 1 partner issues + actionable <3 -Ceren Guzelgun
Note on T64: deniz: kr monitoring için teşekkürler -Ceren Guzelgun
Note on T67: kişisel commitleri daha dikkatli verebilirim + yoğun sprintti -Ceren Guzelgun
Note on T71: operasyonel eksiklikler (test-preprod) -Ceren Guzelgun
Note on T72: task ilerlemedi -Ceren Guzelgun
Note on T73: son günlerde çok task yığıldı -Ceren Guzelgun
Note on T74: son güne yığılma +1 -Ceren Guzelgun
Note on T75: çıkan problemler + hotfixler -Ceren Guzelgun
Note on T77: goaller çıktı ama bahsedilen sıkıntılar. yorucu sprintti -Ceren Guzelgun
Note on U62: güzel sprintti ellere sağlık -Ceren Guzelgun
Note on U67: güzel, sakin bir sprint -Ceren Guzelgun
Note on U69: öğretici bir sprintti -Ceren Guzelgun
Note on U71: sprint genel olarak iyiydi, accuracyden dolayı. -Ceren Guzelgun
Note on U72: iletişimimiz iyiydi, güzel yürüdü -Ceren Guzelgun
Note on U73: fazla yoğun bir sprint değildi ellere sağlık -Ceren Guzelgun
Note on U74: pr'ımı açamadım, tasklar ilerleyemedi -Ceren Guzelgun
Note on U75: task kaldı, ama benim için öğretici bir sprintti -Ceren Guzelgun
Note on U77: pair ve insight tarafına girmek güzeldi -Ceren Guzelgun

## Valorem
Valorem
Quarter | Q1 | [5 empty] | Q2 |  |  |  |  | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April | May |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 04 JAN - 17 JAN | 18 JAN - 31 JAN | 01 FEB - 14 FEB | 15 FEB - 29 FEB | 01 MAR - 14 MAR | 15 MAR - 28 MAR | 29 MAR - 25 APR | 26 Apr - 09 MAY | 10 MAY - 23 MAY | 24 MAY - 13 JUN | 13 JUN - 05 JUL | 05 JUL - 18 JUL | 19 JUL - 01 AUG | 02 AUG-15 AUG | 16 AUG - 29 AUG | 01 SEP - 12 SEP | 13 SEP - 26 SEP | 27 SEP - 10 OCT | 11 OCT - 26 OCT
Sprint Name | uyudun mu? | ben uyumadım da.. | Aleyküm Slay Fırfır💅 | Rızzık Zamanı Valohan | we💜u Aysun | Dolu Dolu Valorem 🕋 | Vol #63 | Vol #64 | Vol #65 | Vol #66 | Vol #67 | Vol #68 | Vol #69 | Vol #70 | IremBehind 🤯 | Finduk In Europe | Vol #73 Notification Center🔔 | Vol #74: Canın Sağ Olsunnn 🚬 | Vol #75: Limit Makarası🪝
Total Effort In the Sprint | 159 | 147 | 189 | 240 | 309 | 340 | 330 | 375 | 273 | 399 | 354 | 303 | 288 | 190 | 288 | 297 | 272 | 256 | 244 | 0 | 0 | 0 | 0 | 0
Commited | 144 | 138 | 164 | 227 | 300 | 325 | 214 | 342 | 263 | 373 | 338 | 285 | 280 | 174 | 267 | 246 | 232 | 227 | 244 | 0 | 0 | 0 | 0 | 0
Emerged | 15 | 9 | 25 | 13 | 9 | 15 | 116 | 33 | 68 | 30 | 16 | 18 | 8 | 16 | 21 | 51 | 40 | 29 | 0 | 0 | 0 | 0 | 0 | 0
Emerged Rate | 9.434% | 6.122% | 13.23% | 5.417% | 2.913% | 4.412% | 35.15% | 8.8% | 24.91% | 7.519% | 4.52% | 5.941% | 2.778% | 8.421% | 7.292% | 17.17% | 14.71% | 11.33% | 0% | 0% | 0% | 0% | 0% | 0%
Done Bug Effort | 16 | 19 | 29 | 17 | 31 | 31 | 67 | 35 | 21 | 35 | 17 | 8 | 0 | 12 | 10 | 26 | 9 | 10
Commited Bug Effort | 13 | 14 | 20 | 17 | 25 | 22 | 33 | 31 | 19 | 29 | 9 | 8 | 0 | 7 | 7 | 13 | 7 | 8
Emerged Bug Effort | 3 | 8 | 9 | 3 | 6 | 14 | 42 | 4 | 10 | 6 | 8 | 0 | 0 | 5 | 3 | 13 | 2 | 10
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 100 | 101 | 140 | 109 | 131 | 122 | 166 | 150 | 124 | 191 | 141 | 98 | 117 | 132 | 172 | 134 | 164 | 112 | 0 | 0 | 0 | 0 | 0 | 0
All Tasks Done Effort | 147 | 109 | 174 | 220 | 268 | 268 | 237 | 341 | 186 | 296 | 249 | 239 | 223 | 161 | 248 | 226 | 211 | 188 | 0 | 0 | 0 | 0 | 0 | 0
Released Effort | 27 | 31 | 72 | 30 | 26 | 69 | 106 | 68 | 81 | 57 | 89 | 37 | 44 | 85 | 172 | 123 | 141 | 74
Undone PBI Effort | 12 | 38 | 15 | 20 | 41 | 72 | 93 | 53 | 98 | 103 | 105 | 56 | 65 | 29 | 40 | 71 | 68 | 68 | 244 | 0 | 0 | 0 | 0 | 0
Comitted Releasable Dev Tasks
Sprint Goal | Solving blocker tasks for Enigma Implementation (PA-24929 & PA-24917) | - Completing OSA & Export Fixes for Enigma Implementation & Conducting QA Camp - Completing Incident Actions | Enigma Feature Flag Ready to Live | Enabling Enigma Transition at least 1 Partner in Live & Completing GLA for HP, OSA & Recurring Export | Resolving Performance Issues & Live for Small & Semi-Enterprise & GLA Single Export and QA Camp | Enigma Live for Long-tail & Semi-Enterprise & GLA QA Camp Fixes, Regression Cases and Live for SIA & Solving Enigma BI Blockers | Enigma Live for All Partners & Hit-Based Impressions Development, QA Tasks & Export Design & Architect Enigma Blockers | Hit-Based QA Tasks & Completing Usage Analytics & Mobile Card Enigma Transition & Removing Enigma Blockers for Email, DWH & Security | Completing Hit-Based Development e2e & Event Conversion: Collecting Purchase Events and Completing Basic Structure for Attribution Engine | Hit-Based Live & Event Conversion System Testable (Released) & Overall Analytics Micro FE Ready for Release | Being Ready for full Product Implementation for Overall Analytics (Components Live & Initial BE Structure Completed) | Moving edit modal to MicroFE Overall Analytics Webpush, Whatsapp, SMS BE Event Conversion Setup, Campaign Analysis | Overall Analytics: FE webpush ve onsite canlıya alınması, BE Email & Subscriber tamamlanması. Event Conv: Streamingin başlaması. | Event conversion: yeni serviste data geldiğini görebilmek, purchase eventlerini storelamak Overall Analytics: Whatsapp, SMS, Email FE live, BE Architect journey | Overall Analytics: Architect, Subscriber, Metric Card Graph live all, all metrics need to be consistent FE&BE, Export Event Conversion: Test env readiness, data streaming will be started. | Overall Analytics: Buglar, QA camp & Save as default Event Conversion: Load Test for Data Streaming & Attribution Engine For: SMS Email WhatsApp | Overall Analytics: Qa Camp çıktılarının tamamlanması, Side menu'ye eklenmesi, feature flag, X beta partnere açılması. Event Conversion: Load testte çıkan sorunların giderilmesi, test env kurulum tamamlanması, data serving başlanması | Event Conversion: Sms, whatsapp, email Dry Run completion, Overall Analytics: Web push subscriber metric update Hit Based Click Impression: Panel&Enigma log type add | Event Conversion: Completing E2E tests. Usage Analytics Monthly/Yearly: Load test, Pre-incident management, component fe readiness
Goal Achieved (0/1) | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 102.1% | 78.99% | 106.1% | 96.92% | 89.33% | 82.46% | 110.7% | 99.71% | 70.72% | 79.36% | 73.67% | 83.86% | 79.64% | 92.53% | 92.88% | 91.87% | 90.95% | 82.82% | 0% | 0% | 0% | 0% | 0% | 0%
Bug/Development Ratio | 16% | 18.81% | 20.71% | 15.6% | 23.66% | 25.41% | 40.36% | 23.33% | 16.94% | 18.32% | 12.06% | 8.163% | 0% | 9.091% | 5.814% | 19.4% | 5.488% | 8.929% | 0% | 0% | 0% | 0% | 0% | 0%
Shipping Accuracy | 27% | 30.69% | 51.43% | 27.52% | 19.85% | 56.56% | 63.86% | 45.33% | 65.32% | 29.84% | 63.12% | 37.76% | 37.61% | 64.39% | 100% | 91.79% | 85.98% | 66.07% | 0% | 0% | 0% | 0% | 0% | 0%
Partner Focus
Bug Score
Sprint Goal KR Effort (%) | [14 empty] | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | bar: Vol #63 to Vol #70
Sprint Goal Effort (%) | 12.5% | 9.4% | 44% | 46% | 20% | 30% | 41% | 31% | 18% | 14% | 27% | 36% | 53% | 51% | 50% | 32% | 48% | 34% | 29% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 85% | 85% | 100% | 100% | 15% | 100% | 100% | 100% | 15% | 15% | 85% | 100% | 30% | 100% | 100% | 100% | 30% | 30% | 15% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [6 empty] | Vol #68: 100%; Vol #69: 30%; Vol #70: 100% | 100% | 100% | 30% | 30%
Individual Committed Effort
Mert Kanber | 45 | 45 | 45 | 44 | 50 | 58 | 47 | 45 | 45 | 56 | 37 | 39 | 50 | 21 | 45 | 45 | 41 | 41 | 50
Ömer Faruk Olcay | 13 | 13 | 62 | 54 | 43 | 56 | 53 | 43 | 49 | 55 | 18 | 33 | 38 | 37 | 41 | 43 | 47 | 51 | 51
Ulaş Kılıç | 48 | 46 | 47 | 12 | 51 | 54 | 60 | 53 | 23 | 55 | 58 | 34 | 36 | 30 | 51 | 51 | 31 | 23 | -
Özkan Meşe | 38 | 34 | 10 | 33 | 41 | 31 | 42 | 39 | 23 | 38 | 39 | 27 | 32 | 19 | 37 | 11 | 41 | 39 | 40
Irem Özdemir | 0 | 42 | 34 | 34 | 37 | 29 | 55 | 47 | 32 | 42 | 39 | 34 | 37 | 26 | 13 | - | - | - | -
Buse Balkan | 34 | 39 | 34 | 29 | 34 | 39 | 36 | 34 | 8 | 34 | 37 | 37 | 34 | 21 | 26 | 34 | 26 | 31 | 34
Esra Bozoklu | 17 | 16 | 9 | 16 | 14 | 18 | 37 | 22 | 19 | 34 | 32 | 31 | 8 | 14 | 17 | 19 | 26 | 18 | 21
Talha Akpınar | 9 | 10 | 4 | 5 | 11 | 9 | 5 | 9 | 10 | 13 | 13 | 13 | 8 | 6 | 3 | 11 | 3 | 3 | 5
Vesile Baloğlu | - | - | - | - | 19 | 26 | 32 | 29 | 13 | 31 | 48 | 21 | 24 | 13 | 16 | 21 | 8 | 16 | 8
Merve Övüt | - | - | - | - | - | 5 | 6 | 11 | 7 | 13 | 17 | 16 | 13 | 13 | 13 | 11 | 16 | 5 | 16
Individual Done Effort
Mert Kanber | 47 | 45 | 46 | 53 | 37 | 46 | 21 | 37 | 45 | 47 | 30 | 39 | 45 | 21 | 41 | 54 | 52 | 41
Ömer Faruk Olcay | 18 | 13 | 75 | 57 | 30 | 59 | 48 | 46 | 46 | 56 | 13 | 30 | 41 | 37 | 51 | 35 | 57 | 51
Ulaş Kılıç | 46 | 38 | 51 | 13 | 48 | 43 | 77 | 57 | 23 | 51 | 54 | 32 | 4 | 23 | 56 | 41 | 22 | 15
Özkan Meşe | 36 | 13 | 2 | 29 | 41 | 24 | 55 | 40 | 12 | 39 | 44 | 14 | 32 | 22 | 37 | 14 | 46 | 26
Irem Özdemir | 8 | 42 | 34 | 34 | 37 | 29 | 55 | 47 | 32 | 42 | 39 | 34 | 37 | 26 | 13 | - | - | -
Buse Balkan | 34 | 39 | 34 | 29 | 34 | 39 | 41 | 34 | 8 | 29 | 26 | 29 | 34 | 21 | 26 | 34 | 26 | 31
Esra Bozoklu | 8 | 8 | 9 | 5 | 11 | 10 | 26 | 15 | 4 | 8 | 10 | 18 | 0 | 13 | 3 | 16 | 5 | 16
Talha Akpınar | 0 | 5 | 4 | 0 | 3 | 3 | 2 | 1 | 10 | 18 | 0 | 13 | 5 | 3 | 0 | 5 | 0 | 0
Vesile Baloğlu | - | - | - | - | 27 | 13 | 29 | 16 | 0 | 5 | 27 | 26 | 24 | 0 | 21 | 21 | 0 | 8
Merve Övüt | - | - | - | - | - | 2 | 3 | 11 | 0 | 1 | 1 | 11 | 0 | 13 | 0 | 6 | 3 | 0
Sprint Goal KR Focused Effort
PO Happiness | 1 | 1 | 1 | 1 | -1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0
Team Happiness | 0 | 0 | 1 | -1 | 0 | -1 | -1 | 1 | -1 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | -1
Team Happiness about PM | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0
|  | Q1'24 | Q2'24 | Q3'24 | Q4'24 | Overall
| Mert Kanber | 274 | 180 | 252 | 93 | 799
| Ömer Faruk Olcay | 252 | 209 | 251 | 108 | 820
| Ulaş Kılıç | 239 | 262 | 178 | 37 | 716
| Özkan Meşe | 145 | 190 | 165 | 72 | 572
| Irem Özdemir | 184 | 215 | 110 | 0 | 509
| Buse Balkan | 209 | 138 | 170 | 57 | 574
| Esra Bozoklu | 51 | 63 | 55 | 21 | 190
| Talha Akpınar | 15 | 31 | 26 | 0 | 72
| Vesile Baloğlu | 40 | 77 | 92 | 8 | 217
| Merve Övüt | 2 | 16 | 33 | 3 | 54
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on B37: On Leave - 6 Working Days -Ömer Faruk Olcay
Note on B61: Aysun: 0 - Değişim yok Deniz: 1 - Goal rahat geçti -Ömer Faruk Olcay
Note on B62: Esra: 0 - Yorum yok Mert: 0 - Yorum yok Olcay: 0 - Sıkıntıları not ettim İrem: 0 - Hastaydım sprintten uzaktım Özkan: 0 - Problemlerle çok boğuşma oldu, birbirimize sahip çıktık Talha: 0 - Güzel, geçen sprinte göre iyiydik Buse: 0 - Ekstra bi yorumum yok Barış: 0 - Taskım yoktu Ulaş: 1 - Her şey ortada -Ömer Faruk Olcay
Note on B63: Esra: 0 - Ekstra bişe yok Mert: 1 - Denize 1, Aysuna 0 Olcay: 0 - Çok fazla yoktum İrem: 0 - Çok fazla yoktum Özkan: 0 - Yorumsuz Talha: 0 - Yani, bi fark yok Buse: 1 - Denizle çok çalıştık, iletişim iyi Barış: 1 - Task yoktu, ama dışardan iyidi Ulaş: 0 - Ekstra bi olay olmadı -Ömer Faruk Olcay
Note on C37: On Leave - 6 Working Days -Ömer Faruk Olcay
Note on C39: death leave -Ozkan Mese
Note on C61: Aysun: 0 - Geçen sprint ile aynı Deniz: 1 - QA tasklardan ötürü -Ömer Faruk Olcay
Note on C62: Esra: 1 - O bug taskı olmadı Mert: 0 - İyileşme göremedim Olcay: 0 - Planningde hatalar vardı İrem: 0 - Ekstram yok Özkan: ! - Ben AFK Talha: 0 - Yorumsuzum Buse: 1 - Güzel geçti Barış: 0 - Ekstram yok Ulaş: 0 - Ortalama bi sprintti -Ömer Faruk Olcay
Note on C63: Esra: 1 - Deniz'in ownershipliği iyiydi Mert: 0 - Yorumsuzum Olcay: 1 - Alignment hızlıydı İrem: 1 - E-nabız destekleri Özkan: ! - Ben AFK Talha: 1 - Fast response Buse: 1 - Yakın çalışma ortamı Barış: 1 - Aysun'un Guild hırsı ve Deniz'in basit anlatımları Ulaş: 1 - Yorumsuzum -Ömer Faruk Olcay
Note on D39: On Leave - 4 Working Days -Ömer Faruk Olcay
Note on D61: Aysun: 1 - Genel pozitifti Deniz: 1 - Aysun ne dediyse imza -Ömer Faruk Olcay
Note on D62: Esra: 1 - teşekkürler Mert: 1 - genel iyiydi Olcay: 1 - iyiye giden şeyler var İrem: 0 - nötr geçti Özkan: 0 - bi tık uzatı Talha: 1 - discorddaki vs. genel ekip içi communication vs. verimliydi Buse: 1 - yani ekipçe keyifliydik Barış: ! Ulaş: 1 - hızlıydık, bunun normalimiz olması lazım -Ömer Faruk Olcay
Note on D63: Esra: 1 - sprint içi takip iyiydi Mert: 0 - ekstra bi +- durum oluşmadı Olcay: 0 - ekstra bi +- durum oluşmadı İrem: 0 - ekstra bi +- durum oluşmadı Özkan: 1 - alignment etkiliydi Talha: 1 - pozitif enerji yaydılar Buse: 1 - özellikle denizle sıkı iletişim oldu Barış: 1 - yardımcı olundu fazlaca Ulaş: 1 - enerci -Ömer Faruk Olcay
Note on E38: On Leave - 5 Working Days -Ömer Faruk Olcay
Note on E61: Aysun: 1 - Goal vs sürecinde dayanışma gözlemledim iyiydi Deniz: 1 - Aksiyonlar yerindeydi -Ömer Faruk Olcay
Note on E62: Esra: -1 - birçok eksik noktalar gördüm. Mert: -1 - Yüzeysel task yapılıyor hissiyatı var. Goal tasklarından birinin reject olması Olcay: -1 - Zincirleme kaza olduğunu düşünüyorum İrem: 0 - Groomda bazı hatalar sezdiğim için bu puanı verdim. Özkan: 0 - Nötr geçti genel olarak. Talha: -1 - GLA groomu ile alakalı problemlerden ötürü. Buse: 0 - Usage analytics'in bitmesi iyi bi konu oldu, ama overall nötr. Barış: 0 - Gergin geçti ama iyiydi. Ulaş: ! - yoktum. Vesile: -1 - Çok iyi geçmedi. -Ömer Faruk Olcay
Note on E63: Esra: 0 - Sahiplenme seviyesi sayesinde 0 a çıktı. Mert: 0 - Nötr. Olcay: 1 - Hızlı iletişim. İrem: 1 - İyi iletişim. Özkan: 0 - Nötr. Talha: 2 - Ekstra iletişim. Buse: 1 - Usage analytics. Barış: 1 - Bilgiye olan açlık. Ulaş: ! - yoktum Vesile: 1 - Etkili Destek. -Ömer Faruk Olcay
Note on F37: On Leave - 4 Working Days -Ömer Faruk Olcay
Note on F61: Deniz: -1 Genel çok blocker yaşadık, planningde de problem vardı. Sona kalan çok task var. -Ömer Faruk Olcay
Note on F62: Esra: -1 Karışık bir sprint yaşadım, yoruldum. Mert: ! Olcay: -1 Personal planning odaklı kalınması, General planning issues İrem: 1 MVP ye karar verilmesi Özkan: 0 Bi sıkıntım yoktu Talha: -1 Test süreçlerinde dışardan sıkıntılar yaşandı. Buse: 1 Takımda olumsuz bir şey yoktu. Merve: 1 onboarding süreci pozitif geçti. Barış: 0 ekstra bir şey yaşanmadı Ulaş: 0 Yoğunduk, her şeyi yaptık ama olmadı Vesile: 0 İyisiyle kötüsüyle nötr -Ömer Faruk Olcay
Note on F63: Esra: 0 Aklıma bir şey gelmiyor. Mert: ! Olcay: 1 Motivasyon amaçlı verdim. İrem: 0 Ekstra bi durum oluşmadı. Özkan: 1 Verimliydi. Talha: 1 Hızlı aksiyon. Buse: 1 Tek başına iyi idare etti. Merve: 1 Iki tane toplantıdan baya verim aldım. Barış: 0 Ekstra bir durum yaşanmadı. Ulaş: 1 Sevdiğim için verdim. Vesile: 1 Onboarding destegi iyiydi. -Ömer Faruk Olcay
Note on G39: On Leave - 2 Working Days -Ömer Faruk Olcay
Note on G61: Deniz: 0 Nötr geçti +- lerde overall -Ömer Faruk Olcay
Note on G62: Esra: -1 Goal dışında problemler yaşıyorum, kaotik olaylar çıktı. Mert: -1 Odak olarak geride hissediyorum, Esra'nın comment Olcay: 0 Esra'nın comment İrem: ! Özkan: -1 Test env. vs problemleri çok geriye attı süre/efor olarak Talha: -1 özkan+esra'nın comment, kube/otomasyon problemleri Buse: -1 planlamada öngörülemeyen problemler ortaya sprint sırasında çıktı. Merve: 0 ekstra efor verilen işler çıktı, ekip içi huzursuzluk sezdim. Barış: -1 bu dönemde Valoremde mutsuz/restricted hissediyorum. Ulaş: 1 survive ettik o yüzden Vesile: 0 assign olan tasklarda smooth ilerleyemedim, ufak taska çok efor gitti. -Ömer Faruk Olcay
Note on G63: Esra: 1 içimden geldi Mert: 1 performansın için teşekkürler. Olcay: 0 iyi align olmaya devam İrem: ! Özkan: 0 yanlış anlaşılmalar oldu, nötr. Talha: 0 her şey yolunda Buse: 1 vermeyelim de taşa mı dönelim Merve: 1 kaos içinde iyi survive etti Barış: 1 problemlere karşı sogukkanlı davrandı Ulaş: 1 aysunsuz deniz iyi dayandı Vesile: 1 ekstra bi gelişme yoktum -Ömer Faruk Olcay
Note on H62: Esra: -1 takım olmaktan uzaklaştık Mert: -1 Olcay: 1 ekip çalışıyor İrem: 0 iletişim problemleri oldu. Özkan: -1 insanlar toksitti Talha: -1 iletişimdeki gerginlik Buse: 0 Merve: -1 stresli tasklar knowhow eksikliği Barış: 0 stresli Ulaş: -1 yorum yok anlatıyor herŞEY Vesile: -1 iletişim sorunları -Orhun Turan
Note on H63: Esra: 1 Mert: 0 Olcay: -1 çıktı yok İrem: 0 Özkan: 1 Talha: 1 Buse: 1 tam destek Merve: 1 enerji yüksek Barış: 1000 elimden tuttu Ulaş: 0 yorumum yok Vesile: 1 aysunda 1 -Orhun Turan
Note on I62: Esra: 0 iyiler kötüler birbirini yedi Mert: -1 hala takım olmuyoruz Olcay: 1 sorunlar çözüldü İrem: 1 workshoplar güzeldi Özkan: -1 fazla al ver oldu tasklarda Talha: 0 success ler düzeldi Buse: 1 workshoplar güzel Merve: 1 stressiz, verimliyim Barış: 1 çözümler hızlı Ulaş: -1 geçen sprinti hazmedemedim Vesile: 1 güzel güzel -Orhun Turan
Note on I63: Esra: 1 Mert: 0 Olcay: 0 İrem: 1 Özkan: 1 Talha: 0 Buse: 1 Merve: 1 Barış: 1 Ulaş:0 Vesile: 1 -Orhun Turan
Note on J10: scope changed cause of event conversion issue (before we worked on overall analytics) -Orhun Turan
Note on J39: On leave - 3 Days -Ozkan Mese
Note on J62: Esra: 0 elinden geleni yaptı ama olmadı Mert: -1 threadler uzadı process ler patladı Olcay: -1 bazıları mutsuz İrem: 0 Özkan: -1 Talha: -1 Buse: 0 Merve: -1 test ortamları baydı smokelar patladı Barış: 0 Ulaş: -1 gergin Vesile:- -Orhun Turan
Note on J63: Esra: 0 Mert: 1 Olcay: 0 İrem: 0 Özkan: 1 Talha: 0 Buse: 0 Merve: 1 Barış: 0 Ulaş:1 Vesile:- -Orhun Turan
Note on K50: added 5 -Orhun Turan
Note on K52: added 13 -Orhun Turan burası güncellenmiş brom sonradan senin haberin var mı -Ozkan Mese
Note on K61: Sibel:1 -Orhun Turan
Note on K62: Esra: -1 kişisel focus kaydı,ekip kopuk Mert: 0 Olcay: 1 mutluyum akıyo İrem: 0 Özkan: -1 başımıza gelmeyen kalmadı Talha: -1 başımıza gelmeyen kalmadı Buse: Merve: -1 stres içindeyim otomasyon sıkıntı Barış: Ulaş: 1 Vesile: -Orhun Turan
Note on K63: Esra: -1 sprint değişiyor bayrak kaldırdık takan olmadı Mert: 1 güzel handle edildi Olcay: -1 gol konuları sıkıntı İrem: 0 Özkan: 0 iletişim kopukluğumuz vardı Talha:-1 gol konuları sıkıntılı Buse: Merve: 1 Barış: Ulaş: 1 Vesile: -Orhun Turan
Note on L61: Sibel:1 Deniz:1 -Orhun Turan
Note on L62: Esra: 0 smart reco sıkıntı Mert: 1 sibel alıştı Olcay: 1 İrem: 0 Özkan: 1 takıma teşekkür Talha: 0 Buse: 1 Merve: 0 Barış: 1 Ulaş: 1 Vesile: 0 -Orhun Turan
Note on L63: Esra: 0 Mert: 1 Olcay:1 İrem:0 Özkan:1 Talha:1 Buse:1 Merve:1 Barış:1 Ulaş:1 Vesile:1 -Orhun Turan
Note on M31: excluded design efforts -Orhun Turan
Note on M39: leave 4 days -Ozkan Mese
Note on M61: Sibel:1 -Orhun Turan
Note on M62: Esra: 0 Mert: 0 Olcay: 1 İrem: 0 Özkan: -1 3 gün çalıştım çok beklenti vardı Talha: 0 Buse: 1 Merve: 1 Barış: 1 Ulaş: 1 Vesile:1 -Orhun Turan
Note on M63: Esra: 0 Mert:1 Olcay:1 İrem:1 Özkan:-1 Talha:1 Buse:1 Merve:1 Barış:1 Ulaş:1 Vesile:1 -Orhun Turan
Note on N31: excluded design efforts -Orhun Turan
Note on N61: Sibel: 1 -Orhun Turan
Note on N62: Esra: 0 genel iletişimsizlik sezdim 2.hafta Mert: - Olcay: 1 İrem: - Özkan: 1 Talha: -1 sr taskları fail, yardımlaşma azdı Buse: - Merve: -1 odak bölündü,value yakalayamadık Barış: 0 Ulaş: 0 Vesile: -1 qa ekibi mutsuz -Orhun Turan
Note on N63: Esra:0 Mert:- Olcay:1 İrem:- Özkan:0 Talha:0 Buse:- Merve:1 Barış: 1 Ulaş:1 Vesile:1 -Orhun Turan
Note on O61: Sibel:1 Özge:1 -Orhun Turan
Note on O62: Esra: 0 Mert: - Olcay: 1 İrem: 1 Özkan: 0 Talha: - Buse: 0 Merve: 0 Barış: - Ulaş: 0 Vesile: 0 -Orhun Turan
Note on O63: Esra: 1 Mert:- Olcay:0 İrem:1 Özkan:0 Talha:- Buse:1 Merve:1 Barış:- Ulaş:1 Vesile:1 -Orhun Turan
Note on P61: Sibel: 0 -Sibel Yildirim
Note on P62: Esra: 0 Mert: 0 Olcay: 1 İrem: - Özkan: 0 Talha: -1 Buse: 0 Merve: 1 Barış: 0 Ulaş: 1 Vesile: 1 -Sibel Yildirim
Note on P63: Esra: 1 (özge <3) Mert: -1 Olcay: 1 İrem: - Özkan: 0 Talha: 0 Buse: 1 Merve: 1 Barış: 1 Ulaş: 0 Vesile: 0 -Sibel Yildirim
Note on Q61: Sibel: 0 Özge: 0 -Ömer Faruk Olcay
Note on Q62: Esra: 1 Mert: -1 Olcay: 0 Özkan: -1 Talha: 0 Buse: 0 Merve: 1 Barış: 0 Ulaş: 0 Vesile: 0 -Ömer Faruk Olcay
Note on Q63: Esra: -1 Mert: -1 Olcay: 1 Özkan: -1 Talha: 0 Buse: 0 Merve: 1 Barış: 0 Ulaş: 0 Vesile: 0 -Ömer Faruk Olcay
Note on R61: Sibel: 1 Özge:1 -Orhun Turan
Note on R62: Esra: -1 Mert: - Olcay: 1 Özkan: 1 Talha: 0 Buse: 1 Merve: 0 Barış: - Ulaş: 1 Vesile:1 -Orhun Turan
Note on R63: Esra: 0 Mert: - Olcay: 1 Özkan: 1 Talha: 1 Buse: 1 Merve: 1 Barış:- Ulaş: 1 Vesile: 1 -Orhun Turan
Note on S61: Sibel: 0 Özge: 0 -Orhun Turan
Note on S62: Esra: 0 Mert: -1 Olcay: -1 event conv hikayesini görebilirdik. overall hikayesinde iletişim sorunu Özkan: -1 concernleri dile getirdim ciddiye alınmadı Talha: 0 Buse: 1 Merve: -1 saçma sapan şeylere vakit Barış: - Ulaş: -1 event conv fuckup Vesile: -1 mutlu değilim -Orhun Turan
Note on S63: Esra:0 Mert:0 Olcay:-1 iletişim eksikliği Özkan: -1 Talha:0 Buse:1 Merve:0 tnx sibel Barış:- Ulaş:0 Vesile:0 -Orhun Turan

## Paracetamol
Paracetamol
Quarter | Q1 | [5 empty] | Q2 | [5 empty] | Q3 | [5 empty] | Q4
Month | Jan |  | Feb |  | March |  | April |  | May |  | June |  | July |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | [7 empty] | 19/04 - 02/05 | 03/05 - 16/05 | 17/05 - 30/05 | 31/05 - 13/06 | 14/06 - 28/06 | 28/06 - 12/07 | 12/07 - 25/07 | 26/07 - 09/08 | 16/08 - 30/08 | 30/08 - 12/09 | 13/09 - 26/09 | 27/09 - 10/10
Sprint Name | [7 empty] | #1 Welcome Everyone | #2 Mayıs Giremez | #3 Follow the White Rabbit | #4 Believing is seeing | #5 Half-Life | #6 Five More Minutes | #7 Honeymoon | #8 Jetgiller | #9 Hangover | #10 Let's make it live | #11 | #12
Total Effort In the Sprint | [7 empty] | 76 | 131 | 131 | 141 | 71 | 147 | 123 | 126 | 135 | 125 | 199 | 188
Commited | [7 empty] | 76 | 118 | 118 | 128 | 71 | 147 | 110 | 126 | 135 | 122 | 186 | 184
Emerged | [7 empty] | 0 | 13 | 13 | 13 | 0 | 0 | 13 | 0 | 0 | 3 | 13 | 4
Emerged Rate | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.924% | 9.924% | 9% | 0% | 0% | 11% | 0% | 0% | 2% | 7% | 2%
Done Bug Effort | [7 empty] | 0 | 3 | 8 | 0 | 0 | 8 | 0 | 0 | 5 | 3 | 34 | 29
Commited Bug Effort | [7 empty] | 0 | 3 | 8 | 0 | 0 | 8 | 0 | 0 | 5 | 0 | 34 | 29
Emerged Bug Effort | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | [7 empty] | 34 | 76 | 79 | 96 | 34 | 139 | 34 | 61 | 23 | 75 | 43 | 57
All Tasks Done Effort | [7 empty] | 34 | 76 | 79 | 96 | 34 | 139 | 34 | 64 | 23 | 75 | 43 | 57
Released Effort | [7 empty] | 0 | 18 | 13 | 73 | 34 | 139 | 34 | 6 | 23 | 20 | 0 | 13
Undone PBI Effort | [7 empty] | 42 | 42 | 47 | 32 | 37 | 8 | 76 | 62 | 107 | 47 | 143 | 120
Comitted Releasable Dev Tasks | [7 empty] | 76 | 118 | 118 | 128 | 71 | 147 | 110 | 123 | 135 | 122 | 186 | 179
Sprint Goal | [7 empty] | - Have a use case management on Gachapon. (developed) - Make the data requirements part more usable for partners | - Completing the business objective part, making it demoable. - Completing edge cases of data planning (making changes on the flow) | - Completing Select Use Case part completely. - Data Integration concept to be confirmed by respective stakeholders | Completing Select Use Case part completely. - Bringing Data for Modals to be ready. - Data Creation concept to be finalized and to be handshaked on it. | - Completing "Use Case Details" page. - Completing design of "Data Source Improvements". | - Complete the FE - Add Event Modal - Finalize the design of Data Integration KR | - Complete the FE - Add Event Modal - Finalize the design of Data Integration KR - Completing the design of the Confirmation Page of Data Planning | - Finishing "data requirements" step tasks - supporting with the complementary actions (design, decisions, alignments) | - We should be ready to release the required tasks to get into QA Camp next sprint. (introduction - data requirements - confirming the plan) | - Making Data Planning LIVE | - data planning should be live on partner accounts after solving the issues - micro-frontend transition will be completely done. | - Solving all bug tasks and going live for all customers (sprint içinde mümkün olan en kısa zamanda)
Goal Achieved (0/1) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 44.74% | 58.02% | 60.31% | 68.09% | 47.89% | 94.56% | 27.64% | 48.41% | 17.04% | 60% | 21.61% | 30.32%
Bug/Development Ratio | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.947% | 10.13% | 0% | 0% | 5.755% | 0% | 0% | 21.74% | 4% | 79.07% | 50.88%
Shipping Accuracy | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.68% | 16.46% | 76.04% | 100% | 100% | 100% | 9.836% | 100% | 26.67% | 0% | 22.81%
Partner Focus | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 97%
Bug Score
Sprint Goal KR Effort (%) | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 45% | 35% | 35% | 70% | 47% | 37% | 58% | 53% | 56% | 33% | 72% | 23% | 0% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 30% | 100% | 30% | 100% | 30% | 30% | 30% | 30% | 30% | 85% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [12 empty] | 100% | 30% | 30% | 30% | 30% | 30% | 15%
Individual Committed Effort
Recep BIYIKLI | [7 empty] | 34 | 55 | 66 | 65 | 34 | 84 | 47 | 64 | 57 | 0 | 64 | 44
Yavuz DALKILIÇ | [7 empty] | 42 | 60 | 52 | 63 | 37 | 63 | 63 | 36 | 42 | 41 | 53 | 54
Umut ÇAYLI | [13 empty] | 0 | 31 | 36 | 26 | 38 | 37
İlker ÇETİN | [16 empty] | 55 | 31 | 50
Individual Done Effort
Recep BIYIKLI | [7 empty] | 34 | 68 | 79 | 65 | 34 | 84 | 34 | 64 | 23 | 4 | 77 | 13
Yavuz DALKILIÇ | [7 empty] | 0 | 5 | 0 | 52 | 21 | 55 | 0 | 0 | 0 | 8 | 14 | 12
Umut ÇAYLI | [13 empty] | 0 | 0 | 0 | 8 | 7 | 19
İlker ÇETİN | [15 empty] | 0 | 55 | 10 | 45
Designers Committed Effort
Eslem KAYNAK | [15 empty] | 55 | 55 | 50 | 50
Suzan HAMED | [15 empty] | 34 | 34 | 42 | 50
Işıl Hande SÜER | [15 empty] | 43 | 51 | 21 | 18
Designers Done Effort
Eslem KAYNAK | [16 empty] | 42 | 50 | 50
Suzan HAMED | [16 empty] | 34 | 8 | 50
Işıl Hande SÜER | [16 empty] | 43 | 21 | 18
Sprint Goal KR Focused Effort
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A32: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%

## Pirates
Pirates
Quarter | Q1 | [5 empty] | Q2 |  |  |  |  | Q3 | [6 empty] | Q4
Month | Jan |  | Feb |  | March |  | April | May |  | June |  | July |  |  | Aug |  | Sep |  | Oct |  | Nov |  |  | Dec
Sprint Start-End Dates | 04/01 - 18/01 | 18/01 - 01/02 | 01/02 - 15/02 | 15/02 - 29/02 | 29/02 - 14/03 | 21/03 - 28/03 | 28/03 - 25/04 | 25/04 - 09/05 | 09/05 - 23/05 | 23/05 - 06/06 | 06/06 - 14/06 | 20/06 - 04/07 | 04/07 - 18/07 | 18/07 - 01/08 | 01/08 - 09/08 | 16/08 - 29/08 | 29/08 - 12/09 | 12/09 - 26/09 | 26/09 - 10/10
Sprint Name | Squad #48 Single Ladies | Squad #49 Öneri Reddedildi 💔 | Squad #50 Yat Bakalım Melih 🛏 | Squad #51 Kalk Bakalım Melih ⏰ | Squad #52: Koyun AFK 🐏🐑 | Squad #54 | Squad #55 Kamaz Dolusu BE 🛻 | Squad #56 Sana Guardiyolar ⚽ | Squad #57 İnzibatlar Geldi 🪖 | Squad #58 58 Olabilir mi 58? | Squad #59 Too hot to sprint 🌡 | Squad #60 AlpomDamatOluyo 🤵🏻 | Squad #61 HE SAID EVEETT👰🏻‍♂ | Squad #62 Yanaklar 75px 🍑 | Squad #63 Welcome (Akustik) 🎸 | Squad #64 Farewell (Akustik) | Squad #65 DelirmedimNoWorries | Squad #66 HaydiGülsüSanayiye🛠 | Squad #67 AlpErenYılmaz 🏴‍☠
Total Effort In the Sprint | 200.5 | 206.5 | 196.5 | 211 | 177 | 96.5 | 258.5 | 198.5 | 202 | 158.5 | 99.5 | 167 | 176 | 183.5 | 101 | 470 | 454 | 434 | 480
Commited | 182 | 195 | 190.5 | 203 | 170 | 93 | 249.5 | 194.5 | 200 | 156.5 | 88 | 154 | 160 | 171.5 | 95.5 | 449 | 448 | 423 | 464
Emerged | 18.5 | 11.5 | 6 | 8 | 7 | 3.5 | 9 | 4 | 2 | 2 | 11.5 | 13 | 16 | 12 | 5.5 | 21 | 6 | 11 | 16 | 0 | 0 | 0 | 0 | 0 | 0
Emerged Rate | 9.227% | 5.569% | 3.053% | 3.791% | 3.955% | 3.627% | 3.482% | 2.015% | 0.9901% | 1.262% | 11.56% | 7.784% | 9.091% | 6.54% | 5.446% | 4.468% | 1.322% | 2.535% | 3.333% | 0% | 0% | 0% | 0% | 0% | 0%
Done Bug Effort | 16 | 11.5 | 3.5 | 4 | 5.5 | 9 | 14 | 13 | 4 | 3.5 | 5.5 | 6 | 16 | 9 | 8.5 | 38 | 36 | 46 | 27
Commited Bug Effort | 9.5 | 11 | 3 | 2.5 | 2 | 6.5 | 10.5 | 12 | 3.5 | 4.5 | 6 | 5.5 | 12 | 6 | 7 | 49 | 35 | 46 | 13
Emerged Bug Effort | 7.5 | 0.5 | 1 | 1.5 | 3.5 | 2.5 | 3.5 | 1 | 0.5 | 1 | 4.5 | 0.5 | 4 | 3.5 | 1.5 | 5 | 1 | 0 | 14
Done Pool Effort
Done Pool Bug Effort
Dev Tasks Done Effort | 115 | 113 | 81.5 | 93 | 76.5 | 45 | 146 | 79.5 | 51.5 | 70.5 | 41.5 | 58 | 61.5 | 84.5 | 21.5 | 147 | 182 | 174 | 243
All Tasks Done Effort | 195 | 199.5 | 195 | 175 | 155 | 90.5 | 230.5 | 161.5 | 157.5 | 107.5 | 80.5 | 106 | 133.5 | 144 | 91 | 391 | 396 | 421 | 343
Released Effort | 83.5 | 81 | 73.5 | 73 | 45 | 39 | 139 | 63 | 40 | 54.5 | 28 | 56 | 58.5 | 42.5 | 17.5 | 118 | 119 | 128 | 198
Undone PBI Effort | 5.5 | 8 | 1.5 | 36 | 22 | 6 | 28 | 37 | 44.5 | 51 | 19 | 61 | 42.5 | 39.5 | 10 | 79 | 58 | 13 | 137
Comitted Releasable Dev Tasks | 114.5 | 109.5 | 80 | 106.5 | 77.5 | 47.5 | 143 | 105 | 83 | 84 | 44 | 77 | 83 | 89 | 34 | 194 | 230 | 165 | 280
Sprint Goal | ✔️ Incident Actions to be completed. ✔️ Single Push will be released for all partners. ✔️ Enigma implementation for Subscribers and Overall analytics page. | ✔️ Enigma tasks will be ready for release ✔️ Web Push preview improvement will be ready for release w/partner flag ✔️ Web Push Tech Debt and Incident Action tasks will be ready for release | ✔️ Salesforce infrastructure to be released and working for test partner. ✔️ Enigma Transition will be released for each page except the subscriber analytics page. ✔️ UX improvement tasks to be ready for release. | ✔️ Farewell to Token DB and Migration of false attribute users - (Will be released) ✔️ Enigma - Subscriber page to be working with Enigma - (Ready for Release) ✔️ Group Level Access - Getting ready for live! - (Ready for Release) | ✔️ Salesforce Analytics design to be finalized. ✔️ Dynamic Content Preview will be waiting for release. ✔️ Enigma monitoring and alarm systems to be completed. (Will be released) ✔️ Getting ready for GLA release. (Ready for Release) | ✔️ Enigma and SF shut down tasks will be Awaiting Release | ✔️ SF Analytics page tasks to be Waiting for Release. ✔️ Multiple Frequency Capping to be Ready for Release. ✔️ Alarm Improvements to be Done. ✔️ New Gachapon Structure tasks to be Ready for Release. | ✔️ Adjustable Conversion Attribution Window PoC and Test Case Set should be completed. (Done) ✔️ Making "Goal" step visible in web push campaign creation flow for every single push type. (Will be released w/ partner flag) ✔️ Panel access logs will be available. (Awaiting Release) ✔️ Gachapon Controls to be finalized for panel. (Awaiting Release) ✔️ Tech Design for Maintenance Mode to be completed. (Done) ✔️ Research for Web Push Dashboard to be completed. (Done) | ✔️ "Goal" page in every push type will be visible and running with the Conversion Duration settings w/partner flag. (Will be Released) ✔️ Technical structure to be finalized in SW for ACD. (Awaiting Release) ✔️ New Gachapon flows and Migration job to be developed. (Will be Released) ✔️ Migrating to AWS ECS without any issue. (Will be Released) | ✔️ Tech Design and POC for Welcome Push will be completed. (Done) ✔️ Revision of GLA Settings modal will be completed. (Will be Released) ✔️ Adjustable Attribution Window KR tasks will be completed. (Awaiting Release) | - Gachapon ve segmentation paketi için kendi tarafında iş kalmayacak (migration hariç) - Access logları sorunsuz kaydedilir hale gelecek - Optin event Pandora'ya paslanır hale gelecek - GA4/Inone metrik farklılıkları aydınlatılacak | ✔️ Count Bubble behaviour will not be a blocker for the Segmentation package transition. (Awaiting Release) ✔️ Accesslog DB will be released. ✔️ Gachapon migration to be completed for all partners without any problem. (Done) ✔️ Pandora tasks for Default Goal and AAW will be completed. (Awaiting Release) | ✔️ URM v2 endpoint to be live. (Awaiting Release) ✔️ New Web push Gachapon tab to be live. (Released). ✔️ New segmentation package and adjustable attribution tasks will be completed. (Pending for Release) ✔️ New Opt-in collection goal to be live. (Awaiting Release) | ✔️ All Welcome Push tasks will be Awaiting Release with the partner flag. | ✔️ Service Worker and Opt-in research to be completed. ✔️ Welcome Push KR tasks to be Awaiting Release. | ✔️ Welcome push tasks will be ready for release. ✔️ Farewell predefined segment research will be done. ✔️ Multiple frequency capping will be ready for release ✔️ Service worker tech design will be done. ✔️ Dynamic attributes will be added to custom links. (Pending) | ✔️Completion of the design of the onboarding center (without UX writing) ✔️ Being ready to implement consumer producer mechanism for web push integration manager (Done) ✔️Welcome Push will be ready to go! (Task should be released with completing major fixes) | ✔️ Welcome push live for all (with automation coverage) ✔️ Finalization of the design of the onboarding center and new web push settings pages ✔️ Preparation of test case part 1 for integration manager ✔️ Completion of onboarding version of the dolist page (Awaiting) | ✔️ All Web Push Integration Manager KR tasks will be done.
Goal Achieved (0/1) | 0% | 100% | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Plan Accuracy | 107.1% | 102.3% | 102.4% | 86.21% | 91.18% | 97.31% | 92.38% | 83.03% | 78.75% | 68.69% | 91.48% | 68.83% | 83.44% | 83.97% | 95.29% | 87.08% | 88.39% | 99.53% | 73.92% | 0% | 0% | 0% | 0% | 0% | 0%
Bug/Development Ratio | 13.91% | 10.18% | 4.294% | 4.301% | 7.19% | 20% | 9.589% | 16.35% | 7.767% | 4.965% | 13.25% | 10.34% | 26.02% | 10.65% | 39.53% | 25.85% | 19.78% | 26.44% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0%
Shipping Accuracy | 72.61% | 71.68% | 90.18% | 78.49% | 58.82% | 86.67% | 95.21% | 79.25% | 77.67% | 77.3% | 67.47% | 96.55% | 95.12% | 50.3% | 81.4% | 80.27% | 65.38% | 73.56% | 81.48% | 0% | 0% | 0% | 0% | 0% | 0%
Partner Focus | 62.91% | 56.15% | 41.99% | 52.46% | 45.59% | 51.08% | 57.31% | 53.98% | 41.5% | 53.67% | 50% | 50% | 51.88% | 51.9% | 35.6% | 43.21% | 51.34% | 39.01% | 60.34% | 0% | 0% | 0% | 0% | 0% | 0%
UXI/Development Score | 16.15% | 14.54% | 15.13% | 6.29% | 24.52% | 9.39% | 18.32% | 1.86% | 0.64% | 17.67% | 1.65% | 13.79% | 18.67% | 11.35% | 5.84% | 12.05% | 14.5% | 8.04% | 7.87% | 0% | 0% | 0% | 0% | 0% | 0%
Bug Score
Sprint Goal KR Effort (%) | [11 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sprint Goal Effort (%) | 25.79% | 47% | 34% | 31.9% | 33.55% | 14.73% | 39.76% | 30.68% | 36.25% | 38.86% | 15.9% | 31.46% | 24.6% | 33.46% | 40.6% | 31.48% | 36.94% | 36.17% | 37.02% | 0% | 0% | 0% | 0% | 0% | 0%
Number of Team Member Participation | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Advanced Sprint Goal Success | 15% | 100% | 30% | 100% | 100% | 85% | 100% | 30% | 100% | 100% | 15% | 30% | 85% | 100% | 100% | 100% | 100% | 100% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
Updated A. Sprint Goal Success | [11 empty] | 30% | 100% | 100% | 100% | 100% | 100% | 100%
Individual Committed Effort
Alperen | 17 | 19 | 17.5 | 19 | 13 | 7 | 28 | 16.5 | 18.5 | 15.5 | 10.5 | 3.5 | 12 | 15.5 | 13.5 | 49 | 67 | 60 | 63
Görkem | 16 | 1 | 14 | 13.5 | 10 | 9 | 23.5 | 15 | 19.5 | 16.5 | 10.5 | 16 | 16.5 | 6 | 6 | 16 | 21 | 40 | 36
Reza | 15.5 | 17.5 | 17 | 18.5 | 7 | 6.5 | 23.5 | 17.5 | 16 | 0 | 8.5 | 0 | 17 | 14
Ömer | 14 | 19 | 14.5 | 20 | 18.5 | 11 | 21 | 14 | 16.5 | 18 | 9 | 13.5 | 16 | 20.5 | 12 | 53 | 51
Umut | 15 | 18.5 | 14.5 | 17 | 15 | 3.5 | 19 | 16 | 8.5 | 15 | 9 | 15 | 15 | 17.5 | 12 | 51 | 71 | 58 | 63
Umut Ç. | [5 empty] | 3 | 12 | 13.5 | 14 | 9.5 | 0 | 13 | - | - | -
Berkan | 21.5 | 20 | 17 | 11 | 12.5 | 0 | 11 | 11 | 15.5 | 15 | 8.5 | 14 | 12 | 15 | 13 | 47 | 52 | 46 | 48
İlker | 19 | 22 | 16 | 20 | 18 | 10.5 | 25 | 14 | 17 | 16 | 10 | 14 | 13 | 13.5 | 7.5 | 48
Eren | [15 empty] | 8 | 31 | 30 | 40
Mehmet Alp | [16 empty] | 22 | 40 | 50
Yılmaz | [17 empty] | 7 | 25
Total Dev Committed Effort | 118 | 117 | 110.5 | 119 | 94 | 50.5 | 163 | 117.5 | 125.5 | 105.5 | 66 | 89 | 101.5 | 102 | 64 | 272 | 315 | 281 | 325 | 0 | 0 | 0 | 0 | 0 | 0
Ezgi | 18 | 26 | 29 | 33 | 26 | 21 | 26 | 19 | 21 | 0 | 13 | 18 | 16 | 19 | 10 | 52 | 55 | 38 | 33
Sıla | 21 | 21 | 21 | 21 | 26 | 21 | 26 | 19 | 22 | 23 | 6 | 18 | 18 | 21 | 13 | 55 | 55 | 47 | 34
Total Design Committed Effort | 39 | 47 | 50 | 54 | 52 | 42 | 52 | 38 | 43 | 23 | 19 | 36 | 34 | 40 | 23 | 107 | 110 | 85 | 67 | 0 | 0 | 0 | 0 | 0 | 0
Emir | - | - | 0 | 1 | 4 | 0 | 5 | 2.5 | 4.5 | 2.5 | 1 | 4 | 4 | 5 | 1 | 8 | 5 | 8 | 14
Gülsüm | 11 | 6 | 11 | 3 | 4 | 3 | 9.5 | 13.5 | 12 | 13 | 0 | 9 | 2 | 10 | 2.5 | 21 | 5 | 19 | 21
Firuze | 7 | 14 | 9 | 16 | 9 | 0 | 11 | 15 | 13 | 12.5 | 2 | 10 | 11.5 | 7.5 | 3 | 23 | 5 | 12 | 21
Melih | 5.5 | 7 | 8 | 5 | 4 | 0.5 | 9 | 8 | 2 | 0 | 0 | 6 | 7 | 7 | 2 | 18 | 8 | 18 | 16
Total QA Committed Effort | 23.5 | 27 | 28 | 25 | 21 | 3.5 | 34.5 | 39 | 31.5 | 28 | 3 | 29 | 24.5 | 29.5 | 8.5 | 70 | 23 | 57 | 72 | 0 | 0 | 0 | 0 | 0 | 0
Total Committed Manual Test Effort | [5 empty] | 9 | 33 | 25.5 | 35 | 33.5 | 17 | 30.5 | 23 | 30 | 15 | 91 | 84 | 43 | 79
Individual Done Effort
Alperen | 24 | 18.5 | 18.5 | 22 | 16 | 7.5 | 28.5 | 4.5 | 13.5 | 18.5 | 8.5 | 1.5 | 14 | 12.5 | 13.5 | 62 | 69 | 61 | 66
Görkem | 16 | 1 | 14.5 | 5 | 13 | 9 | 23.5 | 15 | 20.5 | 20 | 6 | 11 | 8.5 | 3 | 7 | 16 | 0 | 48 | 38
Reza | 19.5 | 17.5 | 17.5 | 12.5 | 0 | 6.5 | 23.5 | 12.5 | 2 | 0 | 8 | 2.5 | 16.5 | 3.5
Ömer | 14 | 19.5 | 14 | 22.5 | 17.5 | 8 | 21 | 14 | 16.5 | 18 | 9 | 8.5 | 11 | 20.5 | 10 | 58 | 43
Umut Ç. | [5 empty] | 3 | 12 | 10.5 | 4.5 | 0.5 | 0 | 7 | - | -
Umut | 11.5 | 22.5 | 14.5 | 22 | 23 | 3.5 | 22.5 | 16.5 | 8.5 | 15.5 | 12.5 | 17 | 18 | 20.5 | 13 | 51 | 63 | 58 | 63
Berkan | 21.5 | 21 | 17 | 9 | 9.5 | 0 | 11 | 11 | 15.5 | 4 | 6.5 | 1.5 | 7 | 15 | 16.5 | 34 | 31 | 47 | 32
Eren | [15 empty] | 11 | 31 | 31 | 11
Mehmet Alp | [16 empty] | 23 | 40 | 40
Yılmaz | [17 empty] | 1 | 17
İlker | 19 | 23.5 | 16 | 8 | 12 | 7.5 | 24 | 5.5 | 14 | 15 | 10 | 14 | 8 | 17.5 | 7.5 | 40
Total Dev Done Effort | 125.5 | 123.5 | 112 | 101 | 91 | 45 | 166 | 89.5 | 95 | 91.5 | 60.5 | 63 | 83 | 92.5 | 67.5 | 272 | 260 | 286 | 267 | 0 | 0 | 0 | 0 | 0 | 0
Ezgi | 18 | 26 | 29 | 33 | 26 | 21 | 18 | 19 | 21 | 0 | 13 | 13 | 16 | 19 | 2 | 52 | 55 | 34 | 20
Sıla | 21 | 21 | 20 | 21 | 26 | 21 | 26.5 | 19 | 22 | 10 | 6 | 18 | 18 | 21 | 13 | 55 | 55 | 47 | 26
Total Design Done Effort | 39 | 47 | 49 | 54 | 52 | 42 | 44.5 | 38 | 43 | 10 | 19 | 31 | 34 | 40 | 15 | 107 | 110 | 81 | 46 | 0 | 0 | 0 | 0 | 0 | 0
Emir | - | - | 1 | 1 | 4 | 0 | 2 | 2.5 | 2.5 | 2.5 | 1 | 0 | 1 | 2 | 1 | 5 | 5 | 8 | 14
Gülsüm | 11 | 7 | 13 | 2 | 2 | 3 | 7 | 8.5 | 4 | 0 | 0 | 2 | 2 | 0 | 2.5 | 0 | 8 | 16 | 0
Firuze | 10 | 14 | 9 | 11 | 0 | 0 | 11 | 15 | 13 | 3.5 | 0 | 10 | 6.5 | 6.5 | 3 | 5 | 5 | 12 | 8
Melih | 8.5 | 4 | 9 | 3 | 3 | 0.5 | 5 | 8 | 0 | 0 | 0 | 0 | 7 | 3 | 2 | 2 | 8 | 18 | 8
Total QA Done Effort | 29.5 | 25 | 32 | 17 | 9 | 3.5 | 25 | 34 | 19.5 | 6 | 1 | 12 | 16.5 | 11.5 | 8.5 | 12 | 26 | 54 | 30 | 0 | 0 | 0 | 0 | 0 | 0
Total Done Manual Test Effort |  |  |  |  | 24.5 | 6.5 | 41 | 20 | 38 | 33.5 | 12.5 | 21 | 17.5 | 26.5 | 14 | 72 | 74 | 46 | 45
Sprint Goal KR Focused Effort
Note on A24: it is binary component like but to convert it to percentage: if it's 1, enter 100% if not 0%
Note on A33: it is binary component like sprint goal but to convert it to percentage: if half of the team participated in sprint goal tasks, enter 100% if not 0%
Note on P60: eforsuz task var -Melih Mustafa Acet
Note on U24: * 3 Gün arka arkaya deployment cancel oldu * 1 Adet taskımız Security de kaldı -Umut Akkaya

## Summary Per Team
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success | Done PBI Effort | Shipping accuracy formülleri güncellenecek, Release Efficiency metriği eklenecek | Success
Atrium | 1 | #N/A | 48% | 10% | 79% | 65% | #N/A
Atrium | 2 |  | 63% | 13% | 71% | 77.5% | #N/A
Atrium | 3 |  | 73% | 21% | 103% | 95% | #N/A
Atrium | 4 |  | 64% | 25% | 69% | 85%
Atrium | 5 |  | 89% | 29% | 81% | 100%
Atrium | 6 |  | 35% | 36% | 50% | 42.5%
Atrium | 7 |  | 57% | 28% | 51% | 65%
Atrium | 8 |  | 69% | 34% | 75% | 65%
Atrium | 9 |  | 61% | 30% | 41% | 25%
Atrium | 10
Atrium | 11
Atrium | 12
Unix | 1 |  | 45% | 15% | 78% | 65% | #N/A
Unix | 2 |  | 59% | 25% | 90% | 30% | #N/A
Unix | 3 |  | 55% | 20% | 90% | 53% | #N/A
Unix | 4 |  | 69% | 21% | 97% | 65%
Unix | 5 |  | 58% | 20% | 85% | 30%
Unix | 6 |  | 54% | 27% | 95% | 100%
Unix | 7 |  | 79% | 19% | 100% | 65%
Unix | 8 |  | 65% | 22% | 95% | 76.6%
Unix | 9 |  | 56% | 22% | 83% | 30%
Unix | 10
Unix | 11
Unix | 12
Samaritan | 1 |  | 67% | 14% | 99% | 100% | #N/A
Samaritan | 2 |  | 71% | 15% | 91% | 30% | #N/A
Samaritan | 3 |  | 73% | 32% | 91% | 53% | #N/A
Samaritan | 4 |  | 67% | 18% | 100% | 65%
Samaritan | 5 |  | 78% | 27% | 99% | 92.5%
Samaritan | 6 |  | 92% | 31% | 103% | 100%
Samaritan | 7 |  | 74% | 11% | 98% | 65%
Samaritan | 8 |  | 73% | 10% | 95% | 100%
Samaritan | 9 |  | 69% | 18% | 94% | 65%
Samaritan | 10
Samaritan | 11
Samaritan | 12
Contech | 1 |  | 70% | 40% | 74% | 100% | #N/A
Contech | 2 |  | 47% | 30% | 67% | 93% | #N/A
Contech | 3 |  | 81% | 38% | 89% | 90% | #N/A
Contech | 4 |  | 69% | 40% | 85% | 85%
Contech | 5 |  | 82% | 37% | 87% | 57.5%
Contech | 6 |  | 80% | 40% | 65% | 15%
Contech | 7 |  | 73% | 45% | 73% | 30%
Contech | 8 |  | 64% | 30% | 71% | 15%
Contech | 9 |  | 80% | 44% | 86% | 100%
Contech | 10
Contech | 11
Contech | 12
Kraken | 1 |  | 100% | 16% | 69% | 71% | #N/A
Kraken | 2 |  | 61% | 26% | 95% | 92.5% | #N/A
Kraken | 3 |  | 83% | 30% | 88% | 92.5% | #N/A
Kraken | 4 |  | 100% | 43% | 61% | 50%
Kraken | 5 |  | 100% | 20% | 73% | 85%
Kraken | 6 |  | 93% | 63% | 68% | 30%
Kraken | 7 |  | 97% | 57% | 76% | 65%
Kraken | 8 |  | 100% | 54% | 42% | 30%
Kraken | 9 |  | 100% | 32% | 75% | 77%
Kraken | 10
Kraken | 11
Kraken | 12
Cerberus | 1 |  | 96% | 0% | 69% | 100% | #N/A
Cerberus | 2 |  | 99% | 26% | 101% | 100% | #N/A
Cerberus | 3 |  | 100% | 43% | 90% | 53% | #N/A
Cerberus | 4 |  | 100% | 46% | 82% | 100%
Cerberus | 5 |  | 80% | 33% | 72% | 77%
Cerberus | 6 |  | 70% | 44% | 90% | 100%
Cerberus | 7 |  | 72% | 10% | 92% | 100%
Cerberus | 8 |  | 100% | 21% | 86% | 100%
Cerberus | 9 |  | 100% | 65% | 83% | 65%
Cerberus | 10
Cerberus | 11
Cerberus | 12
Coruscant | 1 |  | 92% | 28% | 72% | 15% | #N/A
Coruscant | 2 |  | 84% | 31% | 104% | 50% | #N/A
Coruscant | 3 |  | 79% | 25% | 80% | 90% | #N/A
Coruscant | 4 |  | 85% | 38% | 64% | 30%
Coruscant | 5 |  | 92% | 18% | 90% | 100%
Coruscant | 6 |  | 102% | 14% | 79% | 65%
Coruscant | 7 |  | 92% | 10% | 84% | 100%
Coruscant | 8 |  | 82% | 19% | 78% | 65%
Coruscant | 9 |  | 74% | 53% | 53% | 30%
Coruscant | 10
Coruscant | 11
Coruscant | 12
Korriban | 1 |  | 90% | 27% | 85% | 100% | #N/A
Korriban | 2 |  | 98% | 41% | 105% | 100% | #N/A
Korriban | 3 |  | 100% | 51% | 98% | 77% | #N/A
Korriban | 4 |  | 80% | 28% | 79% | 30%
Korriban | 5 |  | 93% | 22% | 86% | 77%
Korriban | 6 |  | 92% | 40% | 88% | 65%
Korriban | 7 |  | 79% | 23% | 73% | 30%
Korriban | 8 |  | 91% | 33% | 100% | 100%
Korriban | 9 |  | 95% | 31% | 79% | 100%
Korriban | 10
Korriban | 11
Korriban | 12
Design System | 1 |  | 0% | 4% | 103% | 57.5% | #N/A
Design System | 2 |  | 7% | 2% | 95% | 65% | #N/A
Design System | 3 |  | 19% | 7% | 111% | 100% | #N/A
Design System | 4 |  | 0% | 14% | 84% | 100%
Design System | 5 |  | 0% | 0% | 84% | 100%
Design System | 6 |  | 26% | 39% | 117% | 100%
Design System | 7 |  | 20% | 17% | 82% | 53.3%
Design System | 8 |  | 8% | 11% | 96% | 100%
Design System | 9 |  | 25% | 17% | 95% | 100%
Design System | 10
Design System | 11
Design System | 12
GhostBusters | 1 |  | 48% | 11% | 62% | 22.5% | #N/A
GhostBusters | 2 |  | 64% | 24% | 81% | 65% | #N/A
GhostBusters | 3 |  | 62% | 26% | 82% | 92.5% | #N/A
GhostBusters | 4 |  | 73% | 23% | 81% | 65%
GhostBusters | 5 |  | 70% | 24% | 72% | 100%
GhostBusters | 6 |  | 90% | 44% | 84% | 0%
GhostBusters | 7 |  | 76% | 48% | 57% | 50%
GhostBusters | 8 |  | 85% | 40% | 76% | 30%
GhostBusters | 9 |  | 68% | 46% | 67% | 50%
GhostBusters | 10
GhostBusters | 11
GhostBusters | 12
MythBusters | 1 |  | 53% | 24% | 81% | 92.5% | #N/A
MythBusters | 2 |  | 74% | 17% | 93% | 65% | #N/A
MythBusters | 3 |  | 65% | 20% | 78% | 57.5% | #N/A
MythBusters | 4 |  | 91% | 39% | 47% | 30%
MythBusters | 5 |  | 75% | 42% | 94% | 65%
MythBusters | 6 |  | 64% | 37% | 56% | 50%
MythBusters | 7 |  | 77% | 43% | 32% | 15%
MythBusters | 8 |  | 58% | 36% | 77% | 30%
MythBusters | 9 |  | 67% | 41% | 81% | 57.5%
MythBusters | 10
MythBusters | 11
MythBusters | 12
Minerva | 1 |  | 90% | 0% | 90% | 100% | #N/A
Minerva | 2 |  | 93% | 4% | 92% | 100% | #N/A
Minerva | 3 |  | 101% | 13% | 101% | 100% | #N/A
Minerva | 4 |  | 97% | 1% | 97% | 65%
Minerva | 5 |  | 96% | 3% | 96% | 100%
Minerva | 6 |  | 94% | 3% | 94% | 100%
Minerva | 7 |  | 99% | 1% | 99% | 100%
Minerva | 8 |  | 104% | 1% | 104% | 100%
Minerva | 9 |  | 93% | 3% | 93% | 100%
Minerva | 10
Minerva | 11
Minerva | 12
Mobile West | 1 |  | 59% | 21% | 104% | 67% | #N/A
Mobile West | 2 |  | 66% | 36% | 70% | 50% | #N/A
Mobile West | 3 |  | 68% | 32% | 57% | 50% | #N/A
Mobile West | 4 |  | 96% | 25% | 50% | 30%
Mobile West | 5 |  | 94% | 19% | 81% | 53.3%
Mobile West | 6 |  | 83% | 50% | 57% | 30%
Mobile West | 7 |  | 61% | 20% | 82% | 100%
Mobile West | 8 |  | 34% | 27% | 93% | 65%
Mobile West | 9 |  | 88% | 48% | 61% | 30%
Mobile West | 10
Mobile West | 11
Mobile West | 12
Mobile Cartel | 1 |  | 100% | 52% | 71% | 66.6% | #N/A
Mobile Cartel | 2 |  | 100% | 16% | 104% | 100% | #N/A
Mobile Cartel | 3 |  | 100% | 6% | 77% | 50% | #N/A
Mobile Cartel | 4 |  | 100% | 92% | 82% | 30%
Mobile Cartel | 5 |  | 100% | 33% | 30% | 30%
Mobile Cartel | 6 |  | 100% | 16% | 59% | 50%
Mobile Cartel | 7 |  | 100% | 53% | 39% | 30%
Mobile Cartel | 8 |  | 100% | 71% | 46% | 65%
Mobile Cartel | 9 |  | 100% | 24% | 47% | 30%
Mobile Cartel | 10
Mobile Cartel | 11
Mobile Cartel | 12
Mobile East | 1 |  | 64% | 28% | 56% | 33%
Mobile East | 2 |  | 52% | 34% | 99% | 100%
Mobile East | 3 |  | 85% | 20% | 102% | 100%
Mobile East | 4 |  | 53% | 27% | 77% | 57.5%
Mobile East | 5 |  | 67% | 31% | 78% | 53.3%
Mobile East | 6 |  | 33% | 20% | 91% | 65%
Mobile East | 7 |  | 72% | 33% | 110% | 100%
Mobile East | 8 |  | 79% | 35% | 99% | 100%
Mobile East | 9 |  | 90% | 21% | 78% | 65%
Mobile East | 10
Mobile East | 11
Mobile East | 12
Pirate Squad | 1 |  | 72% | 12% | 81% | 57.5% | #N/A
Pirate Squad | 2 |  | 84% | 4% | 43% | 65% | #N/A
Pirate Squad | 3 |  | 73% | 14% | 94% | 92.5% | #N/A
Pirate Squad | 4 |  | 95% | 10% | 92% | 100%
Pirate Squad | 5 |  | 78% | 10% | 77% | 77%
Pirate Squad | 6 |  | 82% | 12% | 80% | 22.5%
Pirate Squad | 7 |  | 73% | 18% | 84% | 100%
Pirate Squad | 8 |  | 81% | 33% | 91% | 100%
Pirate Squad | 9 |  | 69% | 23% | 94% | 100%
Pirate Squad | 10
Pirate Squad | 11
Pirate Squad | 12
Skeletors | 1 |  | 24% | 13% | 81% | 65% | #N/A
Skeletors | 2 |  | 38% | 32% | 84% | 100% | #N/A
Skeletors | 3 |  | 56% | 31% | 96% | 100% | #N/A
Skeletors | 4 |  | 34% | 19% | 97% | 100%
Skeletors | 5 |  | 38% | 23% | 70% | 65%
Skeletors | 6 |  | 45% | 36% | 76% | 92.5%
Skeletors | 7 |  | 58% | 38% | 94% | 65%
Skeletors | 8 |  | 60% | 42% | 70% | 65%
Skeletors | 9 |  | 34% | 32% | 86% | 65%
Skeletors | 10
Skeletors | 11
Skeletors | 12
Liron | 1 |  | 36% | 26% | 81% | 50% | #N/A
Liron | 2 |  | 58% | 22% | 98% | 100% | #N/A
Liron | 3 |  | 58% | 26% | 87% | 62% | #N/A
Liron | 4 |  | 47% | 35% | 85% | 50%
Liron | 5 |  | 58% | 24% | 82% | 58%
Liron | 6 |  | 34% | 26% | 93% | 65%
Liron | 7 |  | 35% | 15% | 104% | 100%
Liron | 8 |  | 48% | 15% | 93% | 65%
Liron | 9 |  | 59% | 30% | 82% | 30%
Liron | 10
Liron | 11
Liron | 12
ScaleUp | 7 |  | 76% | 12% | 94% | 100%
ScaleUp | 8 |  | 74% | 1% | 81% | 30%
ScaleUp | 9 |  | 27% | 15% | 69% | 65%
ScaleUp | 10
ScaleUp | 11
ScaleUp | 12
Valorem | 1 |  | 29% | 17% | 91% | 85% | #N/A
Valorem | 2 |  | 39% | 18% | 102% | 100% | #N/A
Valorem | 3 |  | 38% | 25% | 86% | 57.5% | #N/A
Valorem | 4 |  | 64% | 40% | 111% | 100%
Valorem | 5 |  | 55% | 20% | 85% | 58%
Valorem | 6 |  | 46% | 15% | 77% | 50%
Valorem | 7 |  | 38% | 4% | 82% | 65%
Valorem | 8 |  | 82% | 7% | 93% | 100%
Valorem | 9 |  | 89% | 12% | 91% | 65%
Valorem | 10
Valorem | 11
Valorem | 12
Vikings - SMS | 1 |  | 73% | 13% | 89% | 50%
Vikings - SMS | 2 |  | 88% | 8% | 93% | 100%
Vikings - SMS | 3 |  | 84% | 7% | 97% | 100%
Vikings - SMS | 4 |  | 79% | 11% | 95% | 100%
Vikings - SMS | 5 |  | 71% | 13% | 85% | 67%
Vikings - SMS | 6 |  | 83% | 16% | 70% | 100%
Vikings - SMS | 7 |  | 67% | 14% | 60% | 100%
Vikings - SMS | 8 |  | 90% | 5% | 79% | 100%
Vikings - SMS | 9 |  | 79% | 23% | 86% | 100%
Vikings - SMS | 10
Vikings - SMS | 11
Vikings - SMS | 12
Vikings - WhatsApp | 1 |  | 59% | 28% | 72% | 30%
Vikings - WhatsApp | 2 |  | 64% | 24% | 87% | 51%
Vikings - WhatsApp | 3 |  | 56% | 19% | 65% | 30%
Vikings - WhatsApp | 4 |  | 84% | 20% | 91% | 100%
Vikings - WhatsApp | 5 |  | 75% | 26% | 88% | 100%
Vikings - WhatsApp | 6 |  | 80% | 28% | 85% | 100%
Vikings - WhatsApp | 7 |  | 72% | 20% | 92% | 100%
Vikings - WhatsApp | 8 |  | 64% | 25% | 88% | 100%
Vikings - WhatsApp | 9 |  | 75% | 22% | 68% | 0%
Vikings - WhatsApp | 10
Vikings - WhatsApp | 11
Vikings - WhatsApp | 12
Byte Masters | 1 |  | 56% | 14.5% | 88.5% | 83% | #N/A
Byte Masters | 2 |  | 65% | 20% | 90.5% | 48% | #N/A
Byte Masters | 3 |  | 64% | 26% | 90.5% | 53% | #N/A
Byte Masters | 4 |  | 68% | 19.5% | 98.5% | 65%
Byte Masters | 5 |  | 68% | 23.5% | 92% | 61%
Byte Masters | 6 |  | 73% | 29% | 99% | 100%
Byte Masters | 7 |  | 76.5% | 15% | 99% | 65%
Byte Masters | 8 |  | 69% | 16% | 95% | 88%
Byte Masters | 9 |  | 62.5% | 20% | 88.5% | 48%
Byte Masters | 10
Byte Masters | 11
Byte Masters | 12
DataForce | 1 |  | 93% | 18.3% | 75.3% | 72% | #N/A
DataForce | 2 |  | 93.7% | 32.7% | 103.3% | 72% | #N/A
DataForce | 3 |  | 93% | 38% | 89.3% | 73% | #N/A
DataForce | 4 |  | 88.3% | 37.5% | 75% | 53%
DataForce | 5 |  | 88.3% | 24.3% | 82.7% | 85%
DataForce | 6 |  | 88% | 32.7% | 85.7% | 77%
DataForce | 7 |  | 81% | 14.3% | 83% | 77%
DataForce | 8 |  | 91% | 24.3% | 88% | 86%
DataForce | 9 |  | 89.7% | 49.7% | 71.7% | 65%
DataForce | 10
DataForce | 11
DataForce | 12
QMechanics | 1 |  | 50.5% | 17.5% | 71.5% | 58% | #N/A
QMechanics | 2 |  | 69% | 20.5% | 87% | 65% | #N/A
QMechanics | 3 |  | 63.5% | 23% | 80% | 75% | #N/A
QMechanics | 4 |  | 82% | 31% | 64% | 48%
QMechanics | 5 |  | 72.5% | 33% | 83% | 83%
QMechanics | 6 |  | 77% | 40.5% | 70% | 25%
QMechanics | 7 |  | 76.5% | 45.5% | 44.5% | 33%
QMechanics | 8 |  | 71.5% | 38% | 76.5% | 30%
QMechanics | 9 |  | 67.5% | 43.5% | 74% | 54%
QMechanics | 10
QMechanics | 11
QMechanics | 12
Mobile | 1 |  | 74.3% | 33.7% | 77% | 56% | #N/A
Mobile | 2 |  | 72.7% | 28.7% | 91% | 83% | #N/A
Mobile | 3 |  | 84.3% | 19.3% | 78.7% | 67% | #N/A
Mobile | 4 |  | 83% | 48% | 70% | 39%
Mobile | 5 |  | 87% | 27.7% | 63% | 46%
Mobile | 6 |  | 80% | 29% | 69% | 48%
Mobile | 7 |  | 77.7% | 35.3% | 77% | 77%
Mobile | 8 |  | 71% | 44.3% | 79.3% | 77%
Mobile | 9 |  | 92.7% | 31% | 62% | 42%
Mobile | 10
Mobile | 11
Mobile | 12
Pirates | 1 |  | 72% | 12% | 81% | 57.5% | #REF!
Pirates | 2 |  | 84% | 4% | 43% | 65% | #N/A
Pirates | 3 |  | 73% | 14% | 94% | 92.5% | #N/A
Pirates | 4 |  | 95% | 10% | 92% | 100%
Pirates | 5 |  | 78% | 10% | 77% | 77%
Pirates | 6 |  | 82% | 12% | 80% | 22.5%
Pirates | 7 |  | 73% | 18% | 84% | 92.5%
Pirates | 8 |  | 81% | 33% | 91% | 100%
Pirates | 9 |  | 69% | 23% | 94% | 100%
Pirates | 10
Pirates | 11
Pirates | 12
Scalability | 1 |  | 30% | 19.5% | 81% | 58% | #N/A
Scalability | 2 |  | 48% | 27% | 91% | 100% | #N/A
Scalability | 3 |  | 57% | 28.5% | 91.5% | 81% | #N/A
Scalability | 4 |  | 68% | 19.5% | 98.5% | 65%
Scalability | 5 |  | 48% | 23.5% | 76% | 62%
Scalability | 6 |  | 39.5% | 31% | 84.5% | 79%
Scalability | 7 |  | 56.3% | 21.7% | 97.3% | 88%
Scalability | 8 |  | 60.7% | 19.3% | 81.3% | 53%
Scalability | 9 |  | 40% | 25.7% | 79% | 53%
Scalability | 10
Scalability | 11
Scalability | 12
Vikings | 1 |  | 66% | 20.5% | 80.5% | 40% | #N/A
Vikings | 2 |  | 76% | 16% | 90% | 76% | #N/A
Vikings | 3 |  | 70% | 13% | 81% | 65% | #N/A
Vikings | 4 |  | 81.5% | 15.5% | 93% | 100%
Vikings | 5 |  | 78% | 19.5% | 86.5% | 84%
Vikings | 6 |  | 81.5% | 22% | 77.5% | 100%
Vikings | 7 |  | 69.5% | 17% | 76% | 100%
Vikings | 8 |  | 83.5% | 15% | 77% | 100%
Vikings | 9 |  | 77% | 22.5% | 77% | 58%
Vikings | 10
Vikings | 11
Vikings | 12
DevOps | 4
DevOps | 5
DevOps | 6
DevOps | 7
DevOps | 8
DevOps | 9
DevOps | 10
DevOps | 11
DevOps | 12
Paracetamol | 4 |  | 0% | 0% | 45% | 100%
Paracetamol | 5 |  | 20% | 7% | 59% | 65%
Paracetamol | 6 |  | 88% | 0% | 58% | 65%
Paracetamol | 7 |  | 100% | 3% | 61% | 65%
Paracetamol | 8 |  | 55% | 11% | 33% | 30%
Paracetamol | 9 |  | 13% | 42% | 41% | 30%
Paracetamol | 10
Paracetamol | 11
Paracetamol | 12
Griffin

## DEV Bug Rate
SUM of Bug/Development Ratio | Month
Team | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total Result
Atrium | 10% | 13% | 21% | 25% | 29% | 36% | 28% | 34% | 30% |  |  |  | 226%
Byte Masters | 14.5% | 20% | 26% | 19.5% | 23.5% | 29% | 15% | 16% | 20% |  |  |  | 183.5%
Cerberus | 0% | 26% | 43% | 46% | 33% | 44% | 10% | 21% | 65% |  |  |  | 288%
Contech | 40% | 30% | 38% | 40% | 37% | 40% | 45% | 30% | 44% |  |  |  | 344%
Coruscant | 28% | 31% | 25% | 38% | 18% | 14% | 10% | 19% | 53% |  |  |  | 236%
DataForce | 18.3% | 32.7% | 38% | 37.5% | 24.3% | 32.7% | 14.3% | 24.3% | 49.7% |  |  |  | 271.8%
Design System | 4% | 2% | 7% | 14% | 0% | 39% | 17% | 11% | 17% |  |  |  | 111%
GhostBusters | 11% | 24% | 26% | 23% | 24% | 44% | 48% | 40% | 46% |  |  |  | 286%
Korriban | 27% | 41% | 51% | 28% | 22% | 40% | 23% | 33% | 31% |  |  |  | 296%
Kraken | 16% | 26% | 30% | 43% | 20% | 63% | 57% | 54% | 32% |  |  |  | 341%
Liron | 26% | 22% | 26% | 35% | 24% | 26% | 15% | 15% | 30% |  |  |  | 219%
Minerva | 0% | 4% | 13% | 1% | 3% | 3% | 1% | 1% | 3% |  |  |  | 29%
Mobile | 33.7% | 28.7% | 19.3% | 48% | 27.7% | 29% | 35.3% | 44.3% | 31% |  |  |  | 297%
Mobile Cartel | 52% | 16% | 6% | 92% | 33% | 16% | 53% | 71% | 24% |  |  |  | 363%
Mobile East | 28% | 34% | 20% | 27% | 31% | 20% | 33% | 35% | 21% |  |  |  | 249%
Mobile West | 21% | 36% | 32% | 25% | 19% | 50% | 20% | 27% | 48% |  |  |  | 278%
MythBusters | 24% | 17% | 20% | 39% | 42% | 37% | 43% | 36% | 41% |  |  |  | 299%
Paracetamol |  |  |  | 0% | 7% | 0% | 3% | 11% | 42% |  |  |  | 63%
Pirate Squad | 12% | 4% | 14% | 10% | 10% | 12% | 18% | 33% | 23% |  |  |  | 136%
Pirates | 12% | 4% | 14% | 10% | 10% | 12% | 18% | 33% | 23% |  |  |  | 136%
QMechanics | 17.5% | 20.5% | 23% | 31% | 33% | 40.5% | 45.5% | 38% | 43.5% |  |  |  | 292.5%
Samaritan | 14% | 15% | 32% | 18% | 27% | 31% | 11% | 10% | 18% |  |  |  | 176%
Scalability | 19.5% | 27% | 28.5% | 19.5% | 23.5% | 31% | 21.7% | 19.3% | 25.7% |  |  |  | 215.7%
ScaleUp | [6 empty] | 12% | 1% | 15% |  |  |  | 28%
Skeletors | 13% | 32% | 31% | 19% | 23% | 36% | 38% | 42% | 32% |  |  |  | 266%
Unix | 15% | 25% | 20% | 21% | 20% | 27% | 19% | 22% | 22% |  |  |  | 191%
Valorem | 17% | 18% | 25% | 40% | 20% | 15% | 4% | 7% | 12% |  |  |  | 158%
Vikings | 20.5% | 16% | 13% | 15.5% | 19.5% | 22% | 17% | 15% | 22.5% |  |  |  | 161%
Vikings - SMS | 13% | 8% | 7% | 11% | 13% | 16% | 14% | 5% | 23% |  |  |  | 110%
Vikings - WhatsApp | 28% | 24% | 19% | 20% | 26% | 28% | 20% | 25% | 22% |  |  |  | 212%

## 23Sum Per Team
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success | Done PBI Effort | Shipping accuracy formülleri güncellenecek, Release Efficiency metriği eklenecek | Success
Atrium | 10 | 62.8% | 62.8% | 8.4% | 84.6% | 100%
Atrium | 11 | 44.2% | 44.2% | 12.8% | 67.6% | 100%
Atrium | 12 | 49.1% | 49.1% | 8.1% | 78.5% | 50%
Unix | 10 | 48.5% | 62.6% | 22.8% | 100% | 100%
Unix | 11 | 46.9% | 55.5% | 15.7% | 111.4% | 100%
Unix | 12 | 62.5% | 67.2% | 9.1% | 98.6% | 50%
Samaritan | 10 | 43.3% | 76% | 20.6% | 96.1% | 50%
Samaritan | 11 | 34.4% | 54.9% | 12.1% | 85.6% | 50%
Samaritan | 12 | 43.1% | 66.7% | 6.3% | 96.3% | 100%
Contech | 10 | 86% | 89.3% | 40.6% | 74.5% | 100%
Contech | 11 | 87.6% | 74.1% | 34.2% | 69.3% | 0%
Contech | 12 | 81.7% | 93.6% | 26.8% | 68.3% | 100%
Kraken | 10 |  | 100% | 35.5% | 67.4% | 0%
Kraken | 11 |  | 86% | 10.2% | 80.1% | 100%
Kraken | 12 |  | 100% | 14.8% | 50% | 50%
Cerberus | 10 | 73.5% | 56.9% | 2.4% | 92.7% | 100%
Cerberus | 11 | 76% | 65.2% | 5.1% | 55.1% | 0%
Cerberus | 12 | 66.9% | 76.8% | 9.7% | 100.7% | 100%
Coruscant | 10 | 79% | 82.9% | 13.5% | 93% | 100%
Coruscant | 11 | 91.5% | 81.8% | 9.6% | 97.4% | 100%
Coruscant | 12 | 100.3% | 86.6% | 9.8% | 54.2% | 0%
Korriban | 10 | 67.5% | 72.6% | 15.2% | 76% | 50%
Korriban | 11 | 96.1% | 97.5% | 51.2% | 86.4% | 50%
Korriban | 12 | 69.1% | 82.1% | 17.1% | 47.2% | 50%
GhostBusters | 10 | 59.5% | 61.7% | 4.8% | 66.1% | 100%
GhostBusters | 11 | 85.3% | 95.7% | 14.9% | 84.7% | 100%
GhostBusters | 12 | 48.4% | 50.6% | 18.3% | 73.3%
MythBusters | 10 | 72.6% | 65.2% | 28.7% | 78.8% | 0%
MythBusters | 11 | 80.6% | 74.8% | 17.4% | 54.6% | 50%
MythBusters | 12 | 76% | 27.6% | 26.2% | 57.1%
Mobile West | 10 | 75.9% | 99% | 22.6% | 87.9% | 50%
Mobile West | 11 | 19.8% | 51% | 19.3% | 61.9% | 100%
Mobile West | 12 | 28.7% | 53% | 19.5% | 57% | 100%
Cartel | 10 | 91.5% | 100% | 17.8% | 82.3% | 100%
Cartel | 11 | 82.3% | 100% | 15.1% | 89.5% | 50%
Cartel | 12 | 54.8% | 100% | 5.5% | 71.2% | 100%
Mobile East | 10 | 75.9% | 99.2% | 22.6% | 87.9% | 50%
Mobile East | 11 | 19.8% | 51.3% | 19.3% | 61.9% | 100%
Mobile East | 12 | 41% | 39.3% | 10.6% | 74.5% | 100%
Pirate Squad | 10 | 45.3% | 60% | 5.4% | 90.8% | 50%
Pirate Squad | 11 | 58.8% | 57.1% | 5.3% | 96.4% | 100%
Pirate Squad | 12 | 60.4% | 68.5% | 3.7% | 94.1% | 100%
Skeletors | 10 | 50% | 72.4% | 33.7% | 108.9% | 100%
Skeletors | 11 | 92.6% | 58.4% | 41.1% | 83.5% | 100%
Skeletors | 12 | 74.5% | 52.1% | 55.8% | 86.6% | 100%
Liron | 10 | 85.6% | 77.9% | 36.7% | 95.7% | 100%
Liron | 11 | 96.7% | 77.6% | 21.6% | 102.4% | 100%
Liron | 12 | 86.1% | 60% | 28.8% | 81.3% | 0%
Valorem | 10 | 0% | 57.3% | 30.1% | 87.1% | 50%
Valorem | 11 | 0% | 42.6% | 16.8% | 76.4% | 0%
Valorem | 12 | 0% | 46.8% | 40.2% | 61.5% | 50%
Vikings - SMS | 10 | 47.7% | 86.5% | 5.9% | 112.6% | 100%
Vikings - SMS | 11 | 63.9% | 34.8% | 5.6% | 93.6% | 100%
Vikings - SMS | 12 | 54.9% | 82.1% | 1.7% | 90% | 100%
Vikings - WhatsApp | 10 | 60.9% | 56.6% | 12% | 74.9% | 100%
Vikings - WhatsApp | 11 | 52% | 49.6% | 1.8% | 91.9% | 50%
Vikings - WhatsApp | 12 | 47.1% | 59.1% | 4.9% | 89.4% | 100%
Byte Masters | 10 | 46% | 69% | 22% | 98% | 75%
Byte Masters | 11 | 41% | 55% | 14% | 98% | 75%
Byte Masters | 12 | 53% | 67% | 8% | 97% | 75%
DataForce | 10 | 73.3% | 70.8% | 10.3% | 87.2% | 83%
DataForce | 11 | 87.9% | 81.5% | 22% | 79.6% | 50%
DataForce | 12 | 78.8% | 81.8% | 12.2% | 67.4% | 50%
QMechanics | 10 | 66% | 63.5% | 16.8% | 72.5% | 50%
QMechanics | 11 | 83% | 85.2% | 16.2% | 69.7% | 75%
QMechanics | 12 | 62.2% | 39.1% | 22.2% | 65.2% | #DIV/0!
Mobile | 10 | 83.7% | 99.5% | 20.2% | 85.1% | 75%
Mobile | 11 | 51.1% | 75.5% | 17.2% | 75.7% | 75%
Mobile | 12 | 41.7% | 76.5% | 12.5% | 64.1% | 100%
Pirates | 10 | 45.3% | 60% | 5.4% | 90.8% | 50%
Pirates | 11 | 58.8% | 57.1% | 5.3% | 96.4% | 100%
Pirates | 12 | 60.4% | 68.5% | 3.7% | 94.1% | 100%
Scalability | 10 | 67.8% | 75.2% | 35.2% | 102.3% | 100%
Scalability | 11 | 94.7% | 68% | 31.4% | 92.9% | 100%
Scalability | 12 | 80.3% | 56.1% | 42.3% | 83.9% | 50%
Vikings | 10 | 54.3% | 71.5% | 8.9% | 93.8% | 100%
Vikings | 11 | 57.9% | 42.2% | 3.7% | 92.7% | 75%
Vikings | 12 | 51% | 70.6% | 3.3% | 89.7% | 100%

## Planning Accuracy Pivot
AVERAGE of Shipping Accuracy | Month
Team | 1 | Total Result
Atrium | 48% | 48%
Byte Masters | 56% | 56%
Contech | 70% | 70%
DataForce | 93% | 93%
Design System | 0% | 0%
GhostBusters | 48% | 48%
Kraken | 100% | 100%
Liron | 36% | 36%
Minerva | 90% | 90%
Mobile | 74.3% | 74.3%
MythBusters | 53% | 53%
Pirates | 72% | 72%
Scalability | 30% | 30%
Valorem | 29% | 29%
Vikings | 66% | 66%
Total Result | 57.69% | 57.69%

## BugDev Pivot
Bug/Development Ratio | - multiple -
Team | AVERAGE of Bug/Development Ratio
Minerva | 5.2%
Vikings - SMS | 13.12%
ScaleUp | 13.5%
Design System | 13.88%
Pirate Squad | 15.11%
Pirates | 15.11%
Paracetamol | 15.75%
Vikings | 17.31%
Valorem | 17.56%
Samaritan | 19.56%
Byte Masters | 20.39%
Unix | 21.22%
Vikings - WhatsApp | 23.56%
Scalability | 23.75%
Liron | 24.33%
Atrium | 25.11%
Coruscant | 26.22%
Mobile East | 27.67%
QMechanics | 29.07%
Skeletors | 29.56%
DataForce | 29.69%
Mobile West | 30.89%
Mobile | 31.59%
GhostBusters | 31.78%
Cerberus | 31.86%
Kraken | 32.86%
Korriban | 32.89%
MythBusters | 33.22%
Mobile Cartel | 36.5%
Contech | 37.38%
Total Result | 24.75%

## Sprint Goal Pivot
AVERAGE of Sprint Goal Success | Month
Team | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total Result
Atrium | 65% | 77.5% | 95% | 85% | 100% | 42.5% | 65% | 65% | 25% |  |  |  | 68.89%
Byte Masters | 83% | 48% | 53% | 65% | 61% | 100% | 65% | 88% | 48% |  |  |  | 67.89%
Cerberus | 100% | 100% | 53% | 100% | 77% | 100% | 100% | 100% | 65% |  |  |  | 88.33%
Contech | 100% | 93% | 90% | 85% | 57.5% | 15% | 30% | 15% | 100% |  |  |  | 65.06%
Coruscant | 15% | 50% | 90% | 30% | 100% | 65% | 100% | 65% | 30% |  |  |  | 60.56%
DataForce | 72% | 72% | 73% | 53% | 85% | 77% | 77% | 86% | 65% |  |  |  | 73.33%
Design System | 57.5% | 65% | 100% | 100% | 100% | 100% | 53.3% | 100% | 100% |  |  |  | 86.2%
GhostBusters | 22.5% | 65% | 92.5% | 65% | 100% | 0% | 50% | 30% | 50% |  |  |  | 52.78%
Korriban | 100% | 100% | 77% | 30% | 77% | 65% | 30% | 100% | 100% |  |  |  | 75.44%
Kraken | 71% | 92.5% | 92.5% | 50% | 85% | 30% | 65% | 30% | 77% |  |  |  | 65.89%
Liron | 50% | 100% | 62% | 50% | 58% | 65% | 100% | 65% | 30% |  |  |  | 64.44%
Minerva | 100% | 100% | 100% | 65% | 100% | 100% | 100% | 100% | 100% |  |  |  | 96.11%
Mobile | 56% | 83% | 67% | 39% | 46% | 48% | 77% | 77% | 42% |  |  |  | 59.44%
Mobile Cartel | 66.6% | 100% | 50% | 30% | 30% | 50% | 30% | 65% | 30% |  |  |  | 50.18%
Mobile East | 33% | 100% | 100% | 57.5% | 53.3% | 65% | 100% | 100% | 65% |  |  |  | 74.87%
Mobile West | 67% | 50% | 50% | 30% | 53.3% | 30% | 100% | 65% | 30% |  |  |  | 52.81%
MythBusters | 92.5% | 65% | 57.5% | 30% | 65% | 50% | 15% | 30% | 57.5% |  |  |  | 51.39%
Paracetamol |  |  |  | 100% | 65% | 65% | 65% | 30% | 30% |  |  |  | 59.17%
Pirate Squad | 57.5% | 65% | 92.5% | 100% | 77% | 22.5% | 100% | 100% | 100% |  |  |  | 79.39%
Pirates | 57.5% | 65% | 92.5% | 100% | 77% | 22.5% | 92.5% | 100% | 100% |  |  |  | 78.56%
QMechanics | 58% | 65% | 75% | 48% | 83% | 25% | 33% | 30% | 54% |  |  |  | 52.33%
Samaritan | 100% | 30% | 53% | 65% | 92.5% | 100% | 65% | 100% | 65% |  |  |  | 74.5%
Scalability | 58% | 100% | 81% | 65% | 62% | 79% | 88% | 53% | 53% |  |  |  | 71%
ScaleUp | [6 empty] | 100% | 30% | 65% |  |  |  | 65%
Skeletors | 65% | 100% | 100% | 100% | 65% | 92.5% | 65% | 65% | 65% |  |  |  | 79.72%
Unix | 65% | 30% | 53% | 65% | 30% | 100% | 65% | 76.6% | 30% |  |  |  | 57.18%
Valorem | 85% | 100% | 57.5% | 100% | 58% | 50% | 65% | 100% | 65% |  |  |  | 75.61%
Vikings | 40% | 76% | 65% | 100% | 84% | 100% | 100% | 100% | 58% |  |  |  | 80.33%
Vikings - SMS | 50% | 100% | 100% | 100% | 67% | 100% | 100% | 100% | 100% |  |  |  | 90.78%
Vikings - WhatsApp | 30% | 51% | 30% | 100% | 100% | 100% | 100% | 100% | 0% |  |  |  | 67.89%
Total Result | 64.9% | 76.54% | 75.07% | 69.22% | 72.71% | 64.1% | 73.19% | 72.19% | 59.98% |  |  |  | 69.72%
Note on H21: @eda.bereket@useinsider.com bura 3 sprint hesaplanacak şu an yanlış burası _Assigned to eda.bereket@useinsider.com_ -Görkem Duymaz

## Detail26-Vikings - SMS-6
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - SMS | 6

## Detail11-Vikings-2
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings | 2 |  | 76% | 16% | 90% | 61%

## Shipping Accuracy Pivot
AVERAGE of Shipping Accuracy | Month
Team | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total Result
Atrium | 48% | 63% | 73% | 64% | 89% | 35% | 57% | 69% | 61% |  |  |  | 62.11%
Byte Masters | 56% | 65% | 64% | 68% | 68% | 73% | 76.5% | 69% | 62.5% |  |  |  | 66.89%
Contech | 70% | 47% | 81% | 69% | 82% | 80% | 73% | 64% | 80% |  |  |  | 71.78%
DataForce | 93% | 93.7% | 93% | 88.3% | 88.3% | 88% | 81% | 91% | 89.7% |  |  |  | 89.56%
Design System | 0% | 7% | 19% | 0% | 0% | 26% | 20% | 8% | 25% |  |  |  | 11.67%
Kraken | 100% | 61% | 83% | 100% | 100% | 93% | 97% | 100% | 100% |  |  |  | 92.67%
Minerva | 90% | 93% | 101% | 97% | 96% | 94% | 99% | 104% | 93% |  |  |  | 96.33%
Mobile | 74.3% | 72.7% | 84.3% | 83% | 87% | 80% | 77.7% | 71% | 92.7% |  |  |  | 80.3%
Paracetamol |  |  |  | 0% | 20% | 88% | 100% | 55% | 13% |  |  |  | 46%
Pirates | 72% | 84% | 73% | 95% | 78% | 82% | 73% | 81% | 69% |  |  |  | 78.56%
QMechanics | 50.5% | 69% | 63.5% | 82% | 72.5% | 77% | 76.5% | 71.5% | 67.5% |  |  |  | 70%
Scalability | 30% | 48% | 57% | 68% | 48% | 39.5% | 56.3% | 60.7% | 40% |  |  |  | 49.72%
Valorem | 29% | 39% | 38% | 64% | 55% | 46% | 38% | 82% | 89% |  |  |  | 53.33%
Vikings | 66% | 76% | 70% | 81.5% | 78% | 81.5% | 69.5% | 83.5% | 77% |  |  |  | 75.89%
Total Result | 59.91% | 62.95% | 69.22% | 68.56% | 68.7% | 70.21% | 71.04% | 72.12% | 68.53% |  |  |  | 68.01%
Sub-teams
AVERAGE of Shipping Accuracy | Month
Team | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total Result
Cerberus | 96% | 99% | 100% | 100% | 80% | 70% | 72% | 100% | 100% |  |  |  | 90.78%
Coruscant | 92% | 84% | 79% | 85% | 92% | 102% | 92% | 82% | 74% |  |  |  | 86.89%
DevOps
GhostBusters | 48% | 64% | 62% | 73% | 70% | 90% | 76% | 85% | 68% |  |  |  | 70.67%
Korriban | 90% | 98% | 100% | 80% | 93% | 92% | 79% | 91% | 95% |  |  |  | 90.89%
Liron | 36% | 58% | 58% | 47% | 58% | 34% | 35% | 48% | 59% |  |  |  | 48.11%
Mobile Cartel | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  |  | 100%
Mobile East | 64% | 52% | 85% | 53% | 67% | 33% | 72% | 79% | 90% |  |  |  | 66.11%
Mobile West | 59% | 66% | 68% | 96% | 94% | 83% | 61% | 34% | 88% |  |  |  | 72.11%
MythBusters | 53% | 74% | 65% | 91% | 75% | 64% | 77% | 58% | 67% |  |  |  | 69.33%
Pirate Squad | 72% | 84% | 73% | 95% | 78% | 82% | 73% | 81% | 69% |  |  |  | 78.56%
Samaritan | 67% | 71% | 73% | 67% | 78% | 92% | 74% | 73% | 69% |  |  |  | 73.78%
ScaleUp | [6 empty] | 76% | 74% | 27% |  |  |  | 59%
Skeletors | 24% | 38% | 56% | 34% | 38% | 45% | 58% | 60% | 34% |  |  |  | 43%
Unix | 45% | 59% | 55% | 69% | 58% | 54% | 79% | 65% | 56% |  |  |  | 60%
Vikings - SMS | 73% | 88% | 84% | 79% | 71% | 83% | 67% | 90% | 79% |  |  |  | 79.33%
Vikings - WhatsApp | 59% | 64% | 56% | 84% | 75% | 80% | 72% | 64% | 75% |  |  |  | 69.89%
Total Result | 65.2% | 73.27% | 74.27% | 76.87% | 75.13% | 73.6% | 72.69% | 74% | 71.88% |  |  |  | 72.99%

## Detail28-Vikings - WhatsApp-6
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 6 |  | 80% | 28% | 85% | 100%

## Detail27-Vikings - WhatsApp-5
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 5 |  | 75% | 26% | 88% | 100%

## Detail25-Vikings - WhatsApp-5
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 5 |  | 66% | 26% | 88% | 100%

## Detail24-Vikings - WhatsApp-5
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 5 |  | 66% | 26% | 88% | 100%

## Detail23-Vikings - WhatsApp-4
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 4 |  | 84% | 20% | 91% | 100%

## Detail22-Vikings - WhatsApp-6
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 6

## Detail21-Vikings - WhatsApp-5
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 5 |  | 66% | 26% | 88% | 100%

## Detail20-Vikings - WhatsApp-5
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 5 |  | 66% | 26% | 88% | 100%

## Detail19-Vikings - WhatsApp-5
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 5 |  | 66% | 26% | 88% | 100%

## Detail18-Vikings - WhatsApp-6
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 6

## Detail17-Vikings - WhatsApp-5
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 5 |  | 66% | 26% | 88% | 100%

## Detail16-Vikings - WhatsApp-5
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Vikings - WhatsApp | 5 |  | 85% | 26% | 88% | 100%

## Detail10-Minerva-3
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Minerva | 3 |  | 50% | 13% | 101% | 100%

## Detail8-Atrium-2
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Atrium | 2 |  | 63% | 13% | 71% | 77.5%

## Detail7-Pirates-2
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
Pirates | 2

## Detail6-DataForce-1
Team | Month | Release Efficiency | Shipping Accuracy | Bug/Development Ratio | Planning Accuracy | Sprint Goal Success
DataForce | 1

## Liron Indv. SPA Pivot
Data
Individual Committed Effort | 10 | SUM of 15 | SUM of 16 | SUM of 17 | SUM of 18 | SUM of 19
Arda Berrun Karaca
Aziza Kasenova
Fatih Ertugral | 55 | 56 | 42 | 50 | 49 | 51
Sahin Deniz
Samet Sevindi
Samet Yıldırım | 34 | 32 | 31 | 35
Semih Ünal | 47 | 52 | 39 | 51 | 43 | 15
Tugay İlik
Umur Akbulut | 23 | 31 | 32 | 39 | 35
Total Result | 159 | 171 | 144 | 175 | 127 | 66
Individual Done Effort | 10 | SUM of | SUM of | SUM of | SUM of | SUM of
Arda Berrun Karaca | 0 | 0 | 0 | 0 | 0 | 0
Aziza Kasenova | 0 | 0 | 0 | 0 | 0 | 0
Fatih Ertugral | 55 | 48 | 43 | 47 | 47 | 51
Sahin Deniz | 0 | 0 | 0 | 0 | 0 | 0
Samet Sevindi | 0 | 0 | 0 | 0 | 0 | 0
Samet Yildirim | 33 | 31 | 36 | 14 | 0 | 0
Semih Unal | 47 | 61 | 44 | 52 | 39 | 18
Tugay İlik | 3 | 0 | 0 | 0 | 0 | 0
Umur Akbulut | 23 | 35 | 24 | 39 | 27 | 0
Grand Total | 161 | 175 | 147 | 152 | 113 | 69
| July | Aug | Sep
Fatih Ertugral | 92.86% | 98.19% | 97.96%
Semih Unal | 108.7% | 107.4% | 105.3%
Umur Akbulut | 106.5% | 87.5% | 0%

## Skeletors Indv. SPA Pivot
Data
Individual Committed Effort | SUM of 14 | SUM of 15 | SUM of 16 | SUM of 17 | SUM of 18 | SUM of 19 | SUM of 20
Ahmet Aslan
Aziza Kasenova | 52 | 33 | 29 | 32 | 34 | 46 | 42
Bilge Bavlı |  | 3 | 12 | 15 | 17 | 17 | 17
Mert Adatepe | 41 | 39 | 33 | 43 | 42 | 42 | 38
Tugay İlik | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ugurcan Ertek | 50 | 50 | 20 | 53 | 46 | 52 | 50
Yasin Can Tarlan | 53 | 54 | 20 | 56 | 55 | 46 | 48
Total Result | 196 | 179 | 114 | 199 | 194 | 203 | 195
Individual Done Effort | SUM of | SUM of | SUM of | SUM of | SUM of | SUM of | SUM of
Ahmet Aslan | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aziza Kasenova | 47 | 31 | 32 | 27 | 39 | 40 | 45
Bilge Bavlı | 0 | 6 | 12 | 15 | 17 | 20 | 20
Mert Adatepe | 42 | 42 | 28 | 23 | 34 | 30 | 15
Tugay İlik | 0 | 0 | 1 | 0 | 0 | 0 | 0
Ugurcan Ertek | 50 | 53 | 5 | 37 | 33 | 46 | 50
Yasin Can Tarlan | 27 | 56 | 20 | 4 | 50 | 41 | 55
Grand Total | 166 | 188 | 98 | 106 | 173 | 177 | 185
| July | Aug | Sep
Mert Adatepe | 105.1% | 44.13% | 46.74%
Aziza Kasenova | 92.16% | 193.3% | 188.2%
Uğurcan Ertek | 0% | 0% | 0%
Yasin Can Tarlan | 83% | 53.77% | 93.77%
Bilge Bavlı | 100% | 100% | 108.8%

## ScaleUp Indv. SPA Pivot
Data
Individual Committed Effort | SUM of 14 | SUM of 15 | SUM of 16 | SUM of 17 | SUM of 18 | SUM of 19 | SUM of 20
Ahmet Aslan | 45 | 39 | 8 | 39 | 44 | 45 | 43
Arda Berrun Karaca | 19 | 21 | 26 | 29 | 22 | 26 | 30
Beyza Ozbek | 47 | 50 |  | 52 | 50 | 58 | 52
Eda Taşyürek | 5 | 8 |  | 5 | 10 | 9 | 10
Oktay Yedibela | 13 | 8 |  | 13 | 13 | 11 | 16
Şahin Deniz | 52 | 48 | 44 | 47 | 37 | 48 | 40
Total Result | 181 | 174 | 78 | 185 | 176 | 197 | 191
Ahmet Aslan | 32 | 39 | 8 | 34 | 0 | 34 | 45
Arda Berrun Karaca | 19 | 21 | 28 | 23 | 31 | 37 | 21
Beyza Ozbek | 47 | 13 | 26 | 31 | 29 | 58 | 39
Eda Taşyürek | 5 | 5 | 4 | 3 | 5 | 11 | 10
Oktay Yedibela | 13 | 3 | 0 | 0 | 13 | 14 | 11
Şahin Deniz | 52 | 48 | 18 | 49 | 8 | 48 | 50
Grand Total | 168 | 129 | 84 | 140 | 86 | 202 | 176
ü
üğ
| July | Aug | Sep
Ahmet Aslan | 0% | 0% | 0%
Arda Berrun Karaca | 48.03% | 204.5% | 76.34%
Şahin Deniz | 100% | 72.58% | 60.81%

## Detail12
Individual Committed Effort
Ahmet Aslan | 34 | 46 | 47 | 39 | 18 | 44 | 42 | 31 | 32
Yasin Can Tarlan | 54 | 52 | 47 | 50 | 59 | 52 | 50 | 29 | 46
Tugay İlik | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ugurcan Ertek | 45 | 50 | 53 | 52 | 58 | 53 | 50 | 19 | 37
Mert Adatepe | 40 | 39 | 42 | 38 | 46 | 40 | 41 | 18 | 34

## Detail13
Individual Committed Effort
Aziza Kasenova | 36 | 41 | 39 | 34 | 18 | 32 | 34 | 24
Fatih Ertugral | - | 44 | 55 | 54 | 55 | 57 | 46 | 16
Sahin Deniz | 42 | 41 |  | 46 | 49 | 45 | 42 | 18
Yaman Ozdemir | 45 | 41 | 45 | 48 | 49 | 46 | 37 | 19
Tugay İlik | - | - | - | 8 |  |  | 8
Semih Ünal | 42 | 42 | 45 | 34 | 40 | 42 | 23 | 14
Samet Sevindi |  | - | 5
Samet Yıldırım | 15 | 19 | 24 | 26 | 23 | 25 | 27 | 12